GAS PROCESSING & METHANOL COMPLEX PROJECT NO. xxxxxx

| Project | FEED for Gas Gathering Pipelines & Associated Infrastructure |
| --- | --- |
| Client | Brass Fertilizer and Petrochemical Company Limited |
| Originating Company | Epic Atlantic Limited |
| Document Title | Pipeline Decommissioning & Abadonment Philosophy |
| Document Number | EA-BFPCL-GPMC-GGPL-FEED-GEN-RPT-005 |
| Document Revision | R01 |
| Document Status | Issued For Review |
| Coordinator | Aloy Duru |
| Security Classification | Restricted |
| Issue Date | 27 Apr 2026 |

Pipeline Decommissioning & Abandonment Philosophy

| R01 | 27 Apr 2026 | Issued for Client Review | W. Irem | Kazeem Yusuff | A. Duru |  |
| --- | --- | --- | --- | --- | --- | --- |
| Rev # | Issue Date | Status Description | Originator | Reviewed | Endorsement (Epic Atlantic) | Approval (BFPCL) |

Revision History

| Rev. No. | Date | Description of Revision |
| --- | --- | --- |
| P0 | 27 Apr 2026 | For Review |

Revision Philosophy:

- All documents for review shall be issued at R01, with subsequent R02, R03, etc as required.

- All documents approved for issue or approved for design shall be issued at A01 with subsequent A02, A03, etc. as required. (Management of Change is required for A02, A03, etc.)

for the subsequent project phases, post FEED, it is expected that:

- All Detailed Design documents for review shall be issued at D01, with subsequent D02, D03, etc. as required.

- All documents approved for construction shall be issued at C01 with subsequent C02, C03, etc. as required. (Management of Change is required for C02, C03, etc.)

- All approved “As-Built” documents shall be issued at Z01, with subsequent Z02, Z03, etc as required. (Use versions Z01.1, Z01.2, Z01.3, etc to review the “As-Built” document to Z02).

Restricted

This document is made available subject to the condition that the recipient will neither use nor disclose the contents except as agreed in writing with the copyright owner.  Copyright is vested in Brass Fertilizer and Petrochemical Company Limited (BFPCL) © All rights reserved.

Neither the whole nor any part of this document may be reproduced or distributed in any form or by any means (electronic, mechanical, reprographic, recording, or otherwise) without the prior written consent of the copyright owner.

Summary Page

| Client: | Brass Fertilizer & Petrochemical Company Limited |  |
| --- | --- | --- |
| Project: | Gas Processing & Methanol Complex | Project No. 11998A |
| Facility: | Gas Gathering Pipelines & Associated Infrastructure | Doc No. EA-BFPCL-GPMC-GGPL-FEED-GEN-RPT-001-R01 |

The administration of this document is in respect of FEED Package Overview for Gas Gathering Pipelines & Associated Infrastructure for the Gas Processing & Methanol Plant Project of BFPCL. The document, in consideration of relational design elements & concepts, is a summary of the of the key features of the FEED, and its specific deliverables required by regulators, - which collectively forms the technical and statutory basis for the project’s Financial Close, and the subsequent EPC processes implementation. The Pipelines will be implemented in two phases, - starting with BBOU & ELEP as Phase 1and followed by NUNR, SEIB & OPUG as Phase 2. The focus of the present FEED is on Phase 1, while Phase 2 will be implemented later. Related to this scenario of two phases, is the opportunity to flow 1 BSCFD through the pipeline system to the 1 BSCFD gas hub proposed at Akabel as a separate project. The report has relied on and used data and reference documents provided by the client, and if further documents and information become available, Epic Atlantic reserves the right to update the opinion set out in this report. For better appreciation, this document should be read in conjunction with the references listed below, which are the key components of the key components of the FEED.

KEYWORDS: BASIS OF DESIGN, PIPELINE, MANIFOLD, PLATFORM, MULTIPHASE FLOW, ROW, PTS

| REferences |  |
| --- | --- |
| Document No. | Description |
| EA-BFPCL-GPMC-GGPL-FEED-GEN-RPT-001-R01 | Basis of Design |
| EA-BFPCL-GPMC-GGPL-FEED-GEN-RPT-0011-R01 | Design and Operating Philosophy |
| EA-BFPCL-GPMC-GGPL-FEED-PSE-RPT-001 | Upstream Gas Gathering Concept Select & Revalidation Report |
|  | Materials Specification & Corrosion Management |
|  | Flow Assurance Report |
|  | FISAS ESIA Draft Report (November 2020) |

Table of Contents

Project Information, Terms, Abbreviations, and Definitions	7

Project Information – General	7

Project Information – General (Contd)	8

Definition of Terms	9

Abbreviations	9

Abbreviations (contd.)	10

Abbreviations (contd.)	11

1.	Introduction	12

1.1.	Background Information	12

1.2.	The Project Phases	12

1.3.	The 1 BSCFD Gas Hub Opportunity	14

1.4.	Purpose of Document	14

2.	Battery Limit, and Scope of Work	15

2.1.	Battery Limit	15

BBOU Platform	15

ELEP Platform	15

Akabel Facility	15

2.2.	Scope of Work	16

3.	Project Engineering	17

3.1.	Facilities Highlight	17

3.2.	Interfaces	17

3.3.	Project Cost Estimate	18

3.4.	The Phase 1 Pipelines Route / Right of Way	19

3.5.	The Phase 1 Geotechnical Survey	20

3.6.	Design Criteria	21

3.6.1.	Design Life	21

3.6.2.	Design Units	21

3.6.3.	Cost Effectiveness & Life Cycle Cost	21

3.6.4.	Future Expansion - Phase-2 Facilities	21

3.6.5.	Future Expansion – Proposed 1 Bscfd Gas Hub at Akabel	21

3.6.6.	Buoyancy Combat	21

3.6.7.	Flood Combat	21

3.6.8.	Standardisation	22

3.7.	Local Requirements	22

3.7.1.	Language	22

3.7.2.	Local Content Requirement	22

3.8.	Checklist of NUPRC Requirements	22

3.9.	Checklist of OPL Application Requirements	23

4.	Design Basis & Design Data	27

4.1.	The DCQ 310 Production Forecast	27

4.2.	Water Production Forecast	28

4.3.	The Flow Properties & Fluid Composition	28

4.4.	The Nodal Production Forecast	29

5.	Process Systems Design	30

5.1.	Validation of Pipeline Size – Phase 1 Facilities	30

5.2.	Pipeline Network Simulation with Different Pipeline Sizes	31

5.3.	32

5.4.	Flow Assurance	33

5.4.1.	Steady State	33

5.4.2.	Slugging Assessment	33

5.4.3.	Turndown Assessment	33

5.4.4.	Hydrate Assessment	34

5.4.5.	Cooldown & Pipeline Depressurization Results	34

5.4.6.	Pigging Results	35

5.5.	Process Design	35

5.5.1.	Highlights	35

5.5.2.	Preliminary Specifications of the Slug Catcher	35

5.5.3.	Key Process Deliverables	36

6.	Materials Specifications & Corrosion Management	37

6.1.	Specific Key Drivers	37

6.2.	Materials Selection Philosophy	37

6.3.	Pipe Material Types and Selection Processes	38

6.4.	Corrosion Analysis	39

6.4.1.	Fluid Composition / Internal Corrosion	40

6.5.	Line Pipe Materials Specification	42

6.5.1.	The Chemical Composition	43

6.5.2.	43

6.5.3.	Information and Data for the Pipelines	44

6.5.4.	Procurement / Manufacturing Specification	45

6.6.	Piping Materials Specification	45

6.6.1.	Piping Classes	46

6.7.	Equipment Materials Specification	46

6.8.	Corrosion Inhibitor Specification	46

6.8.1.	Codes and Standards	47

6.8.2.	Injection Provision	47

6.8.3.	Operation Practice	47

6.9.	CP Specification	48

6.9.1.	Sacrificial Anode.	48

6.10.	Impressed Current Cathodic Protection Type Specification.	48

6.10.1.	Groundbed -Deepwell	48

6.11.	Key Materials Specification and Corrosion Management Deliverables	49

7.	Pipeline Engineering	50

7.1.	Specific Key Drivers / Decissions	50

7.2.	The Pipelines	50

7.3.	Route Survey Map / Overall Location Plan	51

7.4.	Pipeline Crossing Schedule	52

7.5.	Pipeline Technical Specifications	53

7.6.	The Pig Launcher & Receiver	56

7.6.1.	General	56

7.6.2.	PIG Trap System Component	56

7.6.3.	Supports	56

7.6.4.	Branch Connections	57

7.6.5.	End Closure	57

7.6.6.	Materials	57

7.6.7.	Fabrication	57

7.6.8.	Inspection and Testing	58

7.6.9.	Surface Preparation and Finish	58

7.6.10.	Pipeline Pig Passage Detector	58

7.6.11.	Nameplates and Labelling	59

7.7.	Key Pipeline Engineering Deliverables	59

8.	Mechanical & Piping	60

8.1.	Specific Key Drivers / Decissions	60

8.2.	Scope	60

8.3.	The Manifolds	61

8.4.	63

8.5.	Key Mechanical & Piping Deliverables	64

9.	Structural Design / Civil and Foundation Engineering	65

9.1.	Specific Key Drivers / Decissions	65

10.	Electrical Engineering	66

10.1.	Specific Key Drivers / Decissions	66

10.2.	The Power Supply Schematics	66

10.3.	The Power System Layout	67

10.4.	Single Line Diagrams	71

10.5.	Key Electrical Engineering Deliverables	71

11.	Control & Instrumentation & Telecommunications Engineering	74

11.1.	Specific Key Drivers / Decissions	74

11.2.	Key Control & Instrumentation and Telecoms Engineering Deliverables	74

12.	Technical HSE and Loss Prevention	77

12.1.	Specific Key Drivers / Decissions	77

12.2.	Key Technical Safety and Loss Prevention Deliverables	77

# Project Information, Terms, Abbreviations, and Definitions

## Project Information – General

| 1.0 | Employer | BRASS FERTILIZER & PETROCHEMICAL COMPANY LIMITED (BFPCL) |
| --- | --- | --- |
| 2.0 | PMC | TATA CONSULTING ENGINEERS LIMITED (TCE) |
| 3.0 | EPCC (CONTRACTOR) | CHINA TIANCHEN ENGINEERING CORPORATION (TCC) |
| 4.0 | Project Title | Gas Processing and Methanol Complex |
| 5.0 | Location | Akabel, Brass Island. The project site is about 85 km South West of Port Harcourt, 70 km South of Yenagoa and 90 km West of Bonny Island. |
| 5.1 | State | Bayelsa State, Nigeria |
| 5.2 | Nearest Air Port and distance | Port Harcourt Airport (PHC), 80 km Yenagoa Airport (BIA), 75 km |
| 5.3 | Nearest Port | Port Harcourt (Onne) |
| 5.4 | Nearest Railway Station & distance | - |
| 5.5 | Highway and distance | Connected through water way only. Road connection does not exist. |
| 5.6 | Important Town and distance | Yenagoa, Nigeria& 67 km |
| 5.7 | Altitude Above Mean Sea Level | 9 m |
| 5.8 | Atmospheric pressure |  |
|  | Average | 1,013 mbar |
| 6.0 | Ambient Air Temperatures | (Refer Note-5,6) |
| 6.1 | Maximum | 38°C |
| 6.2 | Minimum | 18°C |
| 6.3 | Average | 23°C |
| 6.4 | Summer Design Wet Bulb Temp | 28°C |
| 6.5 | Winter Design Wet Bulb Temp | 15°C |
| 6.6 | MDMT | 15°C |

| 6.7 | Swamp temperature | 25°C (23°C to be used wherever a margin is required) |
| --- | --- | --- |
| 6.8 | Ground temperature | 25 - 27.5 °C |
| 6.9 | Black-bulb temperature: | 80°C |
| 7.0 | Relative Humidity |  |
| 7.1 | Maximum | 95 % |
| 7.2 | Minimum | 51 % |
| 7.3 | Average | 73 % |
| 8.0 | Rainfall Data |  |
| 8.1 | Average annual rainfall | 3,800 mm |
| 8.2 | Max daily rainfall: | 180 mm |
| 8.3 | Mean max. Hourly rainfall | 100 mm |
| 9.0 | Transport |  |
| 9.1 | Name of the highway near which the plant is located | Connected through water way only. Road connection does not exist. |
| 9.2 | Access road | - |
| 9.3 | Railway (Gauge) | - |
| 10.0 | Wind Data |  |
| 10.1 | Design Wind Velocity | 35.6 m/sec (Note-1) |
| 10.2 | Wind Direction | Note-2 |
| 11.0 | Seismic Data |  |
| 11.1 | Earthquake Zone | Note-3 |
| 12.0 | High Flood Level (HFL) | * |
| 13.0 | Natural Ground Level | * |
| 14.0 | Slope | * |
| 15.0 | Drainage | * |
| 16.0 | Design temperature for Electrical equipment | 40°C |

## Project Information – General (Contd)

## Definition of Terms

| TERMS | DEFINITIONS |
| --- | --- |
| BFPCL | Brass Fertilizer & Petrochemical Limited. |
| SPDC | Shell Petroleum Development Company Nig. Limited |
| Employer | Party (Usually BFPCL) that initiates the project and ultimately pays for its design and construction. The Employer will generally specify the technical requirements. The Employer may also include an agent or consultant authorized to act for and on behalf of, the Employer. |
| Engineer | The party that carries out the FEED Engineering of the project. |
| Manufacturer/Supplier | Party, which manufactures or supplies equipment and services to perform the duties specified by the Contractor. |
| Shall | The word ‘shall’ indicate a mandatory requirement. |
| Should | The word ‘should’ indicate a recommendation. |
| Measuring Range | Range defined by LRL and URL within which the limits of uncertainty of the measuring instrument are specified (the capability of the instrument). |
| On-Line Instruments | Instruments connected to process and utility lines or equipment via primary isolation valves. |
| Project | Front End Engineering Design for Gas Gathering Pipelines (Phase1) |

## Abbreviations

| Abbreviation | Meaning |
| --- | --- |
| AASHTO | American Association of state Highway Transportation Officials |
| AGEF | Above Ground End Facilities |
| ALARP | As Low as Reasonably Practicable |
| API | American Petroleum Institute |
| ASTM | American Society of Testing and Materials |
| BOD | Basis Of Design |
| CP | Cathodic Protection |
| CPT | Cone Penetrometer Test |
| CTMS | Custody Transfer Metering Station |
| DB&B | Double Block and Bleed |
| DCQ | Daily Contractual Quantity |

## Abbreviations (contd.)

| Abbreviation | Meaning |
| --- | --- |
| DEP | Design and Engineering Practice |
| ESD | Emergency Shutdown |
| ESDV | Emergency Shutdown Valve |
| FEED | Front End Engineering Design |
| FGS | Fire, Gas and Smoke detection systems |
| GPP | Gas Processing Plant |
| GTG | Gas Turbine Generators |
| HAZID | Hazard Identification |
| HAZOP | Hazard Operability |
| HEMP | Hazards and Effects Management Process |
| HFE | Human Factors Engineering |
| HPU | Hydraulic Power Unit |
| HRA | Health Risk Assessment |
| HSES | Health, Safety, Environment and Security |
| HSSE & SP | Health, Safety, Security, Environment and Social Performance |
| IEC | International Electro-technical Commission |
| ISPM | Industry Standard Process Modules |
| JV | Joint-Venture |
| LCD | Liquid Crystal Display |
| LOI | Local Operator Interface |
| LRL | Lower Range Limit |
| LRV | Lower Range Value |
| LIRA | Logistics and Infrastructure Resource Assessment |
| MAC | Main Automation Contractor |
| NAG | Non-Associated Gas |
| OPC | OLE for Process Control |
| OPPS | Overpressure Protection System |

## Abbreviations (contd.)

| Abbreviation | Meaning |
| --- | --- |
| PCD | Process Control Domain |
| PDMS | Plant Design and Management System |
| PEPF | Package Engineering, Procurement, and Fabrication |
| PIG | Pipeline Inspection Gauge |
| PVC | Polyvinyl Chloride |
| RTR | Reliability Test Run |
| SCE | Safety critical elements |
| SI | International System Units |
| SIL | Safety Integrity Level |
| SRB | Sulphate Reducing Bacteria |
| SIS | Safety Instrumented System |
| SWB | Steel Wire Braiding |
| URV | Upper Range Value |
| USC | US Customary Units |
| XLPE | Cross Linked Polyethylene |
| TEG | Tri-ethylene Glycol |
| TQ | Top Quartile |

# Executive Summary

- 1. EXECUTIVE SUMMARY

This proposal defines the strategy and execution plan for the safe decommissioning and abandonment of the integrated OKNU–BBOU–ELEP–AKAB gas pipeline network, traversing the swamp and riverine terrain of the Niger Delta.

The approach adopts a hybrid strategy (Removal + Abandonment-in-Place) to:

- Ensure zero residual hydrocarbon risk

- Minimize environmental disturbance

- Optimize cost and execution feasibility

- Enable asset recovery (TAR)

The proposal is aligned with project FEED philosophy and regulatory expectations.

- 2. SYSTEM OVERVIEW

- Pipeline Network

- Total Length: ~125 km

- Segments:

  - OKNU → BBOU (~85 km, new line)

  - BBOU → ELEP (~8 km)

  - ELEP → AKAB (~32 km trunkline)

- Key Nodes

- OKNU Manifold (KP0)

- River Niger Crossing (~KP10)

- Midline Manifolds (KP38, KP66)

- BBOU (KP85)

- ELEP (KP93)

- AKAB Gas Hub (KP125)

- Terrain Characteristics

- Predominantly swamp and mangrove

- Multiple river and creek crossings

- Offshore export connection to FLNG

- 3. DECOMMISSIONING PHILOSOPHY

- Core Principles

- Safety-first (zero harm, zero release)

- Environmental protection (no inland discharge)

- Regulatory compliance

- Value optimization (TAR)

- Minimum intervention in sensitive terrain

- 4. KEY DECOMMISSIONING PROCESSES

- 4.1 Planning & Regulatory Approval

- Asset verification (as-built vs installed)

- Environmental baseline study

- Decommissioning Execution Plan (DEP)

- Engagement with regulators and communities

- 4.2 Shutdown & Isolation

- Controlled system shutdown

- Mechanical isolation (valves, blinds, spades)

- Electrical and SCADA deactivation

- Segmentation into manageable sections (KP-based)

- 4.3 Cleaning & Hydrocarbon Removal

- Depressurization and venting

- Pigging operations:

  - Cleaning pigs

  - Gauging pigs

- Condensate and sludge removal

- 4.4 Flushing, Drying & Inerting

- Water or chemical flushing

- Air or nitrogen drying

- Nitrogen purging to inert condition

👉 This is the most critical safety barrier

- 4.5 Disconnection & Segmentation

- Cutting pipeline into sections

- Disconnection at:

  - OKNU

  - KP38 & KP66 manifolds

  - BBOU / ELEP

  - AKAB

- 4.6 Execution Decision

Each segment evaluated for:

- Removal or

- Abandonment-in-Place

- 4.7 Pipeline Removal (Where Applicable)

- Excavation using swamp-compatible equipment

- Lifting and transport

- Scrap recovery and reuse

- 4.8 Waste Management

- Segregation:

  - Scrap steel

  - Hazardous waste

  - Contaminated soils

- Certified disposal

- 4.9 Site Restoration

- Backfilling and grading

- Mangrove restoration

- Erosion control

- Post-restoration monitoring

- 5. KEY ABANDONMENT ACTIVITIES

Applied where removal is impractical or environmentally damaging.

- 5.1 Cleaning to Regulatory Standard

- Internal cleaning to hydrocarbon-free condition

- Verification via pigging and sampling

- 5.2 Permanent Isolation

- Installation of:

  - Blind flanges

  - End caps

- Removal of above-ground tie-ins

- 5.3 Filling & Stabilization

- Swamp / Onshore

- Water filling (treated/inhibited)

- Cement grouting (where required)

- River / Offshore

- Seawater flooding

- Natural sediment stabilization

- Rock dumping (if necessary)

- 5.4 Cathodic Protection Decommissioning

- CP system shutdown

- Removal or abandonment of anodes

- Electrical isolation

- 5.5 Long-Term Integrity Assurance

- Corrosion risk evaluation

- Monitoring requirements (if mandated)

- Documentation of abandoned sections

- 5.6 Marking & Records

- GIS update and pipeline status change

- Surface markers (where required)

- Regulatory documentation

- 6. KP-BASED EXECUTION STRATEGY

| Segment | Strategy | Justification |
| --- | --- | --- |
| KP0 (OKNU) | Remove | High-value facilities (TAR) |
| KP0–10 | Mixed | Accessible sections removable |
| KP10 (River Niger) | Abandon | High environmental risk |
| KP10–38 | Abandon (majority) | Deep swamp |
| KP38 Manifold | Remove | Strategic node |
| KP38–66 | Mixed | Access-dependent |
| KP66 Manifold | Remove | Future tie-in |
| KP66–85 | Mixed | Near infrastructure |
| BBOU / ELEP | Remove | Operational hubs |
| ELEP–AKAB | Case-by-case | Depends on reuse |
| Offshore line | Abandon | Industry standard |

- 7. SPECIAL NIGER DELTA CONSIDERATIONS

- Swamp mobility constraints → use low-ground-pressure equipment

- Mangrove sensitivity → prioritize abandonment

- River crossings → avoid disturbance

- Community engagement → critical success factor

- Seasonal flooding → schedule optimization

- 8. SCHEDULE (INTEGRATED)

| Phase | Duration |
| --- | --- |
| Planning & Approvals | 4–6 months |
| Engineering & Preparation | 3–4 months |
| Cleaning & Isolation | 2–3 months |
| Removal / Abandonment | 6–10 months |
| Restoration | 3–6 months |

Total Duration: ~12–18 months

- 9. COST ESTIMATE (ORDER OF MAGNITUDE)

| Component | Cost (₦ Billion) |
| --- | --- |
| Engineering & Approvals | 2.5 – 4.0 |
| Cleaning & Inerting | 3.0 – 5.0 |
| Removal Activities | 15 – 25 |
| Abandonment Activities | 5 – 10 |
| Restoration | 4 – 7 |
| Total | 29 – 49 Billion |

- 10. RISK MANAGEMENT

| Risk | Mitigation |
| --- | --- |
| Residual hydrocarbons | Multi-stage pigging + inerting |
| Environmental damage | Abandonment strategy |
| Swamp instability | Specialized equipment |
| Regulatory delays | Early engagement |
| Community issues | Stakeholder plan |

- 11. CONCLUSION

This proposal delivers a balanced, execution-ready decommissioning strategy that:

- Ensures safe hydrocarbon-free pipeline retirement

- Minimizes environmental impact in the Niger Delta

- Optimizes cost through hybrid removal/abandonment

- Maximizes asset recovery value

- NEXT STEP (HIGHLY RECOMMENDED)

If you want to elevate this to client submission standard, I can:

- Convert this into a fully formatted proposal document (Word/PDF)

- Build a PowerPoint pack with visuals + KP map

- Add a Gantt chart aligned to your FEED timeline

- Or produce a commercial BOQ with detailed line items (Nigeria benchmarks)

Top of Form

Bottom of Form

SPDC fields in OMLs 33, 35 & 36.

- PART 1 — POWERPOINT PACK (DESIGNED CONTENT + VISUAL GUIDE)

- Slide 1 — Title

- Pipeline Decommissioning & Abandonment Strategy
OKNU–BBOU–ELEP–AKAB Gas System (125 km)

- Subtitle:
Integrated Hybrid Removal & Abandonment Plan (Niger Delta)

- Slide 2 — System Overview (Visual Map Intro)

- Content:

- Total Network: 125 km

- Capacity: up to 300 MMscfd

- Terrain: Swamp | River | Offshore

- Visual:

- Use a horizontal corridor map:

OKNU ───── KP38 ───── KP66 ───── BBOU ── ELEP ───── AKAB

- Add icons:

- 🌿 Swamp

- 🌊 River (KP10)

- ⚙️ Facilities

- Slide 3 — KP STRATEGY MAP (CORE VISUAL SLIDE)

- Use Color Coding:

- 🔴 REMOVE

- 🟢 ABANDON

- 🟡 MIXED

- Diagram:

KP0     KP10      KP38      KP66      KP85     KP93      KP125
│--------│----------│----------│----------│---------│----------│
🟡        🟢          🔴          🔴          🔴        🔴          🔴

- Labels:

- KP10 → River Niger → ABANDON

- KP38 / KP66 → REMOVE (nodes)

- Facilities → REMOVE

- Deep swamp → ABANDON

- Slide 4 — Decommissioning Process Flow

- Use horizontal arrows:

- Planning → Engineering → Shutdown → Cleaning → Segmentation → Decision → Execution → Restoration → Close-out

- Add icons for each stage.

- Slide 5 — Key Decommissioning Processes

- Split into 3 blocks:

- Block 1:

- Shutdown & Isolation

- Pigging & Cleaning

- Block 2:

- Flushing & Inerting

- Disconnection

- Block 3:

- Removal / Abandonment

- Restoration

- Slide 6 — Abandonment Activities (Visual)

- Left (Steps):

- Cleaning to hydrocarbon-free

- Isolation (caps/blinds)

- Flooding / grouting

- CP decommissioning

- Right (Diagram):

- Simple pipe cross-section filled with water/grout

- Slide 7 — Removal Activities

- Excavation (swamp-compatible)

- Lifting & transport

- Scrap recovery (TAR)

- Facility dismantling

- Add excavator + pipeline visuals

- Slide 8 — Decision Tree (Simple Visual)

- Start →
Environment sensitive? → YES → ABANDON
NO → Accessible? → YES → REMOVE
Else → Cost vs Risk → Decide

- Slide 9 — Niger Delta Constraints

- Icons + short bullets:

- Swamp instability

- Mangrove protection

- River crossings

- Community interface

- Slide 10 — Integrated Schedule (Gantt Intro)

- “Execution aligned to FEED timeline (Jul–Dec 2026)”

- PART 2 — GANTT CHART (ALIGNED TO YOUR FEED TIMELINE)

- Time Axis: Jul – Dec 2026

Phase                          Jul Aug Sep Oct Nov Dec
-----------------------------------------------------
FEED Finalization              ███ ███
Regulatory Approvals           ███ ███ ███
Detailed Decommission Planning     ███ ███
Procurement & Mobilization         ███ ███ ███
Cleaning & Isolation                    ███ ███
Segmentation & Disconnection               ███ ███
Removal Activities                           ███ ███ ███
Abandonment Activities                       ███ ███ ███
Restoration & Reinstatement                      ███ ███
Close-out & Certification                         ███

- Critical Logic (Important for Boardroom)

- FEED → enables accurate decommissioning plan

- Approvals run in parallel with planning

- Cleaning is the gate before any field work

- Removal & abandonment run concurrently

- Restoration overlaps late execution

- PART 3 — HIGH-IMPACT VISUAL SLIDE (RECOMMENDED ADDITION)

- “VALUE OPTIMIZATION STRATEGY”

- Left:

- Abandon swamp & river → ↓ cost

- Remove facilities → ↑ asset recovery

- Right:

- Bar chart concept:

- Full removal → Highest cost

- Hybrid → Optimal

- Full abandonment → Regulatory risk

- PART 4 — DELIVERY FORMAT (HOW I CAN FINALIZE FOR YOU)

- If you want this turned into a ready-to-send file, I can generate:

- ✅ Option 1 — PowerPoint File (.pptx)

- Clean consulting layout (McKinsey-style)

- Icons + color coding

- Editable Gantt

- ✅ Option 2 — With Map Upgrade

- Proper geographic route map (satellite style)

- KP markers (0, 10, 38, 66, 85, 93, 125)

- ✅ Option 3 — Executive Version

- 6-slide ultra-condensed board pack

- My recommendation (based on your earlier work):

- Go with:
👉 Full deck + map + Gantt (investment committee grade)

- If you say “build the PPT file”, I’ll generate a downloadable .pptx with:

- Proper layout

- Icons

- Clean KP map

- Professional Gantt chart

- Ready for client submission.

Top of Form

Bottom of Form

- PART 1 — POWERPOINT PACK (DESIGNED CONTENT + VISUAL GUIDE)

- Slide 1 — Title

- Pipeline Decommissioning & Abandonment Strategy
OKNU–BBOU–ELEP–AKAB Gas System (125 km)

- Subtitle:
Integrated Hybrid Removal & Abandonment Plan (Niger Delta)

- Slide 2 — System Overview (Visual Map Intro)

- Content:

- Total Network: 125 km

- Capacity: up to 300 MMscfd

- Terrain: Swamp | River | Offshore

- Visual:

- Use a horizontal corridor map:

OKNU ───── KP38 ───── KP66 ───── BBOU ── ELEP ───── AKAB

- Add icons:

- 🌿 Swamp

- 🌊 River (KP10)

- ⚙️ Facilities

- Slide 3 — KP STRATEGY MAP (CORE VISUAL SLIDE)

- Use Color Coding:

- 🔴 REMOVE

- 🟢 ABANDON

- 🟡 MIXED

- Diagram:

KP0     KP10      KP38      KP66      KP85     KP93      KP125
│--------│----------│----------│----------│---------│----------│
🟡        🟢          🔴          🔴          🔴        🔴          🔴

- Labels:

- KP10 → River Niger → ABANDON

- KP38 / KP66 → REMOVE (nodes)

- Facilities → REMOVE

- Deep swamp → ABANDON

- Slide 4 — Decommissioning Process Flow

- Use horizontal arrows:

- Planning → Engineering → Shutdown → Cleaning → Segmentation → Decision → Execution → Restoration → Close-out

- Add icons for each stage.

- Slide 5 — Key Decommissioning Processes

- Split into 3 blocks:

- Block 1:

- Shutdown & Isolation

- Pigging & Cleaning

- Block 2:

- Flushing & Inerting

- Disconnection

- Block 3:

- Removal / Abandonment

- Restoration

- Slide 6 — Abandonment Activities (Visual)

- Left (Steps):

- Cleaning to hydrocarbon-free

- Isolation (caps/blinds)

- Flooding / grouting

- CP decommissioning

- Right (Diagram):

- Simple pipe cross-section filled with water/grout

- Slide 7 — Removal Activities

- Excavation (swamp-compatible)

- Lifting & transport

- Scrap recovery (TAR)

- Facility dismantling

- Add excavator + pipeline visuals

- Slide 8 — Decision Tree (Simple Visual)

- Start →
Environment sensitive? → YES → ABANDON
NO → Accessible? → YES → REMOVE
Else → Cost vs Risk → Decide

- Slide 9 — Niger Delta Constraints

- Icons + short bullets:

- Swamp instability

- Mangrove protection

- River crossings

- Community interface

- Slide 10 — Integrated Schedule (Gantt Intro)

- “Execution aligned to FEED timeline (Jul–Dec 2026)”

- PART 2 — GANTT CHART (ALIGNED TO YOUR FEED TIMELINE)

- Time Axis: Jul – Dec 2026

Phase                          Jul Aug Sep Oct Nov Dec
-----------------------------------------------------
FEED Finalization              ███ ███
Regulatory Approvals           ███ ███ ███
Detailed Decommission Planning     ███ ███
Procurement & Mobilization         ███ ███ ███
Cleaning & Isolation                    ███ ███
Segmentation & Disconnection               ███ ███
Removal Activities                           ███ ███ ███
Abandonment Activities                       ███ ███ ███
Restoration & Reinstatement                      ███ ███
Close-out & Certification                         ███

- Critical Logic (Important for Boardroom)

- FEED → enables accurate decommissioning plan

- Approvals run in parallel with planning

- Cleaning is the gate before any field work

- Removal & abandonment run concurrently

- Restoration overlaps late execution

- PART 3 — HIGH-IMPACT VISUAL SLIDE (RECOMMENDED ADDITION)

- “VALUE OPTIMIZATION STRATEGY”

- Left:

- Abandon swamp & river → ↓ cost

- Remove facilities → ↑ asset recovery

- Right:

- Bar chart concept:

- Full removal → Highest cost

- Hybrid → Optimal

- Full abandonment → Regulatory risk

- PART 4 — DELIVERY FORMAT (HOW I CAN FINALIZE FOR YOU)

- If you want this turned into a ready-to-send file, I can generate:

- ✅ Option 1 — PowerPoint File (.pptx)

- Clean consulting layout (McKinsey-style)

- Icons + color coding

- Editable Gantt

- ✅ Option 2 — With Map Upgrade

- Proper geographic route map (satellite style)

- KP markers (0, 10, 38, 66, 85, 93, 125)

- ✅ Option 3 — Executive Version

- 6-slide ultra-condensed board pack

- My recommendation (based on your earlier work):

- Go with:
👉 Full deck + map + Gantt (investment committee grade)

- If you say “build the PPT file”, I’ll generate a downloadable .pptx with:

- Proper layout

- Icons

- Clean KP map

- Professional Gantt chart

- Ready for client submission.

# Introduction

## Background Information

Brass Fertilizer and Petrochemical Company Limited (BFPCL) is developing a 10,000 metric tonnes per day (MTPD) capacity greenfield methanol production facility in Akabel (Odioma), Brass LGA, Bayelsa state. The plant complex is to be based on natural gas feedstock from 5 SPDC fields in OMLs 33, 35 & 36.

## Background Information

Brass Fertilizer and Petrochemical Company Limited (BFPCL) is developing a 10,000 metric tonnes per day (MTPD) capacity greenfield methanol production facility in Akabel (Odioma), Brass LGA, Bayelsa state. The plant complex is to be based on natural gas feedstock from 5 SPDC fields in OMLs 33, 35 & 36.

The Project involves the development, construction, and operation of a plant comprising:

Two trains of 5,000 MTPD methanol plant, producing a total of 10,000 MTPD of methanol

340 MMscfd Gas Processing Plant (“GPP”), which will extract NGL from the natural gas feedstock, prior to feeding the lean gas to the methanol plant.

Gas gathering pipelines and associated manifolds transporting the natural gas from five fields, viz: Bubouwe Bou (BBOU), Elepa (ELEP), Nun River (NUNR), Seibou (SEIB), and Opugbene (OPUG) to the GPP at Akabel.

Product Export Lines and SBM for the export of the methanol, and NGL of the GPP.

All offsite, utility, and off-plot facilities (including product storage, internal power generation, steam generation, and export jetty) for the operation of the processing plants.

TCE is the Project Management Consultant for the project, and TCC the EPC Contractor.

## The Project Phases

The Pipelines will be implemented in two phases, - starting with BBOU & ELEP as Phase 1 and followed by NUNR, SEIB & OPUG as Phase 2.

The focus of the present FEED is on Phase 1 as shown in figure 1 below, while Phase 2 will be implemented later; and the related 1 BCFD gas hub opportunity much later.

The Nodal Gas Gathering Schematics

|  | - Gas Gathering from six SPDC Nodes |
| --- | --- |
| Figure 1-1: Fields & Nodes covered in Phase 1 & 2 Gas Gathering |  |

The Nodal Gas Gathering Schematics (contd.)

Figure 1-2: Gas Gathering Concept, Phase 1

Figure 1-3: Wholistic Gas Gathering Concept, Phase 1 & 2

## The 1 BSCFD Gas Hub Opportunity

The schematics for the 1 BSCFD gas gathering for the gas hub opportunity is shown below.

Figure 1.4 Schematics for the Gas Gathering of the1 BSCFD Gas Hub

Production from ‘Other Node’ flowing through SEIB & NUNR Nodes to ELEP Evacuation Manifold, and thence to AKAB Gas Hub, through the existing phases-1&2 ELEP – AKAB Pipeline, and a new Pipeline as a loop line to the existing ELEP - AKAB Pipeline, given that the phases 1&2 facilities are already in place.

The basic principle behind the details of the configuration is the optimal mix of line sizes and compression requirement to deliver the gas at the required pressure at destination.

## Purpose of Document

The purpose of the document is to provide a structured summary of the key features of the FEED, - notably the project specifications, and specific deliverables required by regulators, - which collectively forms the technical and statutory basis for the project’s Financial Close, and the subsequent EPC processes implementation.

key decommissioning processes and abandonment activities

- Here’s a clear, executive-grade breakdown of the key decommissioning processes and abandonment activities, aligned with your OKNU–BBOU–ELEP–AKAB pipeline system and Niger Delta conditions:

- KEY DECOMMISSIONING PROCESSES & ABANDONMENT ACTIVITIES

- 1. Decommissioning Processes (End-to-End Execution)

- 1.1 Pre-Decommissioning Planning

- Asset verification (as-built vs actual condition)

- Regulatory approvals (Nigerian Upstream Petroleum Regulatory Commission, Nigerian Midstream and Downstream Petroleum Regulatory Authority)

- Environmental baseline and risk assessment

- Stakeholder/community engagement

- 1.2 System Shutdown & Isolation

- Controlled shutdown of gas flow

- Mechanical isolation (valves, blinds, spading)

- Electrical and instrumentation de-energization

- Segmentation into manageable sections (by KP / hydrotest sections)

- 1.3 Pipeline Cleaning & Hydrocarbon Removal

- Depressurization and venting

- Pigging operations:

  - Cleaning pigs

  - Batching pigs

- Chemical cleaning (if required)

- Removal of condensate, sludge, and residues

- 1.4 Flushing, Drying & Inerting

- Water flushing or gel cleaning

- Air or nitrogen drying

- Nitrogen purging to achieve inert condition

- 👉 Critical to eliminate explosion and contamination risks

- 1.5 Disconnection & Mechanical Works

- Cutting of pipeline into sections

- Disconnection from:

  - Manifolds (OKNU, BBOU, ELEP)

  - AKAB gas hub

- Removal of above-ground facilities:

  - Slug catchers

  - Pigging stations

  - Metering systems

- 1.6 Pipeline Removal (Where Applicable)

- Excavation (swamp-compatible methods)

- Lifting and transport

- Removal of:

  - Shallow buried pipelines

  - Congested corridor sections

- Special handling at crossings

- 1.7 Waste Management

- Segregation:

  - Scrap steel

  - Hazardous waste

  - Contaminated soils

- Transport to certified disposal facilities

- Compliance with Federal Ministry of Environment standards

- 1.8 Site Restoration

- Backfilling and grading

- Mangrove and vegetation restoration

- Erosion control (especially in swamp areas)

- Post-restoration monitoring

- 2. Abandonment Activities (Pipeline Left In Place)

- Applied where removal is technically difficult, environmentally risky, or uneconomic.

- 2.1 Cleaning to Acceptable Standard

- Internal cleaning to remove hydrocarbons

- Verification via pigging and sampling

- 2.2 Isolation & Disconnection

- Physical disconnection from live systems

- Installation of:

  - Blind flanges

  - Permanent caps

- Removal of surface tie-ins

- 2.3 Filling / Stabilization

- Depending on location:

- Onshore / Swamp

- Filling with inert material:

  - Nitrogen (short-term)

  - Water or inhibited fluid

  - Cement grout (long-term stability)

- River / Offshore

- Flooding with seawater

- Natural sediment stabilization

- Rock dumping (if required)

- 2.4 Cathodic Protection Decommissioning

- Deactivation of CP systems

- Removal or safe abandonment of anodes

- Electrical isolation

- 2.5 Long-Term Integrity Assurance

- Corrosion risk assessment

- Monitoring (if required by regulator)

- Documentation of abandoned sections

- 2.6 Marking & Records

- Updating pipeline records as “abandoned”

- GIS and survey updates

- Installation of surface markers (where required)

- 3. Special Considerations for OKNU–BBOU–ELEP–AKAB

- High-Priority Abandonment Zones

- River Niger crossing (~KP10) → Abandon in place preferred

- Deep swamp sections (KP10–KP66) → Selective abandonment

- Offshore FLNG line → Flood & stabilize

- High-Priority Removal Zones

- Manifold areas (OKNU, KP38, KP66, BBOU, ELEP, AKAB)

- Congested corridors

- Areas with future development conflicts

- 4. Decision Framework (Removal vs Abandonment)

| Factor | Removal | Abandonment |
| --- | --- | --- |
| Environmental sensitivity | ❌ | ✅ |
| Swamp / offshore terrain | ❌ | ✅ |
| Congested facilities | ✅ | ❌ |
| Cost efficiency | ❌ (higher) | ✅ (lower) |
| Future land use | ✅ | ❌ |

- 5. Executive Takeaway

- Decommissioning success depends on three critical controls:

- Complete hydrocarbon removal and inerting

- Right selection of removal vs abandonment strategy

- Full environmental restoration and regulatory closure

- If you want, I can:

- Convert this into a process flow diagram (visual slide)

- Or build a decision tree for abandonment vs removal (very powerful for board presentation)

- Or align it into your final decommissioning proposal pack with cost + schedule integration

Top of Form

Bottom of Form

do all three

- Below are all three deliverables, structured so you can drop them straight into your proposal pack or slides for the OKNU–BBOU–ELEP–AKAB pipeline system.

- 1. PROCESS FLOW DIAGRAM (EXECUTIVE VISUAL – SLIDE READY)

Writing

- PIPELINE DECOMMISSIONING PROCESS FLOW

- PLANNING & APPROVAL
→ Asset Verification
→ Regulatory Engagement (NUPRC / NMDPRA / FMEnv)
→ Environmental Baseline & Risk Assessment

- ⬇

- ENGINEERING & PREPARATION
→ Decommissioning Execution Plan (DEP)
→ HAZID / HAZOP
→ Work Packs & Method Statements

- ⬇

- SHUTDOWN & ISOLATION
→ Controlled Shutdown
→ Mechanical Isolation (Valves / Blinds)
→ Electrical & SCADA De-energization

- ⬇

- CLEANING & INERTING
→ Depressurization
→ Pigging (Cleaning + Gauging)
→ Flushing & Chemical Cleaning
→ Nitrogen Purging

- ⬇

- DISCONNECTION & SEGMENTATION
→ Cut & Cap Sections
→ Disconnect from OKNU / BBOU / ELEP / AKAB
→ Prepare Sections for Removal or Abandonment

- ⬇

- EXECUTION DECISION
→ REMOVE | ABANDON-IN-PLACE

- ⬇

- PIPELINE REMOVAL (IF SELECTED)
→ Excavation (Swamp Methods)
→ Lifting & Transportation
→ Scrap / Reuse Handling

- ⬇

- ABANDONMENT (IF SELECTED)
→ Final Cleaning Verification
→ Flooding / Grouting / Stabilization
→ Permanent Isolation

- ⬇

- WASTE MANAGEMENT
→ Segregation (Scrap / Hazardous / Soil)
→ Certified Disposal

- ⬇

- SITE RESTORATION
→ Backfilling & Regrading
→ Mangrove Restoration
→ Erosion Control

- ⬇

- CLOSE-OUT
→ As-Left Documentation
→ Regulatory Sign-Off
→ Lessons Learned

- 2. DECISION TREE – REMOVAL vs ABANDONMENT

Writing

- PIPELINE DECOMMISSIONING DECISION TREE

- START: PIPELINE SEGMENT IDENTIFIED

- ⬇

- Q1: Is the segment in a sensitive environment?
(Swamp / River / Offshore / Mangrove)

- → YES → Proceed to Q2
→ NO → Proceed to Q3

- ⬇

- Q2: Will removal cause significant environmental damage?
→ YES → ABANDON IN PLACE
→ NO → Proceed to Q3

- ⬇

- Q3: Is the segment located in a congested or developable area?
(Facilities / Future projects / Urban proximity)

- → YES → REMOVE PIPELINE
→ NO → Proceed to Q4

- ⬇

- Q4: Is the pipeline shallow and easily accessible?
→ YES → REMOVE PIPELINE
→ NO → Proceed to Q5

- ⬇

- Q5: Is abandonment more cost-effective with acceptable risk?
→ YES → ABANDON IN PLACE
→ NO → REMOVE PIPELINE

- ⬇

- FINAL VALIDATION
→ Regulatory Approval (NUPRC / FMEnv)
→ Environmental Acceptability
→ Long-Term Liability Assessment

- 3. INTEGRATION INTO FINAL PROPOSAL PACK (COST + SCHEDULE LINKAGE)

- 3.1 Integrated Execution Strategy (OKNU–BBOU–ELEP–AKAB)

- Segment-Based Approach

| Segment | Strategy | Rationale |
| --- | --- | --- |
| OKNU Facilities (KP0) | Remove | High-value equipment (TAR) |
| KP0–KP10 (Swamp) | Partial removal | Accessibility varies |
| River Niger Crossing (~KP10) | Abandon | High environmental risk |
| KP10–KP38 | Selective abandonment | Deep swamp terrain |
| KP38 Manifold | Remove | Future tie-in conflict |
| KP38–KP66 | Mixed | Depends on access |
| KP66 Manifold | Remove | Strategic node |
| KP66–KP85 (BBOU) | Partial removal | Near infrastructure |
| BBOU / ELEP Facilities | Remove | Integration hubs |
| ELEP–AKAB trunkline | Case-by-case | Depends on reuse |
| Offshore FLNG line | Abandon | Standard offshore practice |

- 3.2 Integrated Schedule (Aligned to Decommissioning Phases)

| Phase | Duration | Key Output |
| --- | --- | --- |
| Planning & Approval | 4–6 months | Permits secured |
| Engineering & Prep | 3–4 months | DEP finalized |
| Cleaning & Isolation | 2–3 months | Hydrocarbon-free system |
| Removal / Abandonment | 6–10 months | Pipeline retired |
| Restoration | 3–6 months | Site reinstated |

- Total Duration: ~12–18 months

- 3.3 Cost Integration (Linked to Strategy)

| Activity | Cost Driver |
| --- | --- |
| Cleaning & Inerting | Pigging, chemicals |
| Removal | Excavation, logistics |
| Abandonment | Filling, stabilization |
| Restoration | Environmental sensitivity |
| TAR Recovery | Cost offset opportunity |

- 3.4 Value Optimization Lever

- Maximize abandonment in deep swamp & offshore → reduces cost by ~30–50%

- Maximize removal at facilities → enables asset recovery (TAR)

- Hybrid strategy = optimal lifecycle cost + regulatory acceptance

- EXECUTIVE CLOSE

- This integrated approach ensures:

- Safety: Fully cleaned and inert system

- Environmental Protection: Minimal disturbance in Niger Delta

- Cost Efficiency: Right balance of removal vs abandonment

- Value Recovery: Preservation of high-value assets

- If you want the final polish

- I can now:

- Turn this into a fully designed PowerPoint deck (icons, colors, layout)

- Add a visual map (KP0–125 with strategy overlay) ← very powerful for boardrooms

- Or merge everything into your complete decommissioning submission pack (ready for client)

Top of Form

Bottom of Form

- Alright—here’s a complete, boardroom-ready package covering all three:

- 1. POWERPOINT SLIDE DECK (CONTENT + DESIGN STRUCTURE)

- (You can paste this directly into PowerPoint — I’ve structured each slide with title + content + visual cues)

- Slide 1 – Title Slide

- Title:
Pipeline Decommissioning Strategy
OKNU–BBOU–ELEP–AKAB Gas System

- Subtitle:
Integrated Removal & Abandonment Plan

- Slide 2 – Executive Overview

- Content:

- End-to-end decommissioning of ~125 km pipeline network

- Hybrid strategy: Removal + Abandonment-in-Place

- Designed for:

  - Niger Delta swamp terrain

  - Regulatory compliance

  - Cost optimization

- Visual: 4 icons → Safety | Environment | Cost | Compliance

- Slide 3 – Process Flow

- (Use horizontal flow arrows)

- Flow:
Planning → Engineering → Shutdown → Cleaning → Segmentation → Decision → Execution → Restoration → Close-out

- Slide 4 – Removal vs Abandonment Strategy

- Left Column: Removal

- Facilities & manifolds

- Accessible shallow sections

- Future development zones

- Right Column: Abandonment

- River crossings

- Deep swamp sections

- Offshore pipelines

- Slide 5 – KP-Based Execution Strategy

- (Insert simple linear diagram KP0 → KP125)

- KP0–10: Partial removal

- KP10 (River Niger): Abandon

- KP10–66: Selective abandonment

- KP38 & KP66: Remove (nodes)

- KP85–125: Mixed strategy

- Slide 6 – Decision Framework

- (Flowchart style)

- Environmental sensitivity?

- Access feasibility?

- Cost vs risk?
→ Decision: Remove / Abandon

- Slide 7 – Schedule

- Timeline bar:

- Engineering: 4–6 months

- Cleaning: 2–3 months

- Execution: 6–10 months

- Restoration: 3–6 months

- Slide 8 – Cost Overview

- Total Estimate: ₦29B – ₦49B

- Key drivers:

  - Terrain

  - Removal scope

  - Restoration requirements

- Slide 9 – Value Optimization

- Hybrid strategy reduces cost

- Asset recovery (TAR)

- Reduced environmental liability

- Slide 10 – Key Risks & Controls

| Risk | Control |
| --- | --- |
| Residual gas | Pigging + inerting |
| Swamp instability | Specialized equipment |
| Environmental damage | Abandonment strategy |

- Slide 11 – Conclusion

- Safe

- Compliant

- Cost-optimized

- Execution-ready

- 2. VISUAL MAP (KP0–125 STRATEGY OVERLAY)

- You can recreate this easily in PowerPoint or Visio.

- Linear Map Representation

OKNU (KP0)
│
├── KP10 → River Niger Crossing → [ABANDON]
│
├── KP38 → Midline Manifold → [REMOVE]
│
├── KP66 → Midline Manifold → [REMOVE]
│
├── BBOU (KP85) → [REMOVE]
│
├── ELEP (KP93) → [REMOVE]
│
└── AKAB (KP125) → Gas Hub

- Color Coding (Important)

- 🔴 RED → Remove

- 🟢 GREEN → Abandon

- 🟡 YELLOW → Mixed / Conditional

- Segment Strategy Overlay

| Segment | Strategy |
| --- | --- |
| KP0–10 | 🟡 Mixed |
| KP10 Crossing | 🟢 Abandon |
| KP10–38 | 🟢 Mostly abandon |
| KP38 Node | 🔴 Remove |
| KP38–66 | 🟡 Mixed |
| KP66 Node | 🔴 Remove |
| KP66–85 | 🟡 Mixed |
| Facilities | 🔴 Remove |

- 3. FULL PROPOSAL PACK STRUCTURE (MERGED & READY)

- This is your final submission structure—you can compile into Word or PDF.

- SECTION 1 – EXECUTIVE SUMMARY

- Project overview

- Decommissioning objective

- Hybrid strategy

- SECTION 2 – SYSTEM DESCRIPTION

- OKNU–BBOU–ELEP–AKAB pipeline

- Length, diameter, facilities

- Terrain (swamp, river, offshore)

- SECTION 3 – DECOMMISSIONING PHILOSOPHY

- Safety-first approach

- Removal vs abandonment principles

- TAR (asset recovery) integration

- SECTION 4 – KEY PROCESSES

- Shutdown & isolation

- Cleaning & inerting

- Segmentation

- Execution

- SECTION 5 – ABANDONMENT METHODOLOGY

- Cleaning standards

- Filling (water / grout)

- Stabilization

- Long-term integrity

- SECTION 6 – SEGMENT STRATEGY (KP-BASED)

- KP0–125 breakdown

- River crossing approach

- Facility removal plan

- SECTION 7 – AS-BUILT & DATA REQUIREMENTS

- Drawing checklist

- Data room structure

- Critical gaps

- SECTION 8 – SCHEDULE

- Integrated timeline (12–18 months)

- SECTION 9 – COST ESTIMATE

- ₦29B – ₦49B range

- Cost drivers

- Optimization levers

- SECTION 10 – RISK MANAGEMENT

- Environmental

- Technical

- Execution

- SECTION 11 – ENVIRONMENTAL & REGULATORY

- Compliance strategy

- Restoration approach

- Stakeholder engagement

- SECTION 12 – CONCLUSION

- Safe execution

- Regulatory alignment

- Cost efficiency

- FINAL EXECUTIVE POSITIONING

- What you now have is a complete, investment-grade narrative:

- Slide deck → for decision makers

- Map → for clarity and alignment

- Full proposal → for submission and execution

- If you want the last mile polish:

- I can next:

- Design this into a fully formatted PowerPoint file (consulting-grade visuals)

- Create a proper geographic map (satellite-style with route overlay)

- Or build a financial model (NPV of removal vs abandonment scenarios)

Top of Form

Bottom of Form

# Battery Limit, and Scope of Work

## Battery Limit

The phase 1 facilities are the focus of the present FEED, however with consideration for provisions and retrofits that will accommodate the phase 2 facilities in a rather seamless manner.

The Phase-1 main facilities are:

BBOU – ELEP pipeline

ELEP - AKAB Pipeline

BBOU Satellite Manifold

ELEP Evacuation Manifold, and

The Pipeline End Manifold at AKAB, complete with Pig Receiver.

The battery limits are shown below:

Figure 2.1 Battery Limit – Phase 1 Facilities

### BBOU Platform

The terminal flanged ball valve on the manifold collecting well fluids from BBOU Wells.

The flanged ball valve provided for the tie-in of Opugbene (OPUG) Pipeline on the manifold transporting well fluids to ELEP.

### ELEP Platform

The terminal flanged ball valve on the manifold collecting well fluids from ELEPA Wells.

The flanged ball valve provided for the tie-in of NUN River Pipeline on the manifold transporting well fluids to AKAB.

### Akabel Facility

The Pipeline terminal flange at the inlet to the slug catcher at AKAB.

The drain outlet flange on the pig receiver at AKAB.

## Scope of Work

The FEED scope covers, but not limited to the following:

- Project Engineering

- Process Systems Design, complete with Pipe Flow Hydraulics Analysis and Flow Assurance

- Materials Specification

- Pipeline Engineering

- Mechanical and Piping Design

- Structural Design

- Civil and Foundation Engineering

- Electrical Engineering

- Control & Instrumentation, and Telecommunications Engineering

- Technical Safety and Loss Prevention

- EPC Cost Estimate

The Facilities to be covered under project scope are:

Satellite Manifold at BBOU complete with all Process, Utility & Control Infrastructure, however with provision for future installation of PIG receiver as will be required for phase 2 production from OPUG.

Evacuation Manifold at ELEP complete with all Process, Utility & Control Infrastructure, however with provision for future installation of PIG receiver as will be required for phase 2 production from NUNR.

Pipeline from BBOU to ELEP

Pipeline from ELEP to AKAB (up to Inlet Flange of Slug Catcher)

PIG Launchers at BBOU and ELEP Manifold

PIG Receivers at ELEP and AKAB

Manifold control system also to be provided. Control Room required at each Manifold to house the Manifold Control system & Telecom system

Cabinet Room to house the electrical MCC.

UPS Power for Control System, associated Civil, Mechanical, Pipeline, Electrical, Instrumentation & Control, Telecommunication, and all other supporting infrastructure.

- Final Executive Insight

- For your OKNU–BBOU–ELEP–AKAB system, the most critical drawing gaps to watch are:

- River Niger crossing as-built details

- Midline manifold tie-in documentation (KP38 & KP66)

- Weld maps and material traceability

- Updated P&IDs reflecting integration with AKAB

- → These will make or break safe isolation, cleaning, and regulatory approval.

## Data Room Index Structure

- 01. Project Overview

- Pipeline description

- Key coordinates and KP definitions

- Asset register

- 02. Route & Survey

- Alignment sheets

- ROW drawings

- Survey as-builts

- 03. Pipeline Engineering

- GA drawings

- Isometrics

- Wall thickness & specs

- 04. Facilities

- OKNU

- KP38 manifold

- KP66 manifold

- BBOU

- ELEP

- AKAB

- 05. Crossings

- River Niger crossing

- Creek crossings

- HDD drawings

- 06. Mechanical & Materials

- Weld maps

- Material certificates

- Coating specs

- 07. Process & Instrumentation

- P&IDs

- Cause & Effect

- SCADA

- 08. Electrical & CP

- CP layouts

- SLDs

- Earthing

- 09. Civil & Structural

- Foundations

- Supports

- Access infrastructure

- 10. Testing & Commissioning

- Hydrotest

- Drying

- Pre-commissioning

- 11. Environmental

- EIA

- Baseline data

- Restoration plans

- 12. Modifications

- Redlines

- Tie-ins

- Design changes

- 13. Decommissioning (To Be Developed)

- Decommissioning Execution Plan

- Cleaning & pigging procedures

- Waste management plan

- Restoration plan

## Layout & Configuration

- 1. Route & Alignment

- Pipeline Alignment Sheets (Plan & Profile, KP 0–125 km)

- ROW Drawings (full corridor coverage)

- Survey As-Built (final coordinates and deviations)

- Pipeline General Arrangement (GA)

- Plot Plans:

  - OKNU Manifold (KP 0)

  - BBOU Manifold (KP 85)

  - ELEP (KP 93)

  - AKAB Gas Hub (KP 125)

- Pipeline Isometrics (segment-wise)

- 3. Crossings & Special Sections

- River Niger Crossing (~KP 10) drawings

- Creek/River crossings (all locations)

- HDD / trenchless installation drawings

- Trench and burial profiles

- 4. Mechanical & Materials

- Weld maps (full traceability)

- Wall thickness and coating specs

- Line pipe data sheets

- Material certificates (API 5L traceability)

- 5. Valves & Facilities

- Valve location drawings (chainage-based)

- Pig launcher/receiver drawings

- Manifold piping layouts (OKNU, KP38, KP66, BBOU, ELEP)

- Slug catcher drawings

- 6. Process & Control

- As-built P&IDs (entire system)

- Cause & Effect diagrams

- SCADA / instrumentation layouts

- 7. Electrical & CP

- Cathodic Protection layout

- Transformer Rectifier (TR) locations

- Earthing & bonding drawings

- Electrical Single Line Diagrams

- 8. Civil & Structural

- Foundations (manifolds, slug catchers)

- Pipe supports and sleepers

- Access roads and pads

- 9. Testing & Commissioning

- Hydrotest layouts and sectioning

- Dewatering/drying layouts

- 10. Environmental

- Baseline environmental maps

- Sensitive area mapping (mangroves, wetlands)

- Restoration drawings (if applicable)

- 11. Modifications & Deviations

- Redline drawings

- Tie-in modifications (KP38, KP66, BBOU integration)

- Looping / resizing updates

- A2. Submission Requirements

- Digital format (PDF + native CAD)

- Indexed and searchable

- Linked to asset register

- Verified as “As-Built” (not IFC/IFD)

- B. KP-BY-KP DRAWING RELEVANCE (OKNU → AKAB)

- This maps critical drawings to physical pipeline segments—very useful for execution planning.

- KP 0 – KP 10 (OKNU → River Niger Crossing)

- Key Features: Inlet manifold, slug catcher, swamp terrain

- Required Drawings:

- OKNU Plot Plan & P&IDs

- Slug catcher GA

- Alignment sheets

- Valve and pigging drawings

- CP layout

- KP 10 – River Niger Crossing

- Key Features: Major river crossing (~200 m width)

- Required Drawings:

- HDD / crossing profile drawings

- Bathymetric and geotechnical drawings

- Crossing method as-built

- Environmental sensitivity maps

- Execution Note: High likelihood of abandonment-in-place

- KP 10 – KP 38 (Swamp Section)

- Key Features: Challenging swamp terrain

- Required Drawings:

- Alignment + trench details

- CP and coating drawings

- Weld maps

- Access road drawings

- KP 38 – Midline Manifold (SEIB Tie-in)

- Key Features: Future tie-in node

- Required Drawings:

- Manifold GA and piping layout

- Metering system drawings

- Isolation valve drawings

- KP 38 – KP 66

- Key Features: Long swamp stretch

- Required Drawings:

- Alignment sheets

- Weld maps

- CP layout

- Environmental maps

- KP 66 – Midline Manifold (NUNR/DBUC Tie-in)

- Key Features: Conditional tie-in

- Required Drawings:

- Manifold GA

- Tie-in spool drawings

- Instrumentation layouts

- KP 66 – KP 85 (BBOU)

- Key Features: Approach to major hub

- Required Drawings:

- Alignment and profile

- Valve segmentation drawings

- Hydrotest section drawings

- KP 85 – BBOU Manifold

- Key Features: Major integration node

- Required Drawings:

- Plot plan & P&IDs

- Tie-in drawings (OKNU + ELEP line)

- Metering and control systems

- KP 85 – KP 93 (BBOU → ELEP)

- Key Features: Existing/planned 20” pipeline

- Required Drawings:

- Alignment sheets

- Isometrics

- CP and coating drawings

- KP 93 – KP 125 (ELEP → AKAB)

- Key Features: 28” trunkline

- Required Drawings:

- Trunkline alignment

- Weld maps

- Hydrotest layouts

- SCADA layouts

- KP 125 – AKAB Gas Hub

- Key Features: Processing hub

- Required Drawings:

- Full plot plan

- P&IDs

- Slug catcher / inlet facilities

- Export tie-ins (methanol / LNG)

# Project Engineering

## Facilities Highlight

- API 5L X70 Mild Carbon Steel, to be concrete coated throughout the entire pipeline length for negative buoyancy (given the all-year flooded swampy terrain), and enhanced physical protection; except at river crossings where HDD method will be used.

However, the continuous HDD (Horizontal Directional Drilling) option was evaluated against the backdrop of pipeline vandalization, and may be considered if the security risk assessment dictates as we progress.

- Manifolds integration between the BFPCL Pipeline Manifold Platforms and SPDC Well Pad Manifold Platforms at BBOU and ELEP.

- Submarine Armoured Power Cable from the Plant Complex at AKAB to ELEP and BBOU Manifolds for power supply to the manifolds.

## Interfaces

The interfaces related to the project that need to be managed are as follows:

- Interface of BFPCL Pipeline Manifolds with SPDC Well Pad Manifolds at BBOU and ELEP, in respect of power supply from BFPCL, tie-ins to the SPDC bulklines, metering, chemical injection, data transfer, telecommunications, utilities, drain systems, cold vent, control systems, safeguarding systems, operations start-up.

- Interface of BFPCL Pipeline End Manifold at AKAB with BFPCL Slug Catcher, and the Plant Complex, in respect of power supply from BFPCL Captive Power Plant, tie-in to the Slug Catcher, metering, chemical injection, data transfer, telecommunications, utilities, drain systems, flare, control, & safeguarding systems, pre-commissioning, operations start-up.

- The contractor will manage interfaces with subcontractors within its scope.

- Site installation with con-current operations will require a robust interface and IAP (integrated activity planning) with the operations team for detailed design, shutdown, tie-ins, PTW management, etc. The BFPCL / SPDC OR&A engineers and representatives from the Production Operations function will form part of the project team. These personnel will be required to be part of key review events during detailed design, construction, commissioning and start-ups.

- The BFPCL SD team will manage interfaces with communities and local contractors across the Pipeline stretch, through MOU that will be put in place, and framework that will be provided by the Project SP plan.

- Other interfaces with partners, discipline engineering, regulatory agencies, etc. will be managed by the PMT.

## Project Cost Estimate

The EPC Cost Estimate of the Pipeline System is USD193,590,106.

| S/N |  |  | Item Description | BOQ or Specification | Cost |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | NGN | USD |
| I | Direct Cost |  |  |  |  |  |
| 1 |  | Pipeline Cost |  |  |  |  |
|  |  | 1.1 | Line Pipes | FEED Specification |  |  |
|  |  | 1.2 | Key Equipment | FEED Specification |  |  |
|  |  | 1.3 | Other Equipment | FEED Specification |  |  |
|  |  | 1.4 | Bulk Materials (Pipe / Valve / Flange / Miscellaneous) | FEED BOQ |  |  |
|  |  | 1.5 | Structural Steel | FEED BOQ |  |  |
|  |  | 1.6 | Cable & Electric | FEED BOQ |  |  |
|  |  | 1.7 | Civil Work | FEED BOQ |  |  |
|  |  | 1.8 | MEI Installation Work | FEED BOQ |  |  |
| 2 |  | Consumable for Initial Filling |  |  |  |  |
| 3 |  | Incidental Cost of Eqpt & Materials |  |  |  |  |
|  |  | 3.1 | Ocean Freight & Ocean Shipping Insurance |  |  |  |
|  |  | 3.2 | Local Transportation to Site |  |  |  |
| II | Indirect Cost |  |  |  |  |  |
| 1 |  | Pre-Engineering Survey |  |  |  |  |
| 2 |  | Detail Engineering Design |  | Man-Hours Estimated |  |  |
| 3 |  | Project Management |  | Man-Hours Estimated |  |  |
| 4 |  | Procurement Service |  | Man-Hours Estimated |  |  |
| 5 |  | Construction Management |  | Man-Hours Estimated |  |  |
| 6 |  | Insurance Fee |  |  |  |  |
| 7 |  | Commissioning |  |  |  |  |
| 8 |  | Permits Fee |  |  |  |  |
| 9 |  | HSE Fee |  |  |  |  |
| 10 |  | Training |  |  |  |  |
|  |  | Total |  |  |  |  |

| Ref Embed 3.2: EPC Cost Estimate of the Pipeline System |  |
| --- | --- |

## The Phase 1 Pipelines Route / Right of Way

The pipeline route proposed for this phase 1 has been surveyed, and the survey report issued for the FEED.

|  | The pipeline route / Right of Way, running from OKNU through BBOU through ELEP to AKAB is shown in the satellite image on the left |
| --- | --- |
| Fig 3-1: Satellite Image of the proposed OKNU - BBOU – ELEP - AKAB Right of Way |  |

| Ref: Fig 3-1: Satellite Image of the proposed BBOU – ELEP - AKAB Right of Way & Embed 3.4: BFPCL Bubouwe – Akabel Topographical |  |
| --- | --- |

However, the route survey needs to be repeated as pre-eng survey to close the following gaps:

- To incorporate pipeline route extension resulting from the current BBOU and ELEP Manifold locations advised by SPDC; and to follow the conventional description of from source of flow to destination, i.e., from BBOU to ELEP to AKAB.

- To give proper offset from the ELEP Manifold.  The present pipeline runs through the manifold location which should not be.

- Rerouting of Pipeline approach to end at the slug catcher instead of the methanol plant.

- Rerouting of pipeline route from Fantuo community (Bend B) to land at GPP, as dictated by political sensitivity around the Otokolopiri area makes it imperative to re-route pipeline

| Ref Embed 3.4.2: Gas PL Route BBOU-ELEP-AKAB |  |
| --- | --- |

- The parcellation survey did not precisely structure ownership communities on the RoW, more so as the new 2.5 km extension of the route is yet to be surveyed, and re-routing at the Akabel end is being considered, update to ownership of land has to be made.

- The bathymetric data of some creeks and creeklets were not indicated on the drawing.

- All rivers, creeks and creek-lets should be labelled serially end-to-end with appropriate IDs for easy referencing.

- Bathymetric chart datum should be tied to project elevation datum and not on predicted tide.

- It’s reported that topographical spot-heightening was conducted on ROW centreline at 25m interval, but the centreline was never traversed.

- There is no topographical elevation data on the entire ROW

## The Phase 1 Geotechnical Survey

The Geotechnical Survey has been done by Brone, and report issued for use in the foundation design.

| Ref Embed 3.5: Soil Investigation Survey Draft Final Report |  |
| --- | --- |

However, pre-Engineering Geotechnical survey for the pipeline Row also needs to be carried out to establish dense foundation strata, as well as cover the current pipeline manifold platform locations.  In this respect, a geotechnical consultant and accredited soil testing laboratory will have to be engaged for analysis of data, - to enable close the following gaps:

- Brone’s thorough review of their recommendation to install piles at unstable soft formation of soil, which Epic does not see as feasible.  This soft formation can be seen from the lithograph in the report prepared by BRONE.

- EPIC position is that even at 15m depth, the soil is incapable of bearing manifold loads in the magnitude of more than 460Mt, hence need for further deeper soil investigation (This view is also shared by BRONE in its report).

- From BRONE report, BH 20 that has the highest SPT - N counts are used by EPIC to compute the in-situ undrained shear strength and angles of internal friction of samples at various depths to 15m deepest termination layer. The estimated empirical result reveals a negative undrained shear strength; hence this layer of formation cannot support the imposed loads.

| Ref Embed 3.4: Undrained Shear Strength Computation |  |
| --- | --- |

- The graphical illustration of the –ve undrain shear strengths/cohesion when plotted against SPT shows an inverse settlement of the pile when compared with +ve settlement depicting that at 15m the layer cannot settle uniformly (See embed file).

| Ref Embed 3.5.4: Illustration of -ve Undrained Shear Strength |  |
| --- | --- |

- There is no Geological model to show lateral and vertical extend of 'soil strata on the investigated locations, including the ‘sand which may likely be silt’ formation as depicted in BH 1,2,9 profile, hence the ‘’sand’’ formation couldn’t have just been profiled to terminate exactly at every 500 meters boundary as depicted in the lithology (see in BRONE report).

## Design Criteria

### Design Life

The Design Life of this project is 30 years.

### Design Units

The FEED design was carried out using SI units. This is in accordance with DEP 00.00.20.10 – GEN (The use of SI Quantities and Units – Endorsement of ISO/IEC 80000) which specifies requirements and gives recommendations for the expression of quantities in SI units.

### Cost Effectiveness & Life Cycle Cost

The Phase 1 & 2 pipelines are sized to deliver gas at the pressure required at Akabel, without the need for booster compressors, thereby avoiding higher Capex & Opex of compression when compared with the savings from use of smaller pipe size, coupled with opportunity cost owing to availability & reliability challenges associated with compressors.

### Future Expansion - Phase-2 Facilities

The design has made provision for tie-ins at ELEP & BBOU Manifolds for the future Phase-2 production coming through NURN-ELEP & OPUG-BBOU Pipelines respectively.

### Future Expansion – Proposed 1 Bscfd Gas Hub at Akabel

The Phase 1 & 2 pipelines are designed without the need for booster compression, and hence are at their maximum sizes.  These pipeline sizes are therefore robust enough to support the addition of loopline to the ELEP-AKAB Pipeline in optimal mix with booster compressors, as future expansion in respect of realising the proposed 1 Bscfd Gas Hub at Akabel.

### Buoyancy Combat

Concrete Coating through the entire pipeline length, for negative buoyancy, and enhanced physical protection, - except at River Crossings where there will be HDD (Horizontal Directional Drilling) across the river.

### Flood Combat

Placement of the Pipeline Manifold Platforms at a height that is reasonably above flood level that will ever be experienced in the area, - drawing lessons from the 2012 rare flood experience.

### Standardisation

Choice of wet gas metering at the Custody Transfer Point was standardised as Venturi Meter, which is what SPDC proposed to use at their Well Pad Manifold.

## Local Requirements

### Language

English language is the approved project language. All project documentation, drawings, correspondence were provided in English Language.

### Local Content Requirement

The project shall ensure compliance with the Nigeria oil and gas industry content development act directives and associated requirement by the NCDMB (Nigerian content development monitoring board) The FEED of the project complied with the requirement for design with the FEED done in-country and minimum of 90% of the man-hours achieved in-country. The NCD law requires that:

- FEED and Detailed engineering on onshore facilities to be conducted in Nigeria with a minimum of 90% of the man hours in-country.

- Minimum fabrication of 80% by tonnage of steel in Nigeria or by registered OEM.

- Supply of the following materials where possible from Nigeria or by registered OEM: steel line pipes, steel plate, valves, LV and HV Cables etc.

- Employment and training of Nigerian labour and project personnel.

The project Nigerian content plan will be updated by the project management team before the start of detailed design.