## Slide 1: Pipeline Decommissioning & Abandonment Strategy
OKNU–BBOU–ELEP–AKAB Gas System (125 km)
Hybrid Removal + Abandonment | Investment Committee Pack

## Slide 2: Executive Overview
Integrated decommissioning of ~125 km pipeline network
Hybrid strategy: Removal + Abandonment-in-Place
Designed for Niger Delta swamp, river, and offshore conditions
Objectives: Safety, Compliance, Cost Optimization, Asset Recovery (TAR)

## Slide 3
System Overview (OKNU → AKAB)
OKNU (KP0)
River Niger (KP10)
KP38
KP66
BBOU (KP85)
ELEP (KP93)
AKAB (KP125)

## Slide 4
KP Strategy Map (Remove / Abandon / Mixed)
KP0
MIXED
KP10
ABANDON
KP38
REMOVE
KP66
REMOVE
KP85
REMOVE
KP93
REMOVE
KP125
REMOVE

## Slide 5: Decommissioning Process Flow
Planning & Approvals → Engineering & Preparation → Shutdown & Isolation
Cleaning & Inerting → Segmentation & Disconnection
Decision: Remove or Abandon
Execution → Waste Management → Restoration → Close-out

## Slide 6: Key Decommissioning Processes
Shutdown, isolation, and system segmentation
Pigging, cleaning, and hydrocarbon removal
Flushing, drying, and nitrogen inerting
Disconnection and preparation for execution

## Slide 7: Abandonment Activities
Cleaning to hydrocarbon-free condition
Permanent isolation (caps, blinds)
Flooding / grouting / stabilization
Cathodic protection decommissioning and records update

## Slide 8: Removal Activities
Excavation using swamp-compatible equipment
Cutting, lifting, and transportation
Scrap recovery and reuse (TAR)
Facility dismantling (manifolds, slug catchers, metering)

## Slide 9: Decision Framework
Is environment sensitive? → Abandon
Is access feasible? → Remove
Cost vs risk optimization
Regulatory validation and long-term liability check

## Slide 10: Niger Delta Constraints
Swamp instability and access limitations
Mangrove and biodiversity protection
Major river and creek crossings
Community and stakeholder interface

## Slide 11
Integrated Schedule (Jul–Dec 2026)
Phase | Jul | Aug | Sep | Oct | Nov | Dec
FEED Finalization | X | X |  |  |  | 
Regulatory Approvals | X | X | X |  |  | 
Detailed Planning |  | X | X |  |  | 
Procurement & Mobilization |  | X | X | X |  | 
Cleaning & Isolation |  |  |  | X | X | 
Segmentation & Disconnection |  |  |  | X | X | 
Removal Activities |  |  |  |  | X | X
Abandonment Activities |  |  |  |  | X | X
Restoration & Reinstatement |  |  |  |  |  | X
Close-out & Certification |  |  |  |  |  | X