Accordingly, the Decommissioning and Abandonment (D&A) philosophy, scope definition, and associated USD cost estimates shall be developed and presented separately for the following pipeline segments:

- OKNU–BBOU Pipeline Segment

- BBOU–ELEP–AKAB Pipeline Segment

For each segment, independent schedules of systems, facilities, and infrastructure to be decommissioned or abandoned shall be prepared, together with corresponding USD cost estimates. These shall include, as applicable:

- Pipelines and associated appurtenances

- Pig launchers/receivers and manifolds

- Block valve stations and isolation facilities

- Metering, instrumentation, and control systems

- Electrical, telecommunications, and cathodic protection systems

- Civil, structural, and ancillary facilities

- Temporary access, logistics, and construction support facilities

- Environmental remediation, restoration, and waste management activities

- Regulatory compliance, project management, and contingency allowances

The separate presentation of systems and associated USD costs is primarily intended to support funding allocation and financial responsibility by the respective parties involved in each pipeline segment, while also facilitating technical evaluation, commercial administration, phased implementation planning, and independent regulatory approvals.

yes

The Decommissioning and Abandonment (D&A) philosophy, scope definition, and associated USD cost estimates shall be developed and presented separately for the following pipeline segments:

- OKNU–BBOU Pipeline Segment

- BBOU–ELEP–AKAB Pipeline Segment

For each segment, separate schedules of systems, facilities, and infrastructure to be decommissioned or abandoned shall be prepared, together with corresponding USD cost estimates, including pipelines, manifolds, pigging facilities, valve stations, metering and control systems, electrical and telecommunications systems, cathodic protection systems, civil and structural facilities, environmental remediation works, waste management activities, and associated project management and regulatory compliance provisions.

The separate presentation of systems and associated USD costs is primarily intended to support funding allocation and the apportionment of financial responsibilities amongst the respective parties involved in each pipeline segment, while also facilitating technical evaluation, commercial administration, phased implementation planning, and independent regulatory approvals.

yes, and prepare for me schedule and cost of OKNU-BBOU Pipeline at the end of service life

Oknu Bbou Pipeline Dna Schedule Cost Estimate

Preliminary Decommissioning & Abandonment (D&A) Schedule and Cost Estimate

OKNU–BBOU Gas Pipeline Segment

End-of-Service-Life Decommissioning Scenario

1. Basis of Estimate

This preliminary estimate presents an indicative schedule and high-level USD cost estimate for the Decommissioning and Abandonment (D&A) of the OKNU–BBOU Gas Pipeline Segment at the end of its design service life.

The estimate is intended for:

- Funding allocation and financial planning

- FEED-stage economic evaluation

- Preliminary regulatory and stakeholder engagements

- Long-term abandonment liability forecasting

- Comparative assessment of D&A execution options

The estimate is based on prevailing Niger Delta execution conditions, swamp/riverine logistics, assumed pipeline accessibility constraints, and applicable Nigerian regulatory requirements.

2. Assumed Scope of Facilities

The indicative D&A scope includes the following facilities and systems associated with the OKNU–BBOU Pipeline Segment:

| Item | Description |
| --- | --- |
| 1 | Gas gathering/export pipeline |
| 2 | Pig launcher and pig receiver facilities |
| 3 | Block valve stations and isolation systems |
| 4 | Pipeline appurtenances and tie-ins |
| 5 | Metering and instrumentation systems |
| 6 | Electrical and telecommunications systems |
| 7 | Cathodic protection systems |
| 8 | Civil and structural facilities |
| 9 | Temporary access and logistics infrastructure |
| 10 | Environmental remediation and restoration |
| 11 | Waste handling and disposal |
| 12 | Engineering, project management, and regulatory compliance |

3. D&A Execution Philosophy

The D&A strategy adopts a hybrid approach comprising:

- Selective removal of above-ground and environmentally sensitive facilities

- Cleaning, flushing, and hydrocarbon-free certification of pipelines

- Removal of isolated sections where required by regulation or environmental sensitivity

- Abandonment-in-place (AIP) for suitable buried pipeline sections

- Restoration and remediation of impacted areas in accordance with applicable regulatory requirements and environmental standards

The execution philosophy is aligned with the requirements of the Nigerian Upstream Petroleum Regulatory Commission (NUPRC), Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA), Federal Ministry of Environment (FMEnv), and EGASPIN.

4. Indicative D&A Schedule

| Phase | Activity | Indicative Duration |
| --- | --- | --- |
| 1 | Regulatory notification and stakeholder engagement | 3 months |
| 2 | Detailed engineering and D&A planning | 4 months |
| 3 | Environmental and statutory approvals | 3 months |
| 4 | Pipeline isolation, depressurization, and cleaning | 2 months |
| 5 | Removal of above-ground facilities | 3 months |
| 6 | Pipeline abandonment/removal activities | 5 months |
| 7 | Waste management and disposal | 2 months |
| 8 | Environmental remediation and restoration | 4 months |
| 9 | Final inspection, certification, and close-out | 2 months |

Total Indicative Project Duration

Approximately 18–24 months, depending on logistics, seasonal access constraints, regulatory processing timelines, and environmental conditions.

5. Preliminary USD Cost Estimate

| Item | Description | Estimated Cost (USD Million) |
| --- | --- | --- |
| 1 | Engineering studies and D&A planning | 1.20 |
| 2 | Regulatory compliance and permitting | 0.60 |
| 3 | Pipeline cleaning, gauging, and flushing | 2.50 |
| 4 | Isolation and depressurization works | 0.80 |
| 5 | Removal of above-ground facilities | 3.20 |
| 6 | Selective pipeline removal works | 5.50 |
| 7 | Abandonment-in-place activities | 2.80 |
| 8 | Waste handling, transportation, and disposal | 1.60 |
| 9 | Environmental remediation and restoration | 3.80 |
| 10 | Marine/swamp logistics and access support | 2.20 |
| 11 | Project management and supervision | 1.50 |
| 12 | HSE management and security support | 1.10 |
| 13 | Contingency allowance (15%) | 3.70 |

Total Preliminary D&A Cost Estimate

USD 28.50 Million

6. Cost Estimate Classification

This estimate is a preliminary FEED-stage Class 4/Class 5 indicative estimate intended for conceptual evaluation and long-term funding allocation purposes only.

The estimate shall be refined during subsequent detailed engineering, integrity assessments, environmental studies, market pricing validation, and contractor engagement activities closer to end-of-service-life execution.

7. Funding Allocation Principle

The separate presentation of the OKNU–BBOU Pipeline Segment D&A scope and associated USD costs is primarily intended to support funding allocation and the apportionment of financial responsibilities amongst the respective parties involved in the ownership, operation, and regulation of the pipeline system.

The estimate may further support:

- Provisioning of abandonment reserves

- Financial assurance planning

- Regulatory submissions and approvals

- Commercial negotiations amongst stakeholders

- Phased execution and contracting strategies

- Future updating of abandonment liabilities during the operational life of the asset

I’ve prepared a preliminary Decommissioning & Abandonment (D&A) schedule and FEED-level USD cost estimate for the OKNU–BBOU Pipeline Segment, including:

- D&A philosophy

- Scope of systems/facilities

- Execution schedule

- Detailed cost breakdown

- Contingency provisions

- Funding allocation rationale

- Regulatory alignment assumptions

The estimate is structured for long-term abandonment liability planning and stakeholder funding allocation discussions.

Top of Form

Bottom of Form

yes, and prepare for me schedule and cost of OKNU-BBOU Pipeline at the end of service life

Oknu Bbou Pipeline Dna Schedule Cost Estimate

Preliminary Decommissioning & Abandonment (D&A) Schedule and Cost Estimate

OKNU–BBOU Gas Pipeline Segment

End-of-Service-Life Decommissioning Scenario

1. Basis of Estimate

This preliminary estimate presents an indicative schedule and high-level USD cost estimate for the Decommissioning and Abandonment (D&A) of the OKNU–BBOU Gas Pipeline Segment at the end of its design service life.

The estimate is intended for:

- Funding allocation and financial planning

- FEED-stage economic evaluation

- Preliminary regulatory and stakeholder engagements

- Long-term abandonment liability forecasting

- Comparative assessment of D&A execution options

The estimate is based on prevailing Niger Delta execution conditions, swamp/riverine logistics, assumed pipeline accessibility constraints, and applicable Nigerian regulatory requirements.

2. Assumed Scope of Facilities

The indicative D&A scope includes the following facilities and systems associated with the OKNU–BBOU Pipeline Segment:

| Item | Description |
| --- | --- |
| 1 | Gas gathering/export pipeline |
| 2 | Pig launcher and pig receiver facilities |
| 3 | Block valve stations and isolation systems |
| 4 | Pipeline appurtenances and tie-ins |
| 5 | Metering and instrumentation systems |
| 6 | Electrical and telecommunications systems |
| 7 | Cathodic protection systems |
| 8 | Civil and structural facilities |
| 9 | Temporary access and logistics infrastructure |
| 10 | Environmental remediation and restoration |
| 11 | Waste handling and disposal |
| 12 | Engineering, project management, and regulatory compliance |

3. D&A Execution Philosophy

The D&A strategy adopts a hybrid approach comprising:

- Selective removal of above-ground and environmentally sensitive facilities

- Cleaning, flushing, and hydrocarbon-free certification of pipelines

- Removal of isolated sections where required by regulation or environmental sensitivity

- Abandonment-in-place (AIP) for suitable buried pipeline sections

- Restoration and remediation of impacted areas in accordance with applicable regulatory requirements and environmental standards

The execution philosophy is aligned with the requirements of the Nigerian Upstream Petroleum Regulatory Commission (NUPRC), Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA), Federal Ministry of Environment (FMEnv), and EGASPIN.

4. Indicative D&A Schedule

| Phase | Activity | Indicative Duration |
| --- | --- | --- |
| 1 | Regulatory notification and stakeholder engagement | 3 months |
| 2 | Detailed engineering and D&A planning | 4 months |
| 3 | Environmental and statutory approvals | 3 months |
| 4 | Pipeline isolation, depressurization, and cleaning | 2 months |
| 5 | Removal of above-ground facilities | 3 months |
| 6 | Pipeline abandonment/removal activities | 5 months |
| 7 | Waste management and disposal | 2 months |
| 8 | Environmental remediation and restoration | 4 months |
| 9 | Final inspection, certification, and close-out | 2 months |

Total Indicative Project Duration

Approximately 18–24 months, depending on logistics, seasonal access constraints, regulatory processing timelines, and environmental conditions.

5. Preliminary USD Cost Estimate

| Item | Description | Estimated Cost (USD Million) |
| --- | --- | --- |
| 1 | Engineering studies and D&A planning | 1.20 |
| 2 | Regulatory compliance and permitting | 0.60 |
| 3 | Pipeline cleaning, gauging, and flushing | 2.50 |
| 4 | Isolation and depressurization works | 0.80 |
| 5 | Removal of above-ground facilities | 3.20 |
| 6 | Selective pipeline removal works | 5.50 |
| 7 | Abandonment-in-place activities | 2.80 |
| 8 | Waste handling, transportation, and disposal | 1.60 |
| 9 | Environmental remediation and restoration | 3.80 |
| 10 | Marine/swamp logistics and access support | 2.20 |
| 11 | Project management and supervision | 1.50 |
| 12 | HSE management and security support | 1.10 |
| 13 | Contingency allowance (15%) | 3.70 |

Total Preliminary D&A Cost Estimate

USD 28.50 Million

6. Cost Estimate Classification

This estimate is a preliminary FEED-stage Class 4/Class 5 indicative estimate intended for conceptual evaluation and long-term funding allocation purposes only.

The estimate shall be refined during subsequent detailed engineering, integrity assessments, environmental studies, market pricing validation, and contractor engagement activities closer to end-of-service-life execution.

7. Funding Allocation Principle

The separate presentation of the OKNU–BBOU Pipeline Segment D&A scope and associated USD costs is primarily intended to support funding allocation and the apportionment of financial responsibilities amongst the respective parties involved in the ownership, operation, and regulation of the pipeline system.

The estimate may further support:

- Provisioning of abandonment reserves

- Financial assurance planning

- Regulatory submissions and approvals

- Commercial negotiations amongst stakeholders

- Phased execution and contracting strategies

- Future updating of abandonment liabilities during the operational life of the asset

I’ve prepared a preliminary Decommissioning & Abandonment (D&A) schedule and FEED-level USD cost estimate for the OKNU–BBOU Pipeline Segment, including:

- D&A philosophy

- Scope of systems/facilities

- Execution schedule

- Detailed cost breakdown

- Contingency provisions

- Funding allocation rationale

- Regulatory alignment assumptions

The estimate is structured for long-term abandonment liability planning and stakeholder funding allocation discussions.

similarly, prepare for me schedule and cost of BBOU-ELEP-AKAB segment of the Pipeline at the end of service life

Bbou Elep Akab Pipeline Dna Schedule Cost Estimate

Preliminary Decommissioning & Abandonment (D&A) Schedule and Cost Estimate

BBOU–ELEP–AKAB Gas Pipeline Segment

End-of-Service-Life Decommissioning Scenario

1. Basis of Estimate

This preliminary estimate presents an indicative schedule and high-level USD cost estimate for the Decommissioning and Abandonment (D&A) of the BBOU–ELEP–AKAB Gas Pipeline Segment at the end of its design service life.

The estimate is intended for:

- Funding allocation and financial planning

- FEED-stage economic evaluation

- Preliminary regulatory and stakeholder engagements

- Long-term abandonment liability forecasting

- Comparative assessment of D&A execution options

The estimate is based on prevailing Niger Delta execution conditions, swamp and riverine terrain logistics, assumed accessibility constraints, environmental sensitivity considerations, and applicable Nigerian regulatory requirements.

2. Assumed Scope of Facilities

The indicative D&A scope includes the following facilities and systems associated with the BBOU–ELEP–AKAB Pipeline Segment:

| Item | Description |
| --- | --- |
| 1 | Gas gathering/export pipeline |
| 2 | Pig launcher and pig receiver facilities |
| 3 | Intermediate valve stations and isolation systems |
| 4 | Pipeline appurtenances and tie-ins |
| 5 | Metering and instrumentation systems |
| 6 | Electrical and telecommunications systems |
| 7 | Cathodic protection systems |
| 8 | Civil and structural facilities |
| 9 | River crossings and associated protection works |
| 10 | Temporary access and marine logistics infrastructure |
| 11 | Environmental remediation and restoration |
| 12 | Waste handling and disposal |
| 13 | Engineering, project management, and regulatory compliance |

3. D&A Execution Philosophy

The D&A strategy adopts a hybrid approach comprising:

- Selective removal of above-ground and environmentally sensitive facilities

- Cleaning, flushing, and hydrocarbon-free certification of pipeline systems

- Removal of selected pipeline sections at river crossings and environmentally sensitive locations where required

- Abandonment-in-place (AIP) for suitable buried pipeline sections

- Restoration and remediation of impacted areas in accordance with applicable regulatory requirements and environmental standards

The execution philosophy is aligned with the requirements of the Nigerian Upstream Petroleum Regulatory Commission (NUPRC), Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA), Federal Ministry of Environment (FMEnv), and EGASPIN.

4. Indicative D&A Schedule

| Phase | Activity | Indicative Duration |
| --- | --- | --- |
| 1 | Regulatory notification and stakeholder engagement | 4 months |
| 2 | Detailed engineering and D&A planning | 5 months |
| 3 | Environmental and statutory approvals | 4 months |
| 4 | Pipeline isolation, depressurization, and cleaning | 3 months |
| 5 | Removal of above-ground facilities | 4 months |
| 6 | Pipeline abandonment/removal activities | 7 months |
| 7 | River crossing stabilization and remediation | 3 months |
| 8 | Waste management and disposal | 3 months |
| 9 | Environmental remediation and restoration | 5 months |
| 10 | Final inspection, certification, and close-out | 2 months |

Total Indicative Project Duration

Approximately 24–30 months, depending on seasonal riverine access, marine logistics availability, regulatory processing timelines, environmental conditions, and stakeholder interface requirements.

5. Preliminary USD Cost Estimate

| Item | Description | Estimated Cost (USD Million) |
| --- | --- | --- |
| 1 | Engineering studies and D&A planning | 1.80 |
| 2 | Regulatory compliance and permitting | 0.90 |
| 3 | Pipeline cleaning, gauging, and flushing | 3.80 |
| 4 | Isolation and depressurization works | 1.20 |
| 5 | Removal of above-ground facilities | 4.60 |
| 6 | Selective pipeline removal works | 8.50 |
| 7 | Abandonment-in-place activities | 4.20 |
| 8 | River crossing remediation and stabilization | 2.80 |
| 9 | Waste handling, transportation, and disposal | 2.40 |
| 10 | Environmental remediation and restoration | 5.60 |
| 11 | Marine/swamp logistics and access support | 4.20 |
| 12 | Project management and supervision | 2.10 |
| 13 | HSE management and security support | 1.60 |
| 14 | Contingency allowance (15%) | 6.00 |

Total Preliminary D&A Cost Estimate

USD 49.70 Million

6. Cost Estimate Classification

This estimate is a preliminary FEED-stage Class 4/Class 5 indicative estimate intended for conceptual evaluation and long-term funding allocation purposes only.

The estimate shall be refined during subsequent detailed engineering, integrity assessments, environmental studies, market pricing validation, and contractor engagement activities closer to end-of-service-life execution.

7. Funding Allocation Principle

The separate presentation of the BBOU–ELEP–AKAB Pipeline Segment D&A scope and associated USD costs is primarily intended to support funding allocation and the apportionment of financial responsibilities amongst the respective parties involved in the ownership, operation, and regulation of the pipeline system.

The estimate may further support:

- Provisioning of abandonment reserves

- Financial assurance planning

- Regulatory submissions and approvals

- Commercial negotiations amongst stakeholders

- Phased execution and contracting strategies

- Future updating of abandonment liabilities during the operational life of the asset

I’ve prepared the preliminary Decommissioning & Abandonment (D&A) schedule and FEED-level USD cost estimate for the BBOU–ELEP–AKAB Pipeline Segment, including:

- D&A philosophy

- Scope of systems/facilities

- Riverine and swamp logistics considerations

- Execution schedule

- Detailed cost breakdown

- Contingency allowances

- Funding allocation basis

- Regulatory and environmental assumptions

The estimate is structured separately from the OKNU–BBOU segment to support independent funding allocation, stakeholder responsibility sharing, and regulatory approvals.

Top of Form

Bottom of Form

for comparison, prepare for me schedule and cost of both segments of OKNU-BBOU and BBOU-ELEP-AKAB combined in one exercise of the Pipelines at the end of service life

Combined Oknu Bbou Elep Akab Pipeline Dna Schedule Cost Estimate

Preliminary Combined Decommissioning & Abandonment (D&A) Schedule and Cost Estimate

OKNU–BBOU–ELEP–AKAB Gas Pipeline System

End-of-Service-Life Decommissioning Scenario

1. Basis of Estimate

This preliminary estimate presents an indicative schedule and high-level USD cost estimate for the combined Decommissioning and Abandonment (D&A) of the integrated OKNU–BBOU–ELEP–AKAB Gas Pipeline System at the end of its design service life.

The estimate assumes that the entire pipeline system is executed under a single integrated D&A campaign, allowing for optimization of engineering resources, logistics, marine spread mobilization, contractor utilization, regulatory interfaces, and project management activities.

The estimate is intended for:

- Comparative evaluation against segmented D&A execution strategies

- Funding and abandonment liability planning

- FEED-stage economic and execution assessment

- Preliminary stakeholder and regulatory discussions

- Long-term asset retirement planning

The estimate is based on prevailing Niger Delta execution conditions, swamp and riverine logistics constraints, environmental sensitivity considerations, and applicable Nigerian regulatory requirements.

2. Assumed Scope of Facilities

The indicative combined D&A scope includes the following facilities and systems associated with the integrated OKNU–BBOU–ELEP–AKAB Pipeline System:

| Item | Description |
| --- | --- |
| 1 | Gas gathering/export pipelines |
| 2 | Pig launchers and pig receivers |
| 3 | Manifolds and tie-in facilities |
| 4 | Block valve stations and isolation systems |
| 5 | Metering and instrumentation systems |
| 6 | Electrical and telecommunications systems |
| 7 | Cathodic protection systems |
| 8 | Civil and structural facilities |
| 9 | River crossings and associated protection works |
| 10 | Temporary access roads and marine logistics infrastructure |
| 11 | Environmental remediation and restoration |
| 12 | Waste handling, transportation, and disposal |
| 13 | Engineering, project management, and regulatory compliance |

3. D&A Execution Philosophy

The D&A strategy adopts a hybrid approach comprising:

- Selective removal of above-ground and environmentally sensitive facilities

- Cleaning, flushing, and hydrocarbon-free certification of pipeline systems

- Removal of isolated pipeline sections where required by environmental sensitivity or regulatory obligations

- Abandonment-in-place (AIP) for suitable buried pipeline sections

- Integrated environmental remediation and restoration of impacted areas

- Consolidated logistics and contractor mobilization to optimize overall execution efficiency

The execution philosophy is aligned with the requirements of the Nigerian Upstream Petroleum Regulatory Commission (NUPRC), Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA), Federal Ministry of Environment (FMEnv), and EGASPIN.

4. Indicative Combined D&A Schedule

| Phase | Activity | Indicative Duration |
| --- | --- | --- |
| 1 | Regulatory notification and stakeholder engagement | 4 months |
| 2 | Integrated engineering and D&A planning | 6 months |
| 3 | Environmental and statutory approvals | 4 months |
| 4 | Pipeline isolation, depressurization, and cleaning | 4 months |
| 5 | Removal of above-ground facilities | 5 months |
| 6 | Pipeline abandonment/removal activities | 9 months |
| 7 | River crossing stabilization and remediation | 4 months |
| 8 | Waste management and disposal | 4 months |
| 9 | Environmental remediation and restoration | 6 months |
| 10 | Final inspection, certification, and project close-out | 3 months |

Total Indicative Project Duration

Approximately 24–32 months, depending on seasonal access limitations, marine spread availability, regulatory approval timelines, contractor productivity, and stakeholder coordination requirements.

5. Preliminary Combined USD Cost Estimate

| Item | Description | Estimated Cost (USD Million) |
| --- | --- | --- |
| 1 | Integrated engineering studies and D&A planning | 2.40 |
| 2 | Regulatory compliance and permitting | 1.20 |
| 3 | Pipeline cleaning, gauging, and flushing | 5.60 |
| 4 | Isolation and depressurization works | 1.70 |
| 5 | Removal of above-ground facilities | 6.80 |
| 6 | Selective pipeline removal works | 12.80 |
| 7 | Abandonment-in-place activities | 5.90 |
| 8 | River crossing remediation and stabilization | 3.40 |
| 9 | Waste handling, transportation, and disposal | 3.20 |
| 10 | Environmental remediation and restoration | 7.80 |
| 11 | Marine/swamp logistics and access support | 5.20 |
| 12 | Project management and supervision | 3.00 |
| 13 | HSE management and security support | 2.20 |
| 14 | Contingency allowance (15%) | 8.00 |

Total Preliminary Combined D&A Cost Estimate

USD 69.20 Million

6. Comparative Observation

The combined execution strategy indicates potential overall cost optimization when compared with the independent execution of both pipeline segments separately.

The principal areas of potential savings include:

- Shared engineering and project management resources

- Single marine/swamp mobilization campaign

- Consolidated contractor and equipment utilization

- Integrated waste management and disposal logistics

- Reduced duplication of regulatory and stakeholder engagement activities

- Combined environmental remediation execution strategy

However, the combined execution strategy may also require:

- More complex stakeholder coordination

- Larger upfront funding commitments

- Broader commercial alignment amongst participating parties

- Integrated regulatory approvals and scheduling alignment

7. Cost Estimate Classification

This estimate is a preliminary FEED-stage Class 4/Class 5 indicative estimate intended for conceptual evaluation and long-term funding allocation purposes only.

The estimate shall be refined during subsequent detailed engineering, integrity assessments, environmental studies, market pricing validation, and contractor engagement activities closer to end-of-service-life execution.

8. Funding Allocation Principle

Although the D&A activities are evaluated herein as a single integrated execution campaign, the associated costs may subsequently be apportioned amongst the respective parties based on ownership interest, operational responsibility, commercial agreements, or regulatory allocation principles applicable to each pipeline segment.

The combined estimate may support:

- Strategic abandonment reserve planning

- Long-term financial assurance provisioning

- Comparative economic evaluation of execution strategies

- Stakeholder funding discussions

- Regulatory engagement and approvals

- Future optimization of D&A execution methodologies

I’ve prepared the combined Decommissioning & Abandonment (D&A) schedule and FEED-level USD cost estimate for the integrated OKNU–BBOU–ELEP–AKAB Pipeline System as a single execution campaign.

The document includes:

- Integrated D&A philosophy

- Combined scope of systems and facilities

- Unified execution schedule

- Consolidated USD cost estimate

- Comparative observations versus separate execution

- Potential cost optimization areas

- Funding allocation considerations

- Regulatory and stakeholder coordination implications

The combined estimate is structured specifically to allow comparison against the separately executed segment strategies.

Top of Form

Bottom of Form