Comprehensive Reports on what Epic Atlantic have done or have been doing for Brass Fertilizer Petrochemical Company

The working relationship between Epic Atlantic Limited (“Epic”) and Brass Fertilizer & Petrochemical Company Limited (“Brass”) commenced in July 2013 — 12 years ago — following discussions between myself, Engr. Aloy Duru, Chief Executive of Epic, and Chief Femi Adesanya, a Director of Brass.

Chief Adesanya and I had previously worked together at The Shell Petroleum Development Company of Nigeria Limited (SPDC), where we developed a strong professional rapport. This mutual understanding of each other’s capabilities, forged during our time at SPDC, provided the foundation for our initial business discussions and the enduring partnership between Epic and Brass.

Epic is an oil and gas projects engineering and management firm, providing services across multiple sectors of Nigeria’s oil and gas industry. With recognized expertise in oil and gas facilities engineering, Epic brings multidimensional experience spanning onshore and offshore operations, gas solutions, field development planning, upstream facilities design and construction, production technology and operations, as well as project and asset management.

The engagement formally began with an invitation letter dated 12 July 2013, inviting Epic to join the BFPCL Project Team in creating a framework for developing and maturing an identified gas supply option for the Brass Fertilizer Project. Epic accepted this invitation through a letter dated 16 July 2013.

Consequently, Epic participated as part of the BFPCL Project Team in the inaugural meeting with SPDC Project Team on 17 July 2013, marking the formal joint team kick-off of the project.

On that note, Epic became engaged by BFPCL, with front end engineering works, spanning across the following, - importantly and remarkably:

- Feasibility / Screening Studies, and Conceptual Design

- Administration of Work Processes & Procedures, and Approvals towards Project’s Implementation, relating to Guidelines & Regulatory Requirements: - Permits & Consents, EIA, ESG, PTS / OPL, LTE / ATC, LTO, NCD, CSR, Factories Act

- Related Interfaces with SPDC / JV, 3rd Parties, and Regulators, and Multi-Disciplinary Challenge Sessions towards Benchmark & Best Practices, and Optimisation

- Consultant Subject Matter Experts in Engineering Processes, Procedures, & Methods relating to Oil & Project Maturation, and Natural Gas Pipelines & Process Plants

- Front End Engineering Design (FEED)

- Follow-on Engineering to ensure EPC readiness and smooth operations thereafter

Epic continues to support BFPCL by jointly steering the engineering and project management efforts toward the successful implementation of the Brass Fertilizer Project.

In April 2021, Epic was formally appointed as BFPCL’s Engineering Consultant, with responsibility for all Technical and Project Management Services related to the Dredging and Reclamation Works required to prepare the project site.

Epic has successfully delivered all its assigned front end engineering works from 2013 under BFPCL / SPDC promotion, through to the takeover of RAEC from SPDC in 2025 — notably including the FEED (Front-End Engineering Design) for the Gas Gathering Pipelines and associated infrastructure.

Currently, Epic oversees all engineering matters in BFPCL’s interface with RAEC, ensuring alignment and sustained progress. The project remains ongoing and is expected to advance through the required follow-on engineering into the EPC (Engineering, Procurement, and Construction) phase, and ultimately to commissioning, targeted for completion by 2030.

The table below gives the chronological overview, from the start of the relationship in 2013 to date:

|  | Period / serial no. | Description of Works | Key Elements & Features / Deliverables |
| --- | --- | --- | --- |
| A | 2013-2020 | Front Engineering Studies towards project’s Opportunity Maturation |  |
|  | 1 | Feasibility Study, and Conceptual Design | - Benchmarks & Best Practices - Pipelines Routes Selection / Facilities Configuration & Options - Concept Selection & Project’s Practicality, and Viability Assessment |
|  | 2 | Frameworks for Project Implementation: - Field Development Plan (FDP) - Regulatory Requirements & Regulators Approvals (DPR, NUPRC, NMDPRA) - Government Agencies Approvals - 3rd Parties Consents | Workshop on Regulatory Requirements, and Approval Processes, & Development of Permits & Consent Register / Drive towards approval: - EIA, ESG, ROW, PTS/OPL, LTE/ATC, LTO, NCD, CSR, Factories Act - Risk Assessment |
|  | 3 | Conceptual Design – Gas Pipelines & Gas Plant | - Facilities Configuration & Flow Assurance - Preliminary Project Specification |
|  | 4 | Ad-hoc Project Support Works to BFPCL | - Process Support - Tender for Site Preparation - Deputation on Permits & Consents Mgt |
| B | 2020-2024 | Front Engineering: - Scope Definition, Eng Design, Eqpt Selection, Cost Estimation & Project Schedule |  |
|  | 5 | Interfaces with BFPCL and Related Teams: - SPDC JV, NUPRC, NMDPRA, Agip, et al | - CSW / Multidisciplinary Challenge Sessions - Project Parameters Harmonisation |
|  | 6 | Engineering Design (FEED) | - Basis of Design / Project Specifications - EPC Scope of Work & Cost Estimate |
| C | 2025 - Date | Follow-on Engineering Towards EPC, - interface meetings with RAEC JV and Regulators |  |
|  | 7 | Follow-on Engineering Works Towards EPC | - Updates / Alignment of Parameters for EPC - LTE / OPL and Pipeline Crossing Agreements |

A comprehensive list of the key activities is summarized below chronologically

|  | Period / Item no. | s/n | Description of Works |  | Key Elements & Features / Deliverables |
| --- | --- | --- | --- | --- | --- |
| A | 2013-2020 | Front-end Engineering Studies Towards Opportunity Maturation |  |  |  |
|  | 1 | Feasibility Study, and Conceptual Design - Benchmarks & Best Practices - Pipelines Routes Selection / Facilities Configuration & Options - Concept Selection & Project’s Practicality, and Viability Assessment |  |  | Studies conducted against the backdrop of: - Two main configurations: - Central Gas Processing Plant, or Nodal Plants as options - Wellhead gas gathering from 5 fields – Bubouwe Bou (BBOU), Elepa (ELEP), Nun River (NUNR), Seibou (SEIB), & Opugbene (OPUG) - to central gas processing facility at Akabel 32 km from the nearest node (ELEP) and 97 km from the farthest node (SEIB) - Flow Assurance and deliverability at the right pressures, albeit compression / boosting that may be required - Project’s technical feasibility and commercial viability, balancing capital costs, operating costs, and implementation risks. - Production in phases, starting with BBOU and ELEP as phase1 - Options listing & costing - Concept Selection |
|  |  | 1 | Pipelines Routes Selection |  | A mix of Wellhead Flowlines, Field Manifolds, and Bulk Transport Lines, - optimally configured in terms of cost, layout, and choice of evacuation manifold: - Nodal Bulklines to Central Field/Satellite Manifolds, and Trunkline from Evacuation Manifold at ELEP to central Gas Plant Akabel - Optimal Route Selection between section Nodes, and End Manifold at the Gas Plant site at Akabel - Desktop Preparatory Survey of the 39 km phase-1 BBOU – ELEP – AKAB Route, and indicative routes for the subsequent phases |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  | 2 | Facilities Configuration & Schematics |  | Central Gas Processing Plant at Akabel with Facilities Configuration in three phases: - Phase-1 pipelines gathering wellhead fluids from Bubowei Bou (BBOU) and Elepa (ELEP) to the Central Gas Facility at Akabel - Phase-2 pipelines gathering wellhead fluids from Nun River (NUNR), Seibou (SEIB), and Opugbene (OPUG) to the Central Gas Facility at Akabel - 1 BSCFD Gas Hub Case gas from Okpokunou (OKPO) at a later phase (Phase-3) - Flow Assurance Evaluation of Pipeline Networks |
|  |  | 3 | Land Acquisition Survey (Pipeline ROW) for Conceptual Design, and PTS Application |  | Survey Works as follows: - Desktop Preparatory Survey of the 39 km phase-1 BBOU – ELEP – AKAB Route, capturing all communities traversed - Desktop Indicative Route Survey for the Phase2 pipelines, and the 1 BSCFD Gas Hub Case pipeline from OKPO to SEIB |
|  |  | 4 | Offshore Gas Gathering for Independent / Additional Gas Supply for the 1 Bscfd Gas Hub at Akabel |  | Offshore Gas Gathering from 4 Nodes in OMLs 88, 86, 116, & 137 to Akabel: - On the west flank: - OML 88 Chioma Field (CHIO), 103 km to Akabel, through OML 86 Funiwa Field (FUNI), 74 km to Akabel - On the east flank: - OML 137 Shokoloko Field (SHOK), 77 km to Akabel through OML 116 Agbara Field (AGBA), 41 km to Akabel |
|  | 2 | FDP (Field Development Plan) Document |  |  | Reference Document for Field Development Planning and Conceptual Design / FEED - Integrated FDP Document - Preliminary Basis for Design Document - Workshop on Regulatory Requirement & NTR (Non-Technical Risk) - Project EIA - Project Execution Readiness (Engineering Requirement) |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  | 3 | Interface Management |  |  | Interface with SPDC JV / Regulatory Authorities / 3rd Parties, in respect of the following work processes: - Schedule Alignment - GSPA Heads of Agreement - Liaison with Agip as a 3rd Party whose pipelines will be crossed in the exercise - Liaison with DPR and project presentation towards project approvals Liaison with FMenv / NIWA / etc approvals |
|  | 4 | Project Specifications Update for Conceptual Design / FEED Phase |  |  | Project Specifications Update, covering the following: - Project Survey – PTS & Route Survey, Geotechnical, EIA - Concept Selection - FDP - Basis Design – Gas Gathering Pipelines & Associated Infrastructure - Basic Design – Gas Processing Plant (including the Slug Catcher Specifications) |
|  | 5 | Best Practices & Benchmark Steps / Keeping Abreast with Technology & Frontiers, especially in respect of the following challenges: - Corrosion Management under the high operating pressure, given the corrosive nature of the fluid - Flow Assurance of the wet gas across large expanse pipeline network - Risk Assessment of Laying Marine Underground Power Cable - Risk Assessment of Continuous HDD over Surface Lay, on account of the security of the installed pipeline - Composite Power/Instrument vs Separate Cables - Risk Assessment of Platform Valves motorization vs Manual Valves |  |  | Two Conference Trips to ADIPEC Abu Dhabi, and discussions with conference delegates / exhibitors to gain more insights in new frontiers in respect of the following areas in the project design: - Materials Selection, - on account of substantial CO₂ content and high pressure - CO₂ and Water Removal - Most practicable seamless way of the CO₂ water removal - Continuous HDD - Evaluate the feasibility and risk mitigation for long, continuous HDD installations - Risk Assessment: Marine Underground Power Cable - Carry out updated risk assessments specific to marine and underground power cable installations, - Composite power cable / instrument cable - Investigate and evaluate the use of composite cables (power + control/instrumentation in one jacket), considering their performance, reliability, and installation challenges in marine/underground environments - Flow Assurance - Address flow assurance issues in the systems, including risks of hydrate formation and wax deposition - Platform valve motorization - Assess the need and best approach for motorisation of valves on platforms |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  | 5 | Corrosivity of Fluid / Flow Assurance: - CO₂ and Water Removal - Materials Selection - Flow Assurance |  | Best Practices and Benchmark: - CO₂ and Water Removal - Most practicable seamless way of the CO₂ water removal - Materials Selection, - on account of substantial CO₂ content and high pressure - Flow Assurance - Addressing flow assurance issues in the systems, including risks of hydrate formation and wax deposition |
|  |  | 6 | Continuous HDD vs Conventional Lay, evaluated at the backdrop of risk mitigation in respect of the following concerns: - Security of the Pipeline - Pragmatic construction, operations, and maintenance of the pipeline - Total cost of ownership (TCoO) - Flow Assurance |  | Benchmark: Option Selection, considering the predominantly swamp terrain & many river crossings, with challenging soil or seabed conditions. in the light of the following: - Security of the Pipeline, given the spread of pipeline vandalisation in the region - Construction, operations, and maintenance of the pipeline - Cost, - capex, operating, maintenance, abandonment, and total cost of ownership (TCoO) - Flow Assurance, including risks of hydrate formation and wax depositionn |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  | 7 | Risk Assessment: Marine Underground Power Cable - Carry out updated risk assessments specific to marine and underground power cable installations: - Security of the installation - Pragmatic construction, operations, and maintenance of the cable - Total cost of ownership (TCoO) |  | Benchmark: Marine underground power cable vs overhead / surface cable: - Risk Assessment of the security of the installed cable - Cost, - capex, operating, maintenance, abandonment, and total cost of ownership (TCoO) - Reliability in service |
|  |  | 8 | Rational Choice between platform valve motorization vs manual operation in the light of the following: - Requirement for motorisation - Requirement for manual operations - Total cost of ownership (TCoO) |  | Best Practices and Benchmark: Platform valve motorization - Assess the need and best approach for motorisation of valves on the manifold platforms leading to a choice between: - Motorised Valves - Manually Operated Valves, or - A combination |
|  | 5 | Conceptual Design – Gas Pipelines & Gas Plant |  |  |  |
|  |  | 5 | Opportunity Framing |  | - Defining the Strategic Context - Identifying and Evaluating Opportunities - Developing a Decision-Driven Roadmap |
|  |  | 6 | Development Concept Selection |  | - Development Options - Facility Design - Economic Evaluation - Sensitivity Analysis |
|  |  | 7 | Field Development Plan (FDP) |  | - Process Facilities - Infrastructure - Safety & Environmental Considerations - Economic & Risk Assessment - Project Management - Decommissioning & Abandonmen |
|  |  | 8 | Project Concept & Site for the Project |  |  |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  | 9 | Pipelines Routes |  |  |
|  |  | 11 | Basis of Design Elements |  | Key Elements are as listed in 12 -28, notably the following: - Project Design & Operating Philosophy - Wellhead Fluid Gas Gathering Systems - Process Description & Equipment Configuration - PFD and P&ID - Process Simulation & Flow Assurance Studies - Process Control & Safeguarding System - Safety & Environmental Considerations - Materials Selection & Corrosion Management - Decommissioning & Abandonment |
|  |  | 12 | Project Design Philosophy |  |  |
|  |  | 13 | Regulations, Codes & Standards |  | Notable are the following: - Petroleum Act CAP P10 - Mineral Oil (Safety) Regulations 1963 - Oil & Gas Pipelines Regulations - Environmental Impact Assessment Act, CAP E12, LFN 2004 - Federal Environmental Protection Agency Act, CAP F13, LFN 2004 - Environmental Guidelines and Standards for the Petroleum Industry in Nigeria (EGASPIN), 1991 - Nigerian Oil and Gas Industry Content Development (NOGICD) Act of 2010 - ASME B31.8 / B31.3 - Shell DEPs (Design & Engineering Practices) - API Recommended Practices |
|  |  | 14 | Process Description |  |  |
|  |  | 15 | Pipelines Routes |  |  |
|  |  | 16 | Process Flow Scheme / Diagram |  |  |
|  |  | 17 | Materials Selection & Corrosion Analysis |  |  |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  | 18 | Process Flow Simulation & Flow Assurance |  | - PIPESIM & HYSYS – for Steady State Hydraulics Analysis - OLGA - for Transient Simulation |
|  |  | 19 | Pipeline Transient Simulation Study - Olga |  |  |
|  |  | 20 | Power Supply Options Analysis |  | The following options evaluated notably against cost effectiveness, security of supply, reliability, among other parameters: - Solar in all platform manifolds - Cable Power in all platform manifolds, - underground or overhead - A combination of Cable & Solar Power - IPP in all Manifolds |
|  |  | 21 | Manifold Power Supply & Data Communication |  |  |
|  |  | 21 | Manifold Platform Plot Plan & Equipment General Assembly / Integration with SPDC Facilities |  |  |
|  |  | 22 | Gas Processing Concept & Process Flow |  |  |
|  |  | 23 | Feedstock & Product Metering Systems & Proving Procedures |  |  |
|  |  | 24 | Process Hazard Identification (HAZID) |  |  |
|  |  | 25 | Process Safety Systems |  |  |
|  |  | 26 | Infrastructural Supply Strategy and Manning |  |  |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  | 27 | Decommissioning Philosophy |  |  |
|  |  | 28 | Project Implementation Schedule |  |  |
|  | 6 | Administration of Work Processes & Procedures, and Approvals towards Project’s Implementation, in compliance with Guidelines & Regulatory Requirements |  |  | Compiled list of Approvals Requirement, and developed framework & progressed towards approvals: - PTS / OPL - EIA, ESG - DPR Approval to progress with Conceptual Design - Permits & Consents Drive, - EIA, ESG, PTS / OPL, LTE / ATC, LTO, NCD, CSR, Factories Act |
| B | 2017-2020 | Ad-hoc Project Support Works to BFPCL |  |  |  |
|  | 7 | Tender Administration in respect of Project Site Preparation: - Dredging & Reclamation Works |  |  | - Development of EOI Register and Bid Opening Records, - 28 bidders - Prepared & Agreed Evaluation Criteria with BFPCL - BFPCL/Epic Joint Bid Opening & scoring, and passing the results to BFPCL for further administration |
|  | 8 | Deputation of Permits & Consent Manager to oversee implementation of Regulatory Requirements |  |  | - Interface Meetings with NMDPRA project reps |
| C | 2020-2022 | Front Engineering Works Towards FEED, and its Implementation |  |  |  |
|  | 9 | Interface / Engagement Sessions with TCE (BFPCL PMC Contractor), SPDC JV, NUPRC, NMDPRA, and 3rd Parties |  |  | - Epic Conceptual Design Documents shared on TCE Wrench DCC Platform for Review & Comments / Challenge Session, leading to alignment and validation of the Conceptual Design - Epic Conceptual Design validated by TCE, and adopted by TCE as basis for the RFQ for the Pipelines FEED - Engagement with NMDPRA on Project Rep, leading to the nomination of 2 Reps for the project - Interface & Liaison with NMDPRA Rep on Regulatory Requirement Issues / Bi-weekly interface meetings; and institutionalization of Permits and Consents Register - Interface with Regulatory Authorities and Operators in respect of “No Objection Letters” in respect of PTS / OPL applications - Interface with SPDC on Project Milestones Reviews – Concept Select Workshops (CSW), ITR, etc - Interfaces in respect of Constructability, Schedule, HAZOP, etc Workshops - Engagements with SPDC & NUPRC on project matters that arise from time to time |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  | 10 | Interfaces / Liaison with BFPCL Contractors & Prospective Contractors, in respect of input and oversight of activities |  |  | - General / Routine Project Engineering Interface Management - ESIA bids, - scoped to include offshore SBM, dredging, jetty works, produc export P/L - Interface with FISAS (Fundamental Integrated Site Appraisal Services Limited), EIA / ESIR Contractor on the Project EIA works - Interface with Brone Position & Survey Limited – Pipeline Route Survey works - Interface with Estee Global on CSR works execution - Interface with DAL on bathymetric survey and sand search contract - Interface with prospective site preparation on technical & project management issues related to the RFQ - Engagements with SPDC & NUPRC |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  | 11 | General / Project Management & Documentation / Site Visits |  |  | Interface with Stakeholders & Auditors in respect of Site / Familiarisation Visits: - Site Visit of BFPCL Top Mgt and Executive Secretary of NCDMB - Site Visit of Auditors / Prospective Investors - Site Visit to quantify the works done by Site Clearing Contractor |
| D | 2022-2024 | Engineering Design (FEED) |  |  |  |
|  | 12 | FEED |  |  |  |
|  |  | 29 | General / Project Management & Documentation / Site Visits |  | - Project Plans - Project Documentation / Controls & Document Control |
|  |  | 30 | Project Execution Schedule - Baseline |  |  |
|  |  | 31 | Project’s MDR - Baseline |  |  |
|  |  | 32 | Project Execution Plan |  |  |
|  |  | 33 | Project Quality Management Plan (QA & QC) |  |  |
|  |  | 34 | Project HSE / ESG Plan |  |  |
|  |  | 35 | Project Survey Specification & Liaison with Survey Contractor |  | - Topographical / Geomatics Surveys - Bathymetry - Geotechnical Surveys & Soil Test |
|  |  | 36 | Compliance Monitoring & Project Controls |  | vis-à-vis: - Regulations, Codes & Standards - DEPs & Project Specification - API Recommended Practices - Projects Specifications |
|  |  | 37 | Project Engineering / FEED Package |  |  |
|  |  |  | 1 | FEED Overview | - A structured summary of the key features of the FEED, - notably the project specifications, and specific deliverables required by regulators, - which collectively forms the technical and statutory basis for the project’s Financial Close, and the subsequent EPC processes implementation |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  |  | 2 | Basis of Design | - Summary Technical Specifications for the EPC |
|  |  |  | 3 | Pipeline Design & Operating Philosophy | - Operating Envelope / Boundary Conditions - Excursions |
|  |  |  | 4 | Topography | - Plan & Profile of the Pipelines - GIS Spatial Grid of the Pipeline System - Regional Topography along Pipelines Routes - Pipelines Crossings |
|  |  |  | 5 | Process Systems Engineering | - Process Systems Description & Schematics, PFDs and P&IDs, as well as Specifications - Pipeline Hydraulics and Flow Assurance Analysis - Slug Volumes - Process Control & Safeguarding Philosophy - Design & Operating Philosophy - Pipeline Blow-down and Depressurization Plan - Hazop |
|  |  |  | 6 | Materials Specification & Corrosion Management | - Materials Selection & Corrosion Analysis - Corrosion Protection, and Control Philosophy - Corrosion Inhibitor Specification - CP and Coating Specifications - Manufacturing Inspection Plan for Fabrication of Line Pipes / Coating, as well as Pipeline Fittings / Accessories |
|  |  |  | 7 | Pipeline Engineering | - Pipeline Route Drawings / Location Maps - Pipeline End Manifolds - Pipeline Alignment Sheets - Schedule of Crossings & Details - Pipeline Wall Thickness Calculations - Buoyancy Calculations & On Bottom Stability Analysis - Pipeline Equipment Specifications – Manifold, Pig Launchers & Receiver, Slug Catcher - Pipeline Construction Specifications - Pipelines Crossing & Proximity Agreements - Pipeline Pre-Commissioning Specifications, including Cleaning, Gauging, and Hydrotest - Pipeline Integrity Management Philosophy - Requisitions – Technical Specifications for Long Lead Items, Pipeline Fittings, and Manual Valves |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  |  | 8 | Mechanical & Piping Engineering | - Station Locations Plot Plans - Pipeline End Manifolds {PLEM) - Major / Specialty Equipment Specifications & Datasheets - Pig Launcher / Receiver Specifications & Datasheets - Piping Layout Drawings - Tie-in Drawings - Piping Specifications - Pipe Supports - Piping Stress Analysis |
|  |  |  | 9 | Civil / Foundations Engineering – Manifold Foundations | - Manifold Foundations Design - Foundations Drawings & Calculation Notes - MTO – Civil & Structural |
|  |  |  | 10 | Electrical Engineering | - Analysis of Manifold Power Options - Load / Electrical Equipment List - Electrical Single Line Diagram - Power & Lighting Layout - Earthing Layout Drawing - Schematics of Power Panels - Datasheets for Electrical Equipment - Electrical MTO - Cable Sizing - Pipeline CP Design Calculations - Specification for Cathodic Protection |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  |  | 11 | Automation / Control / Instrumentation Engineering | - Integrated Control & Safety (ICS) Philosophy - ICS Architecture - Control System Block Diagram - Instrument Loop Diagrams - Instrument Hook-up Details - Remote Telemetry Unit - Instrumentation Specifications - Telecommunication Specifications - Specification for Fail-Safe Electrical Actuator - Instrument List / Datasheets - I/O List - Specifications of DCS / ESD Equipment, and Block Diagram - Cause & Effect Diagram - Emergency Shutdown System Block Diagram - Fire & Gas Alarm and Detection System Specifications / Block Diagram - Metering Station Specification and Control Unit Configuration - Instrument Location Layout - Control Valves / Systems Specification - Instrument Cable Route Drawings |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  |  | 12 | Slug Catcher Specifications & Design | - Business Need for the Slug Catcher - Type Selection & Justification for the Selection - Hydraulic Design - Materials Selection - Safeguarding Systems - Specialty Equipment List - Instrument List & Datasheets - Mechanical Design Specifications, - Welding & Testing, Painting & Coating, Hydrotest - Civil Engineering Specifications, - Foundation Design, Supports & Anchors - Design Drawings: - - PFD / P&ID - Piping GA & Layout Details - 3D Model - Civil / Structural / Foundation Drawings - Tie-in Schedule – Pig Receiver Outlet & Gas Plant Intake - Requisitions, - Long Lead Items, & Civil / Structural MTO |
|  |  |  | 13 | Technical HSE | - Project Hazard & Risk Register / Risk Assessment Matrix - Process Safety Systems Engineering - HAZOP - Environmental Management Plan (EMP} - Hazardous Area Classificaion - Safety Equipment & Escape Route |
|  |  | 38 | EPC Support |  |  |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  |  | 14 | Preparation of Probabilistic Schedule & Risk Register | Developed Risk Register / Schedule: - Prepared Pipeline Risk Register for probabilistic schedule - Developed the Probabilistic Pipeline Construction Schedule |
|  |  |  | 15 | Cost Estimation for the EPC Phase |  |
|  |  |  | 16 | EPC Package Preparation | Consisting of: - FEED Overview document, - summarizing key elements of the FEED - Link to complete FEED Dossier |
|  |  |  | 17 | Pre-Commissioning Requirement / Planning | Consolidated the deterministic BFPCL and developed the probabilistic schedule: - Consolidated the schedule, - the Pipeline, the Gas Plant, and the Methanol Plant - Developed the probabilistic schedules - Aligned facilities commissioning dates with SPDC gas onstream dates / GSPA |
|  |  |  | 18 | Schedule Alignment | Consolidated the deterministic BFPCL and developed the probabilistic schedule: - Consolidated the schedule, - the Pipeline, the Gas Plant, and the Methanol Plant - Developed the probabilistic schedules - Aligned facilities commissioning dates with SPDC gas onstream dates / GSPA |
|  |  | 39 | The Long Lead Preparatory Works |  | Key Preparatory Works include: - OPL Application - Land Acquisition for the ROW - Sustainable Development Works |
|  | Period/Item | s/n | Description of Works |  | Key Elements & Features / Deliverables |
|  |  |  | 19 | OPL Application | - Application submitted for the OPL, which NMDPRA is progressing for approval - Prepared materials for the OPL Public Hearing - Public Hearing fixed for Dec 2024 was postponement; and the materials will be updated when the time comes |
|  |  |  | 20 | ROW Land Acquisition | - Prepared Framework Development for ROW Land Acquisition, which BFPCL Management has approved for implementation - Held Pipeline Communities’ Engagement Session - Waiting to do the acquisition when the project re-starts |
|  |  |  | 21 | Sustainable Development Works |  |
|  |  |  | 22 | ITT Package Preparations (Scope of Work) | Consisting of: - Scope of Work - Schedule / Quality / HSE Specifications - General & Special Conditions - Proforma Contract |
|  |  |  | 23 | Preparatory Works for long lead Items | Consisting of: - MTO - Material Specifications & Datasheets - Manufacturing Methods / Specifications - Delivery Terms (Incoterms) |