## Produced Water Treatment Option
S/N | Disposal Options | Key Facilities | CAPEX | OPEX | Year of Operation | Extendaties
1 | Offshore disposal | Offshore pipeline (22km) | $30m | $1.2m | 20 | Long-term, high-volume offshore fields.
|  | Water treatment plant | $100m | $10m |  | Lowest long-term Opex; high operational uptime.
2 | Offshore disposal through shuttle Tanks | Bulk tank | $45m | $5m | 7 | Remote fields with no pipeline access
|  | Shuttle Tanker | $15m | $3m |  | Avoids subsea construction; flexible volume handling
|  | Mooring system | $70m | $12m
3 | Treatment for industral use | Water treatment plant | $25m | $5m | 20 | Water-scarce areas with high utility costs.
|  | storage tanks | $20m | $2m |  | Exceptional ESG profile; reduces freshwater abstraction.
|  | reticulation system | $20m | $3m
|  | Brime management | $55m | $7m
4 | Transportation to BRASS facilities | Buffer tanks | $20m | $5m | 20 | Proximity to a major hub like Brass.
|  | Multiphase pumps | $12m | $3m |  | Shared infrastructure costs; smaller on-site footprint.
|  | Pig launching station/ Pig receiving station | $22m | $7m
|  | Pipeline to terminal(18km) | $15m | $1m
|  | Leak Detection system | $28m | $2m
5 | Transfer to third party | Bulk storage | $15m | $3m | 10 | Low-volume or short-term operations.
|  | Collection sump | $5m | $1m
|  | high-flow station | $10m | $2m
Dr joe's Options:
6 | Floating Hub | Barge-based Modular Flotatio | $15m | $2m | 2 | Discharges into deep-water; modular
|  | Ceramic Membranes | $25m | $2.5m
7 | Subsea Polishing | Subsea Hydrocyclones | $35m | $0.6m | 5 | Invisible infrastructure; zero energy consumption.
|  | Passive Separator at outfall | $15m | $0.2m

## Development Costs
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
CAPEX SUMMARIES of the Potential Concepts
|  |  |  | Facilities CAPEX | Projected Well Cost | Total CAPEX |  | Scope
Concept A | Retain Status Quo - SPDC Opuama & Gbetiokun/Bime FDPs
| Scenario-1 Use of the Existing Opuama D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014, exporting crude thru Otumara M/F, and Gas to NGC at Sapele | 190.2835 | 102.9 | 293.1835 |  | Opuama Multiphase Booster Station + Gbetiokun F/S, & D/L to Otumara M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Otumara M/F, and AG to NGC Plant at Sapele
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014, exporting crude thru Otumar M/F, and Gas to NCG at Sapele | 232.0285 | 102.9 | 334.9285 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara Node + Gbetiokun F/S, & D/L to Otumara M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Otumara M/F, and AG to NGC Plant at Sapele
Concept A1 | Gbetiokun Greenfield Evacuated via Sapele
|  |  | Straight Full OML Development on stream 2014, exporting Opuama thru Otumara, and Gbetiokun thru Sapele | 225.6925 | 102.9 | 328.5925 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara Node + Gbetiokun F/S, & D/L to Sapele M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Sapele M/F, and AG to NGC Plant at Sapele
Concept A2 | Gbetiokun Greenfield Evacuated via Jones Creek
|  |  | Straight Full OML Development on stream 2014, exporting Opuama thru Otumara, and Gbetiokun thru Jones Creek | 215.1325 | 102.9 | 318.0325 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara Node + Gbetiokun F/S, & D/L to Jones Creek M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Jones Creek M/F, and AG to NGC Plant at Jones Creek
Concept A3 | Gas to Power
|  |  | Straight Full OML Development on stream 2014, exporting each field's Processed Crude thru Otumara M/F, and Gas to Power in-field | 222.7885 | 102.9 | 325.6885 |  | Opuama F/S Extension withh AG Facility + Gbetiokun F/S, & D/L to Otumara M/F. Each Field's processed crude to Otumara M/F. Power Generation System in each Field for in-field Gas to Power
Concept B | Opuama CPF (Oil via Otumara)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Opuama, and Exporting via Otumara | 162.0685 | 102.9 | 264.9685 |  | Opuama F/S Extension with AG Facility + Gbetiokun Multiphase Booster Station & Muliphase Line to Opuama. Processed crude to Otumara M/F, and AG to Otumara Gas Node
Concept B1 | Opuama CPF (Gas to Power)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Opuama, and Exporting via Otumara, and Gas to Power in-field | 187.5445 | 102.9 | 290.4445 |  | Opuama F/S Extension with AG Facility + Gbetiokun Multiphase Booster Station & Muliphase Line to Opuama. Processed crude to Otumara M/F, and Gas to Power in-field at Opuama
Concept C | Gbetiokun CPF (Oil via Escravos)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Gbetiokun, Exporting Oil via Escravos & AG via Sapele | 248.1325 | 102.9 | 351.0325 |  | Opuama Multiphase Booster Station & Multiphase Line to Gbetiokun + Gbetiokun F/S, with Oil D/L to Escravos & GasLine to Sapele. Processed crude to Escravos, and AG to NGC Plant at Sapele
Concept C1 | Gbetiokun CPF (Gas to Power)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Gbetiokun, Exporting Oil via Escravos, and Gas to Power in-field | 266.1125 | 102.9 | 369.0125 |  | Opuama Multiphase Booster Station & Multiphase Line to Gbetiokun + Gbetiokun F/S, with Oil D/L to Escravos & GasLine to Sapele. Processed crude to Escravos, and Gas to Power in-field at Gbetiokun
Concept D | Multiphase Solutions
| Scenario-1 Use of the Existing Opuama D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014, exporting multiphase flow thru Otumara Node & Jones Creek F/S | 78.5675 | 102.9 | 181.4675 |  | Opuama Multiphase Booster Station + Gbetiokun Multiphase Booster Station & Multiphase Line to Jones Creek F/S. Opuama Muliphase to Otuma Node, Gbetiokun Multiphase to Jones Creek F/S
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014, exporting multiphase streams thru Otumara Node & Jones Creesk F/S | 120.3125 | 102.9 | 223.2125 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara + Gbetiokun Multiphase Booster Station & Multiphase Line to Jones Creek F/S. Opuama Muliphase to Otuma Node, Gbetiokun Multiphase to Jones Creek F/S
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept A |  |  | Retain Status Quo - SPDC Opuama & Gbetiokun/Bime FDPs
| Scenario-1 Use the Existing Opuama D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014, exporting crude thru Otumara M/F, and Gas to NGC at Sapele | Opua MPB Station + Gbetiokun F/S exporting thru Otumara M/F
CHA with SPDC
|  |  |  | On Stream Date | 2012 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  | 2.6 | 2.1 | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  | 1 | 0.9 | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal (Opuama & Gbetiokun/Bime) | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 4 | 8 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 5.5 | 0 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 5.5 | 97.4 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities / Modifications for Early Production from Opuama
|  |  | Integrity Assessment & Revamp | F/S, D/L + M/F |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | F/S Modification Works | Route 1st Stage Sep Outlet to D/L |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | Mod at Otumara M/F of Adagbassa to Otum T/L | Modify at Otum M/F to Route Flow to Otum F/S |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | Multiphase Booster Pump | 5 Mbpd MPB Pump on existing Pump Bay |  | prem | 2 | 1 |  | 2 |  | 2
|  |  | Multiphase Meter at Otumara |  |  | guess | 0.25 | 1 |  | 0.25 |  | 0.25
Facilities for Full Field Dev - Opuama & Gbetiokun
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | Multiphase Line: Opuama - Otumara F/S | Existing Opuama - Otumara D/L to be used |  | prem |  |  | inch-km | 0 |  | 0 | 0 | 0
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 36km D/L to Otumara M/F |  | prem | 0.12 | 288 | inch-km | 34.56 |  | 3.456 | 17.28 | 13.824
|  |  | Gas Export Line | 12" x 30km Gas Export Line to NGC at Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 17.2985 |  | 1.7299 | 8.6493 | 6.9194
|  |  |  | Facilities Engineering Scope | [5 empty] | 190.2835 |  | 24.0808 | 92.8792 | 66.8234 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-1 |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 5.5 | 97.4 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 2.125 | 9.35 | 0 | 0 | 0
|  |  | Opuama Mod for Early Prod | MPB Pump + F/S & D/L Revamp & Mod | [5 empty] | 5.25 |  | 5.25 | 0 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 7 |  | 0.7 | 3.5 | 2.8 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Otumara | [5 empty] | 99.56 |  | 9.956 | 49.78 | 39.824 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 17.2985 |  | 1.7299 | 8.6493 | 6.9194 | 0 | 0
|  |  |  | Totals | [5 empty] | 293.1835 |  | 29.5808 | 196.7792 | 66.8234 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept A |  |  | Retain Status Quo - SPDC Opuama & Gbetiokun/Bime FDPs
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014, exporting crude thru Otumar M/F, and Gas to NCG at Sapele | Opua MPB Station + Gbetiokun F/S exporting thru Otumara M/F
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities / Modifications for Early Production from Opuama
|  |  | Integrity Assessment & Revamp | F/S, D/L + M/F |  | guess | 1 |  |  | 0 |  | 0
|  |  | F/S Modification Works | Route 1st Stage Sep Outlet to D/L |  | guess | 1 |  |  | 0 |  | 0
|  |  | Mod at Otumara M/F of Adagbassa to Otum T/L | Modify at Otum M/F to Route Flow to Otum F/S |  | guess | 1 |  |  | 0 |  | 0
|  |  | Multiphase Booster Pump | 5 Mbpd MPB Pump on existing Pump Bay |  | prem | 2 |  |  | 0 |  | 0
|  |  | Multiphase Meter at Otumara |  |  | guess | 0.25 |  |  | 0 |  | 0
Facilities for Full Field Dev - Opuama & Gbetiokun
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km New Multiphase Line to Otum F/S |  | prem | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 36km D/L to Otumara M/F |  | prem | 0.12 | 288 | inch-km | 34.56 |  | 3.456 | 17.28 | 13.824
|  |  | Gas Export Line | 12" x 30km Gas Export Line to Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 21.0935 |  | 2.1094 | 10.5468 | 8.4374
|  |  |  | Facilities Engineering Scope | [5 empty] | 232.0285 |  | 21.4053 | 118.5017 | 85.6214 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-2 |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama Mod for Early Prod | MPB Pump + F/S & D/L Revamp & Mod | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | Opua MPB Station + Multiphase Line | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Otumara | [5 empty] | 99.56 |  | 9.956 | 49.78 | 39.824 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 21.0935 |  | 2.1094 | 10.5468 | 8.4374 | 0 | 0
|  |  |  | Totals | [5 empty] | 334.9285 |  | 21.4053 | 227.9017 | 85.6214 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept A1 |  |  | Gbetiokun Greenfield Evacuated via Sapele
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Sapele M/F | Opua MPB Station + Gbetiokun F/S exporting thru Sapele M/F
CHA with SPDC, and SEPLAT
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km Multiphase Line to Otumara F/S |  | prem | 0.12 | 360 |  | 43.2 |  | 4.32 | 21.6 | 17.28
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 30km D/L to Sapele M/F |  | prem | 0.12 | 240 | inch-km | 28.8 |  | 2.88 | 14.4 | 11.52
|  |  | Gas Export Line | 12" x 30km Gas Export Line to Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.5175 |  | 2.0518 | 10.2588 | 8.207
|  |  |  | Facilities Engineering Scope | [5 empty] | 225.6925 |  | 20.7717 | 115.3337 | 83.087 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A1 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Sapele M/F |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2168.8 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Sapele | [5 empty] | 93.8 |  | 9.38 | 46.9 | 37.52 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.5175 |  | 2.0518 | 10.2588 | 8.207 | 0 | 0
|  |  |  | Totals | [5 empty] | 328.5925 |  | 2032.7718 | 2387.0338 | 2097.087 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept A2 |  |  | Gbetiokun Greenfield Evacuated via Jones Creek
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Jones Creek M/F | Opua MPB Station + Gbetiokun F/S exporting thru Jones Creek M/F
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km Multiphase Line to Otumara F/S |  | prem | 0.12 | 360 |  | 43.2 |  | 4.32 | 21.6 | 17.28
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 26km D/L to Jones Creek M/F |  | prem | 0.12 | 208 | inch-km | 24.96 |  | 2.496 | 12.48 | 9.984
|  |  | Gas Export Line | 12" x 26km Gas Export Line to Jones Creek |  |  | 0.12 | 312 | inch-km | 37.44 |  | 3.744 | 18.72 | 14.976
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 19.5575 |  | 1.9558 | 9.7788 | 7.823
|  |  |  | Facilities Engineering Scope | [5 empty] | 215.1325 |  | 19.7157 | 110.0537 | 78.863 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A2 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Jones Creek M/F |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2168.8 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Sapele | [5 empty] | 89.96 |  | 8.996 | 44.98 | 35.984 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 37.44 |  | 3.744 | 18.72 | 14.976 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 19.5575 |  | 1.9558 | 9.7788 | 7.823 | 0 | 0
|  |  |  | Totals | [5 empty] | 318.0325 |  | 2031.7158 | 2381.7537 | 2092.863 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept A3 |  |  | Gas to Power
|  |  | Straight Full OML Development on stream 2014 | Opuama F/S + Gbetiokun F/S
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama F/S Revamp + AG Facilities
|  |  | Revamp Opuama F/S & D/L | 30 MBD F/S + 8" x 2.5 km D/L |  | guess |  |  |  | 5 |  | 0.5 | 2.5 | 2
|  |  | AGG Facilitity (Compression + Gas Conditioning) | 5 - 10 MMscfd Package |  | prem/benchmark |  |  |  | 15 |  | 1.5 | 7.5 | 6
|  |  | Power Plant | 18 MW + Feeder to National Grid |  | prem | 1.25 | 18 | MW | 22.5 |  | 2.25 | 11.25 | 9
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 36km D/L to Otumara M/F |  | prem | 0.12 | 288 | inch-km | 34.56 |  | 3.456 | 17.28 | 13.824
|  |  |  | Provision for Gas Processing | [5 empty] | 5 |  | 0.5 | 2.5 | 2
|  |  | Power Plant | 18 MW + Feeder to National Grid |  |  | 1.25 | 30 | MW | 37.5 |  | 3.75 | 18.75 | 15
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.2535 |  | 2.0254 | 10.1268 | 8.1014
|  |  |  | Facilities Engineering Scope | [5 empty] | 222.7885 |  | 20.4813 | 113.8817 | 81.9254 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A3 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2115.9 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama F/S Revamp + AG Facilities | 30 MBDD F/S + 8" x 2.5 km D/L + 10 MMscfd AG Facs | [5 empty] | 20 |  | 2 | 10 | 8 | 0 | 0
|  |  | Opuama Power Plant | 18 MW + Feeder to Grid | [5 empty] | 22.5 |  | 9.956 | 49.78 | 39.824 | 0 | 0
|  |  | Gbetiokun F/S & D/L | 30 MBD + AGG Fac | [5 empty] | 104.56 |  | 4.25 | 21.25 | 17 | 0 | 0
|  |  | Gbetiokun Power Plant | 30 MW | [5 empty] | 37.5 |  | 5.7754 | 28.8768 | 23.1014 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.2535 |  | 2.0254 | 10.1268 | 8.1014 | 0 | 0
|  |  |  | Totals | [5 empty] | 325.6885 |  | 2036.0067 | 2350.3085 | 2110.0268 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept B |  |  | Opuama Central Processing facility via Otumara (30 MBD Opuama F/S)
|  |  | Straight Full OML Development on stream 2014 | Opua F/S + Gbetiokun MPB Station
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama F/S Revamp + AG Facilities
|  |  | Revamp Opuama F/S & D/L | 30 MBD F/S + 8" x 2.5 km D/L |  | guess |  |  |  | 5 |  | 0.5 | 2.5 | 2
|  |  | AGG Facilitity (Compression + Gas Conditioning) | 10 - 15 MMscfd Package |  | prem/benchmark |  |  |  | 15 |  | 1.5 | 7.5 | 6
|  |  | Gas Export Line | 12" x 36km Gas Export Line to Otumara |  |  | 0.12 | 432 | inch-km | 51.84 |  | 5.184 | 25.92 | 20.736
Gbetiokun MPB
|  |  | Gbetiokun MPB Station | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Opuama F/S | 12" x 33km Multiphase Line to Opuama F/S |  | prem | 0.12 | 396 |  | 47.52 |  | 4.752 | 23.76 | 19.008
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 14.7335 |  | 1.4733 | 7.3667 | 5.8934
|  |  |  | Facilities Engineering Scope | [5 empty] | 162.0685 |  | 14.4093 | 83.5217 | 57.6374 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept B |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 195.3 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama F/S Revamp + AG Facilities | 30 MBDD F/S + 8" x 2.5 km D/L + 10 MMscfd AG Facs | [5 empty] | 20 |  | 2 | 10 | 8 | 0 | 0
|  |  | Opuama Gas Export Line to Otumara | Opuama gas export Line | [5 empty] | 51.84 |  | 1 | 5 | 4 | 0 | 0
|  |  | Gbetiokun MPB | 2 x 10 Mbpd MPB Pumps | [5 empty] | 10 |  | 4.752 | 23.76 | 19.008 | 0 | 0
|  |  | Gbetiokun MPB | 12" x 33km Multiphase Line to Opuama F/S | [5 empty] | 47.52 |  | 1.4733 | 7.3667 | 5.8934 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 14.7335 |  | 1.4733 | 7.3667 | 5.8934 | 0 | 0
|  |  |  | Totals | [5 empty] | 264.9685 |  | 10.6987 | 363.1685 | 42.7948 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept B1 |  |  | Opuama F/S (Central Processing facility) via Otumara, with Power Generation
|  |  | Straight Full OML Development on stream 2015 | Opua F/S + Gbetiokun MPB Station
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama F/S Revamp + AG Facilities
|  |  | Revamp Opuama F/S & D/L | 30 MBD F/S + 8" x 2.5 km D/L |  | guess |  |  |  | 5 |  | 0.5 | 2.5 | 2
|  |  | AGG Facilitity (Compression + Gas Conditioning) | 10 - 15 MMscfd Package |  | benchmark |  |  |  | 30 |  | 3 | 15 | 12
|  |  | Power Plant | 48 MW + Feeder to National Grid |  | prem | 1.25 | 48 | MW | 60 |  | 6 | 30 | 24
Gbetiokun MPB
|  |  | MPB Station - Gbetiokun | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Opuama F/S | 12" x 33km Multiphase Line to Opuama F/S |  | prem | 0.12 | 396 |  | 47.52 |  | 4.752 | 23.76 | 19.008
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 17.0495 |  | 1.705 | 8.5248 | 6.8198
|  |  |  | Facilities Engineering Scope | [5 empty] | 187.5445 |  | 16.9569 | 96.2597 | 67.8278 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept B1 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 195.3 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama F/S Revamp + AG Facilities | 30 MBDD F/S + 8" x 2.5 km D/L + 10 MMscfd AG Facs | [5 empty] | 35 |  | 3.5 | 17.5 | 14 | 0 | 0
|  |  | Opuama Power Plant | 48 MW + Feeder to National Grid | [5 empty] | 60 |  | 1 | 5 | 4 | 0 | 0
|  |  | Gbetiokun MPB | 25 - 30 MBP Multiphase Pumping Station | [5 empty] | 10 |  | 4.752 | 23.76 | 19.008 | 0 | 0
|  |  | Gbetiokun MPB | 12" x 33km Multiphase Line to Opuama F/S | [5 empty] | 47.52 |  | 1.705 | 8.5248 | 6.8198 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 17.0495 |  | 1.705 | 8.5248 | 6.8198 | 0 | 0
|  |  |  | Totals | [5 empty] | 290.4445 |  | 12.6619 | 372.9845 | 50.6476 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept C |  |  | Gbetiokun Central Processing facility via Escravos
|  |  | Straight Full OML Development on stream 2014 | Opua MPB Station + Gbetiokun F/S
CHA with SPDC and CNL
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama MPB to Gbetiokun
Facilities Multiphase Boosting from Opuama - Gbetiokun F/S
|  |  | MPB Station - Opuama | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Otumara F/S |  | prem | 0.12 | 330 |  | 39.6 |  | 3.96 | 19.8 | 15.84
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 10" x 44km D/L to Escravos |  | prem | 0.12 | 440 | inch-km | 52.8 |  | 5.28 | 26.4 | 21.12
|  |  | Gas Export Line | 12" x 30km Gas Export Line to Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 22.5575 |  | 2.2558 | 11.2788 | 9.023
|  |  |  | Facilities Engineering Scope | [5 empty] | 248.1325 |  | 23.0158 | 126.5538 | 92.063 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept C |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2115.9 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Gbetiokun | [5 empty] | 7 |  | 4.66 | 23.3 | 18.64 | 0 | 0
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Otumara F/S | [5 empty] | 39.6 |  | 3.96 | 19.8 | 15.84 | 0 | 0
|  |  | Gbetiokun F/S + D/L to Escravos | 10" x 44km D/L to Escravos | [5 empty] | 117.8 |  | 11.78 | 58.9 | 47.12 | 0 | 0
|  |  | Getiokun Gas Export line | 12" x 30km Gas Export Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 22.5575 |  | 2.2558 | 11.2788 | 9.023 | 0 | 0
|  |  |  | Totals | [5 empty] | 351.0325 |  | 2038.9758 | 2365.1538 | 2121.903 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept C1 |  |  | Gbetiokun Central Processing facility via Escravos, with Power Generation
|  |  | Straight Full OML Development on stream 2014 | Opua MBS + Gbetiokun F/S with Crude to CNL Terminal at Escravos
CHA with SPDC and CNL
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Gbetiokun F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Gbetiokun F/S |  | prem | 0.12 | 330 |  | 39.6 |  | 3.96 | 19.8 | 15.84
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 10" x 44km D/L to Escravos |  | prem | 0.12 | 440 | inch-km | 52.8 |  | 5.28 | 26.4 | 21.12
|  |  |  | Provision for Gas Processing | [5 empty] | 5 |  | 0.5 | 2.5 | 2
|  |  | Power Plant | 48 MW + Feeder to National Grid |  | prem | 1.25 | 48 | MW | 60 |  | 6 | 30 | 24
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 18.7375 |  | 1.8738 | 9.3688 | 7.495
|  |  |  | Facilities Engineering Scope | [5 empty] | 266.1125 |  | 24.8138 | 135.5438 | 99.255 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept C1 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2168.8 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama MPB Station | [6 empty] | 7 |  | 0.7 | 3.5 | 2.8 | 0 | 0
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Otumara F/S | [5 empty] | 39.6 |  | 3.96 | 19.8 | 15.84 | 0 | 0
|  |  | Gbetiokun F/S + AGG Facs | [6 empty] | 65 |  | 6.5 | 32.5 | 26 | 0 | 0 | 0
|  |  | Gbet D/L | 10" x 44km D/L to Escravos | [5 empty] | 52.8 |  | 5.28 | 26.4 | 21.12 | 0 | 0
|  |  | Provision for Gas Conditioning | [6 empty] | 5 |  | 0.5 | 2.5 | 2 | 0 | 0
|  |  | Power Plant | 48 MW + Feeder to National Grid | [5 empty] | 60 |  | 1.8738 | 9.3688 | 7.495 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 18.7375 |  | 1.8738 | 9.3688 | 7.495 | 0 | 0
|  |  |  | Totals | [5 empty] | 369.0125 |  | 2032.6875 | 2386.6125 | 2096.75 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept D |  |  | Multiphase Solutions
| Scenario-1 Use the Existing D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014 | Opua MPB + Gbetiokun MPB Stations
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  | 2.6 | 2.1 | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  | 1 | 0.9 | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 4 | 8 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 5.5 | 0 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 5.5 | 97.4 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities / Modifications for Early Production from Opuama
|  |  | Integrity Assessment & Revamp | F/S, D/L + M/F |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | F/S Modification Works | Route 1st Stage Sep Outlet to D/L |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | Mod at Otumara M/F of Adagbassa to Otum T/L | Modify at Otum M/F to Route Flow to Otum F/S |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | Multiphase Booster Pump | 5 Mbpd MPB Pump on existing Pump Bay |  | prem | 2 | 1 |  | 2 |  | 2
|  |  | Multiphase Meter at Otumara |  |  | guess | 0.25 | 1 |  | 0.25 |  | 0.25
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | Existing Opuama - Otumara D/L to be used |  | prem | 0.12 |  |  | 0 |  | 0 | 0 | 0
Facilities for Full Field Dev - Gbetiokun
|  |  | MPB Station - Gbetiokun | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Jones Creek F/S | 10" x 26km Multiphase Line to Jones Creek F/S |  | prem | 0.12 | 260 |  | 31.2 |  | 3.12 | 15.6 | 12.48
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 7.1425 |  | 0.71425 | 3.5713 | 2.857
|  |  |  | Facilities Engineering Scope | [5 empty] | 78.5675 |  | 12.9093 | 37.0213 | 22.137 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept D |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-1 |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 5.5 | 97.4 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 2.125 | 9.35 | 0 | 0 | 0
|  |  | Opuama Mod for Early Prod | MPB Pump + F/S & D/L Revamp & Mod | [5 empty] | 5.25 |  | 5.25 | 0 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station | [5 empty] | 7 |  | 0.7 | 3.5 | 2.8 | 0 | 0
|  |  | Gbetiokun MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Jones Creek | [5 empty] | 41.2 |  | 4.12 | 20.6 | 16.48 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 7.1425 |  | 0.71425 | 3.5713 | 2.857 | 0 | 0
|  |  |  | Totals | [5 empty] | 181.4675 |  | 18.4093 | 140.9212 | 22.137 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OML 40 Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2011
Concept D |  |  | Multiphase Solutions
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014 | Opua MPB + Gbetiokun MPB Stations
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | MPB Station - Opuama | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km Multiphase Line to Otumara F/S |  | prem | 0.12 | 360 |  | 43.2 |  | 4.32 | 21.6 | 17.28
Facilities for Full Field Dev - Opuama & Gbetiokun
|  |  | MPB Station - Gbetiokun | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Jones Creek F/S | 10" x 26km Multiphase Line to Jones Creek F/S |  | prem | 0.12 | 260 |  | 31.2 |  | 3.12 | 15.6 | 12.48
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 10.9375 |  | 1.0938 | 5.4688 | 4.375
|  |  |  | Facilities Engineering Scope | [5 empty] | 120.3125 |  | 10.2338 | 62.6437 | 40.935 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept D |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-2 |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Jones Creek | [5 empty] | 41.2 |  | 4.12 | 20.6 | 16.48 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 10.9375 |  | 1.0938 | 5.4688 | 4.375 | 0 | 0
|  |  |  | Totals | [5 empty] | 223.2125 |  | 10.2338 | 172.0437 | 40.935 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## Options for The 1 BSCFD
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
CAPEX SUMMARIES of the Potential Concepts
|  |  |  | Facilities CAPEX | Projected Well Cost | Total CAPEX |  | Scope
Concept A | 36" P/L from ELEP to AKAB
| Scenario-1 Use of the Existing Opuama D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014, exporting crude thru Otumara M/F, and Gas to NGC at Sapele | 186.9835 | 350 | 536.9835 |  | Opuama Multiphase Booster Station + Gbetiokun F/S, & D/L to Otumara M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Otumara M/F, and AG to NGC Plant at Sapele
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014, exporting crude thru Otumar M/F, and Gas to NCG at Sapele | 232.0285 | 102.9 | 334.9285 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara Node + Gbetiokun F/S, & D/L to Otumara M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Otumara M/F, and AG to NGC Plant at Sapele
Concept A1 | Gbetiokun Greenfield Evacuated via Sapele
|  |  | Straight Full OML Development on stream 2014, exporting Opuama thru Otumara, and Gbetiokun thru Sapele | 225.6925 | 102.9 | 328.5925 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara Node + Gbetiokun F/S, & D/L to Sapele M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Sapele M/F, and AG to NGC Plant at Sapele
Concept A2 | Gbetiokun Greenfield Evacuated via Jones Creek
|  |  | Straight Full OML Development on stream 2014, exporting Opuama thru Otumara, and Gbetiokun thru Jones Creek | 215.1325 | 102.9 | 318.0325 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara Node + Gbetiokun F/S, & D/L to Jones Creek M/F. Opuama Multiphase Flow to Otumara Node. Gbetiokun Processed Crude to Jones Creek M/F, and AG to NGC Plant at Jones Creek
Concept A3 | Gas to Power
|  |  | Straight Full OML Development on stream 2014, exporting each field's Processed Crude thru Otumara M/F, and Gas to Power in-field | 222.7885 | 102.9 | 325.6885 |  | Opuama F/S Extension withh AG Facility + Gbetiokun F/S, & D/L to Otumara M/F. Each Field's processed crude to Otumara M/F. Power Generation System in each Field for in-field Gas to Power
Concept B | Opuama CPF (Oil via Otumara)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Opuama, and Exporting via Otumara | 162.0685 | 102.9 | 264.9685 |  | Opuama F/S Extension with AG Facility + Gbetiokun Multiphase Booster Station & Muliphase Line to Opuama. Processed crude to Otumara M/F, and AG to Otumara Gas Node
Concept B1 | Opuama CPF (Gas to Power)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Opuama, and Exporting via Otumara, and Gas to Power in-field | 187.5445 | 102.9 | 290.4445 |  | Opuama F/S Extension with AG Facility + Gbetiokun Multiphase Booster Station & Muliphase Line to Opuama. Processed crude to Otumara M/F, and Gas to Power in-field at Opuama
Concept C | Gbetiokun CPF (Oil via Escravos)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Gbetiokun, Exporting Oil via Escravos & AG via Sapele | 248.1325 | 102.9 | 351.0325 |  | Opuama Multiphase Booster Station & Multiphase Line to Gbetiokun + Gbetiokun F/S, with Oil D/L to Escravos & GasLine to Sapele. Processed crude to Escravos, and AG to NGC Plant at Sapele
Concept C1 | Gbetiokun CPF (Gas to Power)
|  |  | Straight Full OML Development on stream 2014, with a Central F/S in Gbetiokun, Exporting Oil via Escravos, and Gas to Power in-field | 266.1125 | 102.9 | 369.0125 |  | Opuama Multiphase Booster Station & Multiphase Line to Gbetiokun + Gbetiokun F/S, with Oil D/L to Escravos & GasLine to Sapele. Processed crude to Escravos, and Gas to Power in-field at Gbetiokun
Concept D | Multiphase Solutions
| Scenario-1 Use of the Existing Opuama D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014, exporting multiphase flow thru Otumara Node & Jones Creek F/S | 78.5675 | 102.9 | 181.4675 |  | Opuama Multiphase Booster Station + Gbetiokun Multiphase Booster Station & Multiphase Line to Jones Creek F/S. Opuama Muliphase to Otuma Node, Gbetiokun Multiphase to Jones Creek F/S
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014, exporting multiphase streams thru Otumara Node & Jones Creesk F/S | 120.3125 | 102.9 | 223.2125 |  | Opuama Multiphase Booster Station & Multiphase Line to Otumara + Gbetiokun Multiphase Booster Station & Multiphase Line to Jones Creek F/S. Opuama Muliphase to Otuma Node, Gbetiokun Multiphase to Jones Creek F/S
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept A |  |  | Gather All Nodes Production to Evacuation Manifold at ELEP
| 36" P/L from ELEP - AKAB |  | BBOU + ELEP on stream 2025 | Subsequent Nodes later, starting with NUNR in 2038 till OPUG in 2050
|  |  |  | On Stream Date | 2025 | [5 empty] | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |  | 2030 | 2031 | 2032 | 2033 | 2034
[5 empty] | NAG Production Forecas |  |  |  |  | MMscfd |  | 1 | 0.9 | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
36.84 | 9.21 |  |  |  | Related Condensate Production Forecast |  |  |  |  | Mbopd |  | 2.6 | 2.1 | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
| 9.58 |  |  |  | Related Water Production Forecast |  |  |  |  | Mbwpd |  | 1 | 0.9 | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
| 0.37 |  | Wells Proposal (BBOU & ELEP & others) | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | BBOU Wells - Drill & Complete | Drill & Complete |  |  |  | 4 |  |  |  | 4
|  | 2 | BBOU Wells - Drill & Complete | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 2 | NUNR Wells - Drill & Complete | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 2 | SEIB Wells - Drill & Complete | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  | 2 | OPUG Wells - Drill & Complete | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | OKPO Wells - Drill & Complete | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 18 |  |  |  | 4 | 14 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs (max envisaged) / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | BBOU Wells - Drill & Complete | Drill & Complete | 25 | mln per | well | 4 | well | 100 |  | 100 | 0 | 0 | 0 | 0
|  | 2 | BBOU Wells - Drill & Complete | Drill & Complete | 25 | mln per | well | 0 | well | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 | NUNR Wells - Drill & Complete | Drill & Complete | 25 | mln per | well | 2 | well | 50 |  | 0 | 50 | 0 | 0 | 0
|  | 2 | SEIB Wells - Drill & Complete | Drill & Complete | 25 | mln per | well | 2 | well | 50 |  | 0 | 50 | 0 | 0 | 0
|  | 3 | OPUG Wells - Drill & Complete | Drill & Complete | 25 | mln per | well | 2 | well | 50 |  | 0 | 50 | 0 | 0 | 0
|  | 4 | OKPO Wells - Drill & Complete | Drill & Complete | 25 | mln per | well | 4 | well | 100 |  | 0 | 100 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 350 |  | 100 | 250 | 0 | 0 | 0
|  |  | Facilities Requirements | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 2 BBOU Wells | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  | premise | 0.25 | 5.7 | km | 1.425 |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  | 0.7
|  |  | Well F/L & Hook-up of 2 ELEP Wells | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
CF-SMF
|  |  | Field Satellite Manifold |  |  | guess | 1 | 1 |  | 1 |  | 1
[6 empty] | guess | 1 | 1 |  | 1 |  | 1
[6 empty] | guess | 0.25 | 1 |  | 0.25 |  | 0.25
Pipelines for Full Field Gathering
|  |  | P/L ELEP - AKAB | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | P/L ELEP | Existing Opuama - Otumara D/L to be used |  | prem |  |  | inch-km | 0 |  | 0 | 0 | 0
|  |  | P/L BBOU | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 36km D/L to Otumara M/F |  | prem | 0.12 | 288 | inch-km | 34.56 |  | 3.456 | 17.28 | 13.824
|  |  |  | 12" x 30km Gas Export Line to NGC at Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  |  | Contingency @ 10% of Total Capex | [5 empty] | 16.9985 |  | 1.6999 | 8.4992 | 6.7994
|  |  |  | Facilities Engineering Scope | [5 empty] | 186.9835 |  | 21.0509 | 92.7293 | 66.7034 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-1 |  | BBOU + ELEP in 2025 followed by Others |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 350 |  | 100 | 250 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 2.125 | 9.35 | 0 | 0 | 0
|  |  | S-MF @ BBOU | MPB Pump + F/S & D/L Revamp & Mod | [5 empty] | 2.25 |  | 2.25 | 0 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 7 |  | 0.7 | 3.5 | 2.8 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Otumara | [5 empty] | 99.56 |  | 9.956 | 49.78 | 39.824 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 16.9985 |  | 1.6999 | 8.4992 | 6.7994 | 0 | 0
|  |  |  | Totals | [5 empty] | 536.9835 |  | 121.0508 | 349.2293 | 66.7034 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept A |  |  | Retain Status Quo - SPDC Opuama & Gbetiokun/Bime FDPs
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014, exporting crude thru Otumar M/F, and Gas to NCG at Sapele | Opua MPB Station + Gbetiokun F/S exporting thru Otumara M/F
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities / Modifications for Early Production from Opuama
|  |  | Integrity Assessment & Revamp | F/S, D/L + M/F |  | guess | 1 |  |  | 0 |  | 0
|  |  | F/S Modification Works | Route 1st Stage Sep Outlet to D/L |  | guess | 1 |  |  | 0 |  | 0
|  |  | Mod at Otumara M/F of Adagbassa to Otum T/L | Modify at Otum M/F to Route Flow to Otum F/S |  | guess | 1 |  |  | 0 |  | 0
|  |  | Multiphase Booster Pump | 5 Mbpd MPB Pump on existing Pump Bay |  | prem | 2 |  |  | 0 |  | 0
|  |  | Multiphase Meter at Otumara |  |  | guess | 0.25 |  |  | 0 |  | 0
Facilities for Full Field Dev - Opuama & Gbetiokun
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km New Multiphase Line to Otum F/S |  | prem | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 36km D/L to Otumara M/F |  | prem | 0.12 | 288 | inch-km | 34.56 |  | 3.456 | 17.28 | 13.824
|  |  | Gas Export Line | 12" x 30km Gas Export Line to Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 21.0935 |  | 2.1094 | 10.5468 | 8.4374
|  |  |  | Facilities Engineering Scope | [5 empty] | 232.0285 |  | 21.4053 | 118.5017 | 85.6214 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-2 |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama Mod for Early Prod | MPB Pump + F/S & D/L Revamp & Mod | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | Opua MPB Station + Multiphase Line | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Otumara | [5 empty] | 99.56 |  | 9.956 | 49.78 | 39.824 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 21.0935 |  | 2.1094 | 10.5468 | 8.4374 | 0 | 0
|  |  |  | Totals | [5 empty] | 334.9285 |  | 21.4053 | 227.9017 | 85.6214 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept A1 |  |  | Gbetiokun Greenfield Evacuated via Sapele
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Sapele M/F | Opua MPB Station + Gbetiokun F/S exporting thru Sapele M/F
CHA with SPDC, and SEPLAT
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km Multiphase Line to Otumara F/S |  | prem | 0.12 | 360 |  | 43.2 |  | 4.32 | 21.6 | 17.28
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 30km D/L to Sapele M/F |  | prem | 0.12 | 240 | inch-km | 28.8 |  | 2.88 | 14.4 | 11.52
|  |  | Gas Export Line | 12" x 30km Gas Export Line to Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.5175 |  | 2.0518 | 10.2588 | 8.207
|  |  |  | Facilities Engineering Scope | [5 empty] | 225.6925 |  | 20.7717 | 115.3337 | 83.087 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A1 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Sapele M/F |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2168.8 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Sapele | [5 empty] | 93.8 |  | 9.38 | 46.9 | 37.52 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.5175 |  | 2.0518 | 10.2588 | 8.207 | 0 | 0
|  |  |  | Totals | [5 empty] | 328.5925 |  | 2032.7718 | 2387.0338 | 2097.087 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept A2 |  |  | Gbetiokun Greenfield Evacuated via Jones Creek
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Jones Creek M/F | Opua MPB Station + Gbetiokun F/S exporting thru Jones Creek M/F
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km Multiphase Line to Otumara F/S |  | prem | 0.12 | 360 |  | 43.2 |  | 4.32 | 21.6 | 17.28
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 26km D/L to Jones Creek M/F |  | prem | 0.12 | 208 | inch-km | 24.96 |  | 2.496 | 12.48 | 9.984
|  |  | Gas Export Line | 12" x 26km Gas Export Line to Jones Creek |  |  | 0.12 | 312 | inch-km | 37.44 |  | 3.744 | 18.72 | 14.976
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 19.5575 |  | 1.9558 | 9.7788 | 7.823
|  |  |  | Facilities Engineering Scope | [5 empty] | 215.1325 |  | 19.7157 | 110.0537 | 78.863 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A2 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014, exporting crude thru Jones Creek M/F |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2168.8 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun F/S + D/L | 30 MBD F/S with AG Booster Compr + D/L to Sapele | [5 empty] | 89.96 |  | 8.996 | 44.98 | 35.984 | 0 | 0
|  |  | Gbetiokun Gas Export to Sapele | 12" x 30km Gas Line to Sapele | [5 empty] | 37.44 |  | 3.744 | 18.72 | 14.976 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 19.5575 |  | 1.9558 | 9.7788 | 7.823 | 0 | 0
|  |  |  | Totals | [5 empty] | 318.0325 |  | 2031.7158 | 2381.7537 | 2092.863 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept A3 |  |  | Gas to Power
|  |  | Straight Full OML Development on stream 2014 | Opuama F/S + Gbetiokun F/S
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama F/S Revamp + AG Facilities
|  |  | Revamp Opuama F/S & D/L | 30 MBD F/S + 8" x 2.5 km D/L |  | guess |  |  |  | 5 |  | 0.5 | 2.5 | 2
|  |  | AGG Facilitity (Compression + Gas Conditioning) | 5 - 10 MMscfd Package |  | prem/benchmark |  |  |  | 15 |  | 1.5 | 7.5 | 6
|  |  | Power Plant | 18 MW + Feeder to National Grid |  | prem | 1.25 | 18 | MW | 22.5 |  | 2.25 | 11.25 | 9
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 8" x 36km D/L to Otumara M/F |  | prem | 0.12 | 288 | inch-km | 34.56 |  | 3.456 | 17.28 | 13.824
|  |  |  | Provision for Gas Processing | [5 empty] | 5 |  | 0.5 | 2.5 | 2
|  |  | Power Plant | 18 MW + Feeder to National Grid |  |  | 1.25 | 30 | MW | 37.5 |  | 3.75 | 18.75 | 15
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.2535 |  | 2.0254 | 10.1268 | 8.1014
|  |  |  | Facilities Engineering Scope | [5 empty] | 222.7885 |  | 20.4813 | 113.8817 | 81.9254 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept A3 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2115.9 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama F/S Revamp + AG Facilities | 30 MBDD F/S + 8" x 2.5 km D/L + 10 MMscfd AG Facs | [5 empty] | 20 |  | 2 | 10 | 8 | 0 | 0
|  |  | Opuama Power Plant | 18 MW + Feeder to Grid | [5 empty] | 22.5 |  | 9.956 | 49.78 | 39.824 | 0 | 0
|  |  | Gbetiokun F/S & D/L | 30 MBD + AGG Fac | [5 empty] | 104.56 |  | 4.25 | 21.25 | 17 | 0 | 0
|  |  | Gbetiokun Power Plant | 30 MW | [5 empty] | 37.5 |  | 5.7754 | 28.8768 | 23.1014 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 20.2535 |  | 2.0254 | 10.1268 | 8.1014 | 0 | 0
|  |  |  | Totals | [5 empty] | 325.6885 |  | 2036.0067 | 2350.3085 | 2110.0268 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept B |  |  | Opuama Central Processing facility via Otumara (30 MBD Opuama F/S)
|  |  | Straight Full OML Development on stream 2014 | Opua F/S + Gbetiokun MPB Station
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama F/S Revamp + AG Facilities
|  |  | Revamp Opuama F/S & D/L | 30 MBD F/S + 8" x 2.5 km D/L |  | guess |  |  |  | 5 |  | 0.5 | 2.5 | 2
|  |  | AGG Facilitity (Compression + Gas Conditioning) | 10 - 15 MMscfd Package |  | prem/benchmark |  |  |  | 15 |  | 1.5 | 7.5 | 6
|  |  | Gas Export Line | 12" x 36km Gas Export Line to Otumara |  |  | 0.12 | 432 | inch-km | 51.84 |  | 5.184 | 25.92 | 20.736
Gbetiokun MPB
|  |  | Gbetiokun MPB Station | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Opuama F/S | 12" x 33km Multiphase Line to Opuama F/S |  | prem | 0.12 | 396 |  | 47.52 |  | 4.752 | 23.76 | 19.008
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 14.7335 |  | 1.4733 | 7.3667 | 5.8934
|  |  |  | Facilities Engineering Scope | [5 empty] | 162.0685 |  | 14.4093 | 83.5217 | 57.6374 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept B |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 195.3 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama F/S Revamp + AG Facilities | 30 MBDD F/S + 8" x 2.5 km D/L + 10 MMscfd AG Facs | [5 empty] | 20 |  | 2 | 10 | 8 | 0 | 0
|  |  | Opuama Gas Export Line to Otumara | Opuama gas export Line | [5 empty] | 51.84 |  | 1 | 5 | 4 | 0 | 0
|  |  | Gbetiokun MPB | 2 x 10 Mbpd MPB Pumps | [5 empty] | 10 |  | 4.752 | 23.76 | 19.008 | 0 | 0
|  |  | Gbetiokun MPB | 12" x 33km Multiphase Line to Opuama F/S | [5 empty] | 47.52 |  | 1.4733 | 7.3667 | 5.8934 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 14.7335 |  | 1.4733 | 7.3667 | 5.8934 | 0 | 0
|  |  |  | Totals | [5 empty] | 264.9685 |  | 10.6987 | 363.1685 | 42.7948 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept B1 |  |  | Opuama F/S (Central Processing facility) via Otumara, with Power Generation
|  |  | Straight Full OML Development on stream 2015 | Opua F/S + Gbetiokun MPB Station
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama F/S Revamp + AG Facilities
|  |  | Revamp Opuama F/S & D/L | 30 MBD F/S + 8" x 2.5 km D/L |  | guess |  |  |  | 5 |  | 0.5 | 2.5 | 2
|  |  | AGG Facilitity (Compression + Gas Conditioning) | 10 - 15 MMscfd Package |  | benchmark |  |  |  | 30 |  | 3 | 15 | 12
|  |  | Power Plant | 48 MW + Feeder to National Grid |  | prem | 1.25 | 48 | MW | 60 |  | 6 | 30 | 24
Gbetiokun MPB
|  |  | MPB Station - Gbetiokun | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Opuama F/S | 12" x 33km Multiphase Line to Opuama F/S |  | prem | 0.12 | 396 |  | 47.52 |  | 4.752 | 23.76 | 19.008
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 17.0495 |  | 1.705 | 8.5248 | 6.8198
|  |  |  | Facilities Engineering Scope | [5 empty] | 187.5445 |  | 16.9569 | 96.2597 | 67.8278 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept B1 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 195.3 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama F/S Revamp + AG Facilities | 30 MBDD F/S + 8" x 2.5 km D/L + 10 MMscfd AG Facs | [5 empty] | 35 |  | 3.5 | 17.5 | 14 | 0 | 0
|  |  | Opuama Power Plant | 48 MW + Feeder to National Grid | [5 empty] | 60 |  | 1 | 5 | 4 | 0 | 0
|  |  | Gbetiokun MPB | 25 - 30 MBP Multiphase Pumping Station | [5 empty] | 10 |  | 4.752 | 23.76 | 19.008 | 0 | 0
|  |  | Gbetiokun MPB | 12" x 33km Multiphase Line to Opuama F/S | [5 empty] | 47.52 |  | 1.705 | 8.5248 | 6.8198 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 17.0495 |  | 1.705 | 8.5248 | 6.8198 | 0 | 0
|  |  |  | Totals | [5 empty] | 290.4445 |  | 12.6619 | 372.9845 | 50.6476 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept C |  |  | Gbetiokun Central Processing facility via Escravos
|  |  | Straight Full OML Development on stream 2014 | Opua MPB Station + Gbetiokun F/S
CHA with SPDC and CNL
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Opuama MPB to Gbetiokun
Facilities Multiphase Boosting from Opuama - Gbetiokun F/S
|  |  | MPB Station - Opuama | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Otumara F/S |  | prem | 0.12 | 330 |  | 39.6 |  | 3.96 | 19.8 | 15.84
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 10" x 44km D/L to Escravos |  | prem | 0.12 | 440 | inch-km | 52.8 |  | 5.28 | 26.4 | 21.12
|  |  | Gas Export Line | 12" x 30km Gas Export Line to Sapele |  |  | 0.12 | 360 | inch-km | 43.2 |  | 4.32 | 21.6 | 17.28
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 22.5575 |  | 2.2558 | 11.2788 | 9.023
|  |  |  | Facilities Engineering Scope | [5 empty] | 248.1325 |  | 23.0158 | 126.5538 | 92.063 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept C |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2115.9 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Gbetiokun | [5 empty] | 7 |  | 4.66 | 23.3 | 18.64 | 0 | 0
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Otumara F/S | [5 empty] | 39.6 |  | 3.96 | 19.8 | 15.84 | 0 | 0
|  |  | Gbetiokun F/S + D/L to Escravos | 10" x 44km D/L to Escravos | [5 empty] | 117.8 |  | 11.78 | 58.9 | 47.12 | 0 | 0
|  |  | Getiokun Gas Export line | 12" x 30km Gas Export Line to Sapele | [5 empty] | 43.2 |  | 4.32 | 21.6 | 17.28 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 22.5575 |  | 2.2558 | 11.2788 | 9.023 | 0 | 0
|  |  |  | Totals | [5 empty] | 351.0325 |  | 2038.9758 | 2365.1538 | 2121.903 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept C1 |  |  | Gbetiokun Central Processing facility via Escravos, with Power Generation
|  |  | Straight Full OML Development on stream 2014 | Opua MBS + Gbetiokun F/S with Crude to CNL Terminal at Escravos
CHA with SPDC and CNL
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Gbetiokun F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Gbetiokun F/S |  | prem | 0.12 | 330 |  | 39.6 |  | 3.96 | 19.8 | 15.84
Gbetiokun F/S & D/L
|  |  | Gbetiokun F/S & D/L | Concrete Barge 30 MBD F/S c/w AG Booster Compr |  | prem | 65 | 1 |  | 65 |  | 6.5 | 32.5 | 26
|  |  |  | 10" x 44km D/L to Escravos |  | prem | 0.12 | 440 | inch-km | 52.8 |  | 5.28 | 26.4 | 21.12
|  |  |  | Provision for Gas Processing | [5 empty] | 5 |  | 0.5 | 2.5 | 2
|  |  | Power Plant | 48 MW + Feeder to National Grid |  | prem | 1.25 | 48 | MW | 60 |  | 6 | 30 | 24
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 18.7375 |  | 1.8738 | 9.3688 | 7.495
|  |  |  | Facilities Engineering Scope | [5 empty] | 266.1125 |  | 24.8138 | 135.5438 | 99.255 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept C1 |  |  | Capex Summary: - Type / Fiscal Classifications
|  |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 2012 | 2168.8 | 2014 | 2015 | 2016
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opuama MPB Station | [6 empty] | 7 |  | 0.7 | 3.5 | 2.8 | 0 | 0
|  |  | New Multiphase Line: Opuama - Gbetiokun F/S | 10" x 33km Multiphase Line to Otumara F/S | [5 empty] | 39.6 |  | 3.96 | 19.8 | 15.84 | 0 | 0
|  |  | Gbetiokun F/S + AGG Facs | [6 empty] | 65 |  | 6.5 | 32.5 | 26 | 0 | 0 | 0
|  |  | Gbet D/L | 10" x 44km D/L to Escravos | [5 empty] | 52.8 |  | 5.28 | 26.4 | 21.12 | 0 | 0
|  |  | Provision for Gas Conditioning | [6 empty] | 5 |  | 0.5 | 2.5 | 2 | 0 | 0
|  |  | Power Plant | 48 MW + Feeder to National Grid | [5 empty] | 60 |  | 1.8738 | 9.3688 | 7.495 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 18.7375 |  | 1.8738 | 9.3688 | 7.495 | 0 | 0
|  |  |  | Totals | [5 empty] | 369.0125 |  | 2032.6875 | 2386.6125 | 2096.75 | 2015 | 2016 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept D |  |  | Multiphase Solutions
| Scenario-1 Use the Existing D/L for Multiphase Flow to Otumara |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014 | Opua MPB + Gbetiokun MPB Stations
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  | 2.6 | 2.1 | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  | 1 | 0.9 | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 4 | 8 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 5.5 | 0 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 5.5 | 97.4 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities / Modifications for Early Production from Opuama
|  |  | Integrity Assessment & Revamp | F/S, D/L + M/F |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | F/S Modification Works | Route 1st Stage Sep Outlet to D/L |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | Mod at Otumara M/F of Adagbassa to Otum T/L | Modify at Otum M/F to Route Flow to Otum F/S |  | guess | 1 | 1 |  | 1 |  | 1
|  |  | Multiphase Booster Pump | 5 Mbpd MPB Pump on existing Pump Bay |  | prem | 2 | 1 |  | 2 |  | 2
|  |  | Multiphase Meter at Otumara |  |  | guess | 0.25 | 1 |  | 0.25 |  | 0.25
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | Opuama MPB Station | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | Existing Opuama - Otumara D/L to be used |  | prem | 0.12 |  |  | 0 |  | 0 | 0 | 0
Facilities for Full Field Dev - Gbetiokun
|  |  | MPB Station - Gbetiokun | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Jones Creek F/S | 10" x 26km Multiphase Line to Jones Creek F/S |  | prem | 0.12 | 260 |  | 31.2 |  | 3.12 | 15.6 | 12.48
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 7.1425 |  | 0.71425 | 3.5713 | 2.857
|  |  |  | Facilities Engineering Scope | [5 empty] | 78.5675 |  | 12.9093 | 37.0213 | 22.137 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept D |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-1 |  | Opuama Early Oil in 2012, followed by Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 5.5 | 97.4 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 2.125 | 9.35 | 0 | 0 | 0
|  |  | Opuama Mod for Early Prod | MPB Pump + F/S & D/L Revamp & Mod | [5 empty] | 5.25 |  | 5.25 | 0 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station | [5 empty] | 7 |  | 0.7 | 3.5 | 2.8 | 0 | 0
|  |  | Gbetiokun MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Jones Creek | [5 empty] | 41.2 |  | 4.12 | 20.6 | 16.48 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 7.1425 |  | 0.71425 | 3.5713 | 2.857 | 0 | 0
|  |  |  | Totals | [5 empty] | 181.4675 |  | 18.4093 | 140.9212 | 22.137 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
BFPCL Fields Development Concepts - Building Blocks and Costs Estimate - $mln RT 2022
Concept D |  |  | Multiphase Solutions
| Scenario-2 New Opuama Multiphase Line to Otumara |  | Straight Full OML Development on stream 2014 | Opua MPB + Gbetiokun MPB Stations
CHA with SPDC
|  |  |  | On Stream Date | 2014 | [5 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
[5 empty] | Related Oil Production Forecast |  |  |  |  | Mbopd |  |  |  | 23.7 | 33.8 | 30.5 |  | 28.3 | 25.7 | 19.1 | 15.1 | 15.1
[5 empty] | Related AG Production Forecast |  |  |  |  | MMscfd |  |  |  | 11.6 | 16.6 | 15.9 |  | 15.1 | 14.1 | 10.6 | 7.9 | 7.9
|  |  | Wells Proposal | Scope & Phasing
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry Opua-1, WC Opua - 3,4,5, or 7 |  |  |  | 4 |  |  |  |  | 4
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry + IC Gbet - 1 & 2 |  |  |  | 2 |  |  |  |  | 2
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete |  |  |  | 2 |  |  |  |  | 2
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete |  |  |  | 4 |  |  |  |  | 4
|  |  |  | Total Wells |  |  |  | 12 |  |  |  | 0 | 12 | 0 | 0 | 0
Cost Phasing
|  |  | Wells Costs / Phasing |  |  |  |  | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  | 1 | 4 Opuama Re-Entry / Recompletions | Re-Entry / Recompletion | 1.375 | mln per | well | 4 | well | 5.5 |  | 0 | 5.5 | 0 | 0 | 0
|  | 2 | 2 Gbetiokun Re-Entry | Re-Entry / Initial Completion | 2.5 | mln per | well | 2 | well | 5 |  | 0 | 5 | 0 | 0 | 0
|  | 3 | 2 Opuama Development Wells (1 Vert, 1 Horz) | Drill & Complete | 19.75 | mln per | well | 2 | well | 39.5 |  | 0 | 39.5 | 0 | 0 | 0
|  | 4 | 4 Gbetiokun Development Welss | Drill & Complete | 13.225 | mln per | well | 4 | well | 52.9 |  | 0 | 52.9 | 0 | 0 | 0
|  |  |  | Total Well Cost | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Facilities Proposals | Engineering Works |  | Ref | unit cost ($mln) | Qty | unit | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wellhead Access Platform | Access Platform c/w Access Ladder |  | premise | 0.5 | 13 | no. | 6.5 |  |  | 6.5
|  |  | Well F/L & Hook-up of 4 Opuama Re-Entry & WC | F/L Replacement - constr |  | premise | 0.25 | 5.7 | km | 1.425 |  |  | 1.425
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 7 | no. | 0.7 |  |  | 0.7
|  |  | Well F/Ls + Hk-up of 6 New Drills & 3 Gbet/Bime Re-Entry | 11 x 4" x 3km F/L ansi 1500 |  |  | 0.25 | 33 | km | 8.25 |  |  | 8.25
|  |  |  | F/L Hk-Up (4" ANSI 1500 ---> 3" x 5000) |  |  | 0.1 | 11 | no. | 1.1 |  |  | 1.1
Facilities Multiphase Boosting from Opuama - Otumara F/S
|  |  | MPB Station - Opuama | 20 - 25 Mbpd Multiphase Pumping Station |  | prem | 7 | 1 |  | 7 |  | 0.7 | 3.5 | 2.8
|  |  | New Multiphase Line: Opuama - Otumara F/S | 10" x 36km Multiphase Line to Otumara F/S |  | prem | 0.12 | 360 |  | 43.2 |  | 4.32 | 21.6 | 17.28
Facilities for Full Field Dev - Opuama & Gbetiokun
|  |  | MPB Station - Gbetiokun | 25 - 30 Mbpd Multiphase Pumping Station |  | prem | 10 | 1 |  | 10 |  | 1 | 5 | 4
|  |  | New Multiphase Line: Gbetiokun - Jones Creek F/S | 10" x 26km Multiphase Line to Jones Creek F/S |  | prem | 0.12 | 260 |  | 31.2 |  | 3.12 | 15.6 | 12.48
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 10.9375 |  | 1.0938 | 5.4688 | 4.375
|  |  |  | Facilities Engineering Scope | [5 empty] | 120.3125 |  | 10.2338 | 62.6437 | 40.935 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Concept D |  |  | Capex Summary: - Type / Fiscal Classifications
| Scenario-2 |  | Straight Full OML Development on stream 2014 |  |  |  |  | Project Cost ($mln) |  |  | Cost Phasing
|  |  | Proposal | Total Proposal Scope |  | Ref | B.I. |  |  | ($mln) | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |  | 2017 | 2018 | 2019 | 2020 | 2021
|  |  | Wells | 6 New Wells + 6 Re-Entries | [5 empty] | 102.9 |  | 0 | 102.9 | 0 | 0 | 0
|  |  | Wellhead Access Platform | Accesss Platform c/w Access Ladder | [5 empty] | 6.5 |  | 0 | 6.5 | 0 | 0 | 0
|  |  | Wells F/Ls + Hook-up | F/Ls + Hk-up for Full Field Dev Prod | [5 empty] | 11.475 |  | 0 | 11.475 | 0 | 0 | 0
|  |  | Opua MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Otumara | [5 empty] | 50.2 |  | 5.02 | 25.1 | 20.08 | 0 | 0
|  |  | Gbetiokun MPB Station for Full Field Development | Multiphase Booster Station + Multiphase Line to Jones Creek | [5 empty] | 41.2 |  | 4.12 | 20.6 | 16.48 | 0 | 0
|  |  | Contingency | Contingency @ 10% of Total Capex | [5 empty] | 10.9375 |  | 1.0938 | 5.4688 | 4.375 | 0 | 0
|  |  |  | Totals | [5 empty] | 223.2125 |  | 10.2338 | 172.0437 | 40.935 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0