CONFIDENTIAL

TECHNO-COMMERCIAL PROPOSAL

FOR

FEED (Front End Engineering Design) of DSV

20” x 85 km OKNU–BBOU Gas Pipeline to

Brass Gas Hub at Akabel

PROJECT TITLE

DSV PIPELINE FROM OKPOKUNOU TO BFPCL

BRASS GAS HUB AT AKABEL

CLIENT: DSV Engineering Limited

20th April 2026

# CONFIDENTIALITY STATEMENT

This document contains proprietary and confidential information prepared exclusively for RAEC / BFPCL for the purpose of evaluating the proposed FEED services for the DSV OKNU–BBOU Gas Pipeline to Brass Gas Hub Project. Unauthorized distribution, reproduction, or disclosure is strictly prohibited.

Table of Contents

CONFIDENTIALITY STATEMENT	2

1.0	EXECUTIVE SUMMARY	10

1.1	Situation	10

1.2	The FEED Link with the Survey	11

1.3	Base Case:	12

1.4	Basic Concepts:	13

a)	Gas Gathering System	13

b)	Gas Processing Plant (GPP) – 500 MMscfd	13

c)	Methanol Production Plant	14

d)	Floating LNG (FLNG) Facility	14

e)	Product Export System	14

f)	Produced Water Management	14

g)	Utilities and Offsite Infrastructure	14

h)	Pipeline Design Philosophy – Flexibility & Expandability	14

1.5	Pipeline Engineering	15

a)	Pipeline Routing Philosophy	15

b)	Liquid Management Strategy	15

i.	Upstream Liquid Removal	15

ii.	Diameter Optimization	16

c)	Receiving Facility Protection	16

d)	Liquid Handling and Disposal	16

1.6	Pipeline Capacity and System Integration	16

e)	1. Design Throughput	16

1.7	System Integration	17

1.8	Key Issues & Challenges	18

The key issues and challenges will be the following:	18

1. Timely completion of pipeline route ROW survey needed to firm up flow assurance studies and pipeline sizes	18

2. Proper integration of the existing and new designs that will lend to proper pipeline system functionality	18

3. Pipeline Capacity design to fit the immediate need and future aspiration of 1 BCFD.	18

1.9	FINANCIAL DIMENSION	19

FEED	19

2.0	DESIGN & ENGINEERING DECISSIONS ISSUES	21

1.10	Design Issues & Challenges	21

3.	Specialized Survey Activities – to be undertaken by the following proposed 3rd Party Experienced Contractors	29

s/n	29

Remarks	29

1	29

Name	29

Sckopemate Konsult Limited	29

Role	29

Topographical & Geotechnical Survey	29

Address	29

#4, 1st Crescent, Rumuibikwe, Port Harcourt	29

Contact	29

Paul Nnamah - MD	29

Remarks	29

2	29

Name	29

Environmental Technology Limited (GETL)	29

Role	29

EIA Survey	29

Address	29

Block A2-9, Suite 117, Sura Complex	29

Contact	29

Omotayo Seriki – Chief Operating Officer	29

Remarks	29

3.0	PROJECT DESCRIPTION	33

3.1	Pipeline System Description and Process Design Basis	33

1.1.1	Integrated Gas Transportation Network	33

2.1.1	Hydraulic Integration Philosophy	33

3.1.1	Corrosion Considerations	34

3.2	Pipeline Route Alignment	34

3.3	Midline Manifolds and Future Tie-ins	34

3.4	Water Separation Strategy (to be optimized)	35

4.0	DESIGN PHILOSOPHY	36

3.1	General	36

3.2	Basic Concepts	36

3.3	Codes, Standards and Regulations	37

3.4	Safety Philosophy	38

3.5	Operability and Maintainability	38

3.6	Focus of FEED	38

3.7	Flow Assurance/Pipe Sizing	39

3.8	Value Engineering	39

3.9	Material Selection	39

3.10	Technical Safety	40

3.11	Gas Pressure Boosting	40

3.12	Electric Power	40

3.13	Ergonomics	41

3.14	Operations Assurance	41

3.15	Security, Fire Protection and Accessibility	41

3.16	Survey	42

3.17	Gas Availability	42

3.18	Surveillance	42

3.19	SCADA system and Field Logistics	43

5.0	SCOPE OF WORK AND FEED PROCEDURE	44

4.1	Summary Scope of Work	44

4.2	Detailed Scope of Work	44

4.3	Scope of FEED Services	45

4.4	FEED Procedure	48

4.5	Key Technical Challenges and Project Risks (FEED Focus)	51

4.6	Key FEED Deliverables	52

4.7	Key FEED Deliverables Schedule	52

6.0	EXECUTION STRATEGY	53

5.1	Project Location	53

5.2	Manpower Resourcing / Organisation Chart	53

5.3	Communication	56

5.4	Documentation	56

5.5	Change Control / Quality	56

5.6	Design Review	57

5.7	Design Software	57

7.0	PROJECT EXECUTION AND ADMINISTRATIVE FRAMEWORK	59

7.1	Progress Reporting	59

7.2	Weekly Progress Report	59

7.3	Monthly Progress Report	59

7.4	Progress Review Meetings	59

7.5	Planning – Scheduling and Control	60

7.6	Client Inputs Required	60

7.7	FEED Assumptions and Exclusions	60

7.8	Value Proposition	61

7.9	Conclusion	61

8.0	FEED EXECUTION SCHEDULE	62

8.1	Overall Phasing	62

8.2	Detailed Week-By-Week Structure	62

8.3	Key Reviews	64

8.4	Critical Path Items	64

8.5	Deliverable Maturity Profile	65

8.6	Summary of Proposed FEED Execution Schedule	65

8.7	Schedule Summary	65

9.0	COMMERCIAL PROPOSAL (INTRODUCTION AND OBJECTIVES)	67

9.1	Purpose of the Commercial Proposal	67

9.2	Objectives of the Proposal	67

9.3	Project Scope Alignment	67

10.0	PRICING PHILOSOPHY, BASIS AND COST DRIVERS	68

10.1	Pricing Philosophy	68

10.2	Pricing Basis	68

10.3	Key Cost Drivers	68

11.0	COMMERCIAL COST STRUCTURE AND ESTIMATION	70

11.1	Cost Breakdown by Discipline	70

12.0	PROJECT SCHEDULE AND COMMERCIAL EXECUTION	71

12.1	Project Duration	71

12.2	Commercial Execution Profile	71

12.3	Resource Loading Strategy	71

13.0	ASSUMPTIONS, EXCLUSIONS AND RISK MANAGEMENT	72

13.1	Key Assumptions	72

13.2	Exclusions	72

13.3	Commercial Risk Assessment	72

13.4	Contingency Provision	72

14.0	CONTRACTUAL FRAMEWORK, LOCAL CONTENT AND VALUE PROPOSITION	73

14.1	Contract Type and Commercial Structure	73

14.2	Variation Management	73

14.3	Local Content Compliance	73

14.4	Value Addition	73

14.5	Commercial Strength & Execution Capability	73

15.0	COMPETITIVE ADVANTAGE (WHY US) AND CONCLUSION	75

15.1	Technical Strength	75

15.2	Commercial Competitiveness	75

15.3	Local Content & Execution Advantage	75

15.4	Integrated Delivery Approach	75

15.5	Commitment to Quality and Schedule	75

15.6	Conclusion	75

16.0	CORPORATE CAPABILITY AND PROJECT EXPERIENCE	77

16.1	Company Profile	77

# EXECUTIVE SUMMARY

## Situation

The Front-End Engineering Design (FEED) scope covers the development of a provisional 20-inch, approximately 85 km DSV gas pipeline from the RAEC Okpokunou (OKNU) Field to the BFPCL Manifold at BBOU, traversing the challenging swamp terrain of the Niger Delta.

The final pipeline diameter and routing will be subject to confirmation based on the FEED studies, including flow assurance and route optimization.

The FEED execution will be undertaken by Epic Atlantic Limited, the contractor responsible for the Phase 1 BBOU–ELEP–AKAB pipeline project. This ensures technical continuity, integration with existing infrastructure, and effective utilization of prior project data and lessons learned.

To support the FEED activities, specialized survey and environmental studies will be executed by experienced third-party contractors as follows:

- Sckope Limited is proposed to undertake the Topographical and Geotechnical Surveys for the pipeline Right-of-Way (ROW), and

- GETL or Foisi Global will be responsible for conducting the Environmental Impact Assessment (EIA) in compliance with applicable regulatory requirements.

Both contractors possess extensive operational experience within the Niger Delta environment and are accredited by the Nigerian Upstream Petroleum Regulatory Commission (NUPRC) and the Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA).

The survey scope is defined as follows:

- The OKNU–BBOU pipeline route is a new development; accordingly, comprehensive topographical, geotechnical, and Environmental Impact Assessment (EIA) surveys shall be executed along the proposed pipeline corridor and all associated facilities.

- The BBOU–ELEP–AKAB pipeline route, previously surveyed under Phase 1, shall undergo repeat and supplementary topographical and geotechnical surveys to accommodate route modifications, updated design requirements, identified data gaps, and sections previously omitted from earlier investigations.

These survey activities will generate the baseline technical and environmental data required to support detailed engineering design, regulatory and environmental approvals, cost estimation, constructability assessment, and overall project execution planning.

## The FEED Link with the Survey

While the FEED will establish a technically robust, flexible, and scalable gas transportation and processing system, enabling:

- Efficient evacuation of OKNU gas

- Seamless integration with existing existing design & infrastructure

- Future expansion into a regional gas hub (up to 1 BCFD)

- Diversified monetization via methanol and LNG production

The Survey provides the data for the Design, under the oversight of the FEED, in shared vision and ownership mode:

- The pipeline will traverse predominantly swamp and riverine terrain, requiring specialized design considerations for constructability, integrity, and environmental protection.

- Define the pipeline route and Right-of-Way (ROW) requirements

- Establish a robust Design Basis Memorandum (DBM)

- Generate cost estimates (±15% accuracy)

- Identify project risks and mitigation strategies

- Provide input for Environmental and Regulatory approvals

- Develop execution philosophy and contracting strategy

New Pipeline: OKNU–BBOU

- Full Topographical Survey (ROW mapping, terrain profiling, obstacles)

- Full Geotechnical Investigation (soil stratigraphy, bearing capacity, swamp conditions)

- Full Environmental Impact Assessment (EIA)

- Repeat and supplementary Topographical Survey

- Updated Geotechnical Investigation

## Base Case:

Schematics of Gas Supply from Okpokunou alongside Phase-1 Gas Supply

Satellite Imagery of Gas Supply from Okpokunou alongside Phase-1 Gas Supply

## Basic Concepts:

The pipeline diameter and length are preliminary and will be finalized based on detailed flow assurance studies, hydraulic simulations, and route surveys.  However, current hydraulic assessments indicate a potential pipeline diameter in the range of 20-inch to 24-inch, depending on throughput optimization scenarios (up to 300 MMscfd, including future expansion cases); and utilization of midline slug catcher between OKNU and ELEP to manage transient flow conditions.

The downstream BBOU–ELEP–AKAB pipeline segment has been previously designed for a capacity of 340 MMscfd.  With the introduction of additional gas volumes from OKNU, a detailed capacity assessment will be conducted to determine whether the existing system can accommodate the incremental flow.

Where required, pipeline resizing, looping, or compression options will be evaluated to ensure full system integrity and performance.

The OKNU–BBOU pipeline will therefore be technically integrated with the existing BBOU–ELEP–AKAB system, ensuring full alignment in:

- Design specifications

- Hydraulic performance

- Materials and corrosion philosophy

- Operational flexibility

This integration may necessitate revisions to previously established pipeline sizes, particularly in anticipation of a future gas hub capacity of up to 1 BCFD.

Gas from OKNU will contribute to a diversified monetization strategy, including methanol production and LNG export.

An offshore Floating LNG (FLNG) facility is proposed at approximately 20 km offshore in ~20 m water depth, utilizing modular topsides and a spread mooring system.

BFPCL Petrochemical Complex at Akabel – Facilities Overview

The integrated development at Akabel will comprise the following key facilities:

# Gas Gathering System

- Network of pipelines and manifolds transporting gas from OKNU, BBOU, and ELEP fields to the central processing facility.

# Gas Processing Plant (GPP) – 500 MMscfd

- Extraction of Natural Gas Liquids (NGLs)

- Delivery of lean gas to downstream facilities

- Includes:

  - Common front-end processing

  - Dedicated polishing units for Methanol and LNG

# Methanol Production Plant

- Two trains, each rated at 5,000 MTPD

- Total production capacity: 10,000 MTPD

# Floating LNG (FLNG) Facility

- Capacity: ~2 MMTPA LNG

- Feed gas: >200 MMscfd processed gas

- Location: ~20 km offshore, ~20 m water depth, complete with +25 km Feed Gas Supply Line from Gas Hub at AKAB to the FLNG

- Products:

  - LNG

  - Condensate

  - LPG (Butane & Propane)

# Product Export System

- Export pipelines

- Offshore Single Buoy Mooring (SBM) system for methanol and NGL export

# Produced Water Management

- Handling, treatment, and disposal facilities

- To be defined through Decision Concept Selection (DCS) studies

# Utilities and Offsite Infrastructure

- Power generation systems

- Steam generation

- Product storage facilities

- Export jetty and marine infrastructure

- All required off-plot and support systems

# Pipeline Design Philosophy – Flexibility & Expandability

While the primary objective of the OKNU–BBOU pipeline is evacuation of Okpokunou gas production, the design incorporates provisions for future network expansion through strategically located midline manifolds, which will also function as sectionalizing valve stations.

Planned Tie-in Points:

- KP 38, - for tie-in of SEIB production:

  - Confirmed tie-in point

  - Identified as a key gas supply node

- KP 66, - for tie-in of NUNR / DBUG production:

  - Conditional tie-in, subject to future development

Given proximity and routing efficiency, SEIB is considered the most practical near-term tie-in to the OKNU–BBOU pipeline, hence the midline manifold at KP 38

For NUNR and DBUC, a shared midline manifold near DBUC, subject to firm gas supply commitments, will be more cost effective than dedicated manifolds.  The option of an independent pipeline network to gather NUNR & DBUC production to BBOU or ELEP will be evaluated during the FEED.

## Pipeline Engineering

# Pipeline Routing Philosophy

The original concept for the Okpokunou Pipeline envisaged a direct connection to the Elepa Manifold (ELEP). However, subsequent routing assessments indicated that the proposed alignment would intersect the BBOU manifold corridor and run in close parallel with the existing/planned BBOU–ELEP pipeline in the downstream section.

It is therefore considered technically and economically prudent to terminate the pipeline at the BBOU manifold and utilize the planned BBOU–ELEP pipeline segment rather than constructing a dedicated line to ELEP.

This approach offers the following advantages:

- Approximate reduction of ~ 8 km in pipeline length

- Measurable CAPEX savings

- Reduced environmental footprint

- Minimized corridor congestion

- Improved constructability within Niger Delta swamp terrain

# Liquid Management Strategy

### Upstream Liquid Removal

The base case concept provides for removal of the majority of entrained liquids upstream at Okpokunou in order to:

- Reduce hydraulic loading

- Improve flow stability

- Minimize slugging risk

- Optimize downstream pipeline sizing

Accordingly, a slug catcher is proposed at Okpokunou.

### Diameter Optimization

Early liquid removal may permit optimization of pipeline diameter. However, final sizing will be confirmed during FEED through:

- Steady-state hydraulic modeling

- Transient multiphase simulation

- Comparative evaluation of alternate slug catcher locations (inlet vs midline vs outlet)

- Sensitivity cases for turndown and ramp-up scenarios

# Receiving Facility Protection

A slug catcher at the Pipeline End Manifold (PLEM) will provide protection against liquid slugs, thereby safeguarding downstream processing equipment and ensuring stable plant operations.

# Liquid Handling and Disposal

The slug catcher facility will include full liquid-handling systems comprising:

- Condensate/NGL transfer facilities to AKAB for processing

- Produced water collection and handling system

- Storage and metering as required

- Produced water disposal options will include:

- Offshore discharge (subject to regulatory compliance)

- De-mineralisation for industrial use

- Other approved beneficial reuse options

Discharge into inland waters is not permissible under NUPRC and FMEnv regulations.

## Pipeline Capacity and System Integration

The pipeline will be designed to transport up to 300 MMscfd of raw wellhead natural gas, made up as follows:

# 1. Design Throughput

The pipeline will be designed for a maximum capacity of 300 MMscfd of raw wellhead natural gas, comprising:

- 200 MMscfd from the RAEC-DSV Gas Sales and Purchase Agreement

- 70 MMscfd make-up gas on RAEC 270 MMscfd, in case the 70 MMscfd production will be coming from the fields whose production will be tied-in to the Okpokunou pipeline, or even from Okpokunou itself.

- 30 MMscfd design allowance, - for production upside

- Total Design Capacity: 300 MMscfd

The 300 MMscfd will flow to the BBOU manifold, from where the gas will join the BBOU enroute to ELEP via an existing/planned 20” x 8km to the ELEP M/F, enroute through 28-inch × 32 km trunkline to the Akabel Gas Processing Hub. At Akabel, the gas will be processed as feedstock for a Methanol Manufacturing Plant.

## System Integration

Gas will flow:

- From OKNU to BBOU via the proposed 20” x ~ 85 km pipeline

- From BBOU through an existing/planned 20” × ~8 km line to ELEP

- From ELEP through a 28” × ~ 32 km trunkline to the Akabel Gas Processing Hub

At Akabel, the gas will be processed as feedstock for a Methanol Manufacturing Plant.

The OKNU–BBOU pipeline shall therefore be designed to reliably transport up to 300 MMscfd under all operating scenarios, while maintaining full flow assurance across the integrated OKNU–BBOU–ELEP–AKAB pipeline network, ensuring delivery of the target 500 MMscfd to the Gas Hub.

Pipeline Routing and Terrain

The approximately 85 km pipeline will traverse challenging Niger Delta swamp terrain and include:

- One major crossing of the River Niger, (a distributary of the Niger River), estimated at:

  - 200 m width

  - 9 m water depth

- Four (4) additional river crossings

- Eight (8) creek crossings

- Standard inlet manifold facilities at OKNU

- Terminal manifold facilities at BBOU

Special crossing methodologies (e.g., HDD, microtunneling, or cofferdam/trench methods) will be evaluated during FEED based on geotechnical and bathymetric investigations.

Pipeline Size Decision

The pipeline diameter shall be selected as the optimum commercial size capable of reliably transporting the forecast gas volumes to BBOU at a delivery pressure sufficient to ensure that the combined streams from BBOU arrive at the Gas Plant inlet at the required 60 barg.

The final diameter will be established through integrated hydraulic and flow assurance modelling of the full export corridor, including:

- OKNU–BBOU pipeline (new design subject line, currently assessed at 20” – 24”)

- Existing Design 20” BBOU–ELEP pipeline, currently assessed at 20” – 24”

- Existing Design 28” ELEP–AKAB pipeline, currently assessed at 30” – 32”

System-wide validation will confirm that the selected diameter sustains the target throughput while maintaining pressure, temperature, and operability margins across all operating scenarios. Should modelling indicate hydraulic or flow assurance constraints within the downstream segments, re-sizing of the affected sections will be evaluated to preserve system integrity and performance.

Where the hydraulically optimal diameter differs materially from the commercially efficient size, competing options shall be comparatively assessed based on:

- Capacity robustness and future expansion potential

- Flow assurance risks (liquids handling, turndown, slugging, hydrate margin)

- CAPEX and lifecycle OPEX implications

- Constructability and swamp terrain constraints

- Uncertainty in production forecast and ramp-up profile

The selected diameter will therefore represent a balanced, risk-informed decision that optimizes commercial viability, operational reliability, and long-term system flexibility.

## Key Issues & Challenges

## The key issues and challenges will be the following:

## 1. Timely completion of pipeline route ROW survey needed to firm up flow assurance studies and pipeline sizes

## 2. Proper integration of the existing and new designs that will lend to proper pipeline system functionality

## 3. Pipeline Capacity design to fit the immediate need and future aspiration of 1 BCFD.

## FINANCIAL DIMENSION

The Techno-Commercial Proposal comprises two (2) independent elements:

- FEED by Epic Atlantic Limited

- Pipeline Route ROW Surveys – EIA, and Topographical & Geotechnical Surveys by 3rd Party Specialist Contractors

# FEED

Price will be based on the following:

- Design & Engineering

| s/n | Item | Description | Value |
| --- | --- | --- | --- |
| 1 | Original Daily Rate | As per current FEED Contract of Feb 2002 | USD 250.00 |
| 2 | Inflation Adjustment | Current USD inflation at 3% p.a. over 4 years (2022–2026) = ((4 x 1.034) – 1) = 0.1255 = 12.55% | + 12.55% |
| 3 | Adjusted Daily Rate | USD 250 x 1.1255 = USD 281.38 | USD 281.38 |
| 4 | FEED Price | Deducible from CTR: Manday Rate x Mandays | USD=1,992,852= |

- Survey Services

| s/n | Item | Description | Bundled Cost Estimate |
| --- | --- | --- | --- |
| 1 | Pipeline Route ROW – EIA Survey & | Bundled Integrated RFQ to 3rd Party | USD=660,000= |
| 2 | Pipeline Route ROW – Topographical Survey | Bundled Integrated RFQ to 3rd Party |  |
| 3 | Pipeline Route ROW – Geotechnical Survey | Bundled Integrated RFQ to 3rd Party |  |

Significant value optimization is achieved when the EIA, Topographical, and Geotechnical scopes are executed under an integrated framework, ensuring schedule efficiency, data consistency, and reduced overall project cost

- Extras / Reimbursable

- Extra-ordinary involvement will be discussed with DSV/BFPCL for separate billing when it arises.

- Site visits will be at DSV/BFPCL’s expense or on a reimbursable basis

- Residency at Project Sites, and Factory Visits - To be agreed separately with DSV/BFPCL

The Cost Time Resource (CTR) Catalogue:

# DESIGN & ENGINEERING DECISSIONS ISSUES

The key issues and challenges will be the following:

1. Timely Completion of ROW Surveys (Topographical, Geotechnical & EIA)
The schedule-critical nature of the ROW surveys cannot be overstated. These surveys form the foundation for route selection, hydraulic modeling, and ultimately pipeline sizing. Delays or incomplete data will directly impact flow assurance studies, constructability assessments, and cost estimates.
In the Niger Delta swamp terrain, additional constraints such as accessibility, seasonal flooding, community interface, and permitting can further affect timelines. Early mobilization, parallel execution of survey activities, and robust stakeholder engagement will be essential to mitigate schedule risks.

2. Integration of Existing and New Pipeline Systems
A key technical challenge lies in ensuring seamless integration between the proposed OKNU–BBOU pipeline and the existing BBOU–ELEP–AKAB pipeline network. This requires:

Verification of existing pipeline integrity, alignment, and as-built data

Hydraulic compatibility (pressure regimes, flow rates, and backpressure effects)

Alignment of control systems, metering philosophy, and SCADA integration

Tie-in design that minimizes operational disruption and ensures safety

Failure to properly integrate both systems could result in operational inefficiencies, bottlenecks, or integrity risks. A comprehensive system-wide simulation and interface management plan will therefore be required.

3. Pipeline Capacity Design for Immediate and Future Demand (Up to 1 BCFD)
The pipeline must be designed to accommodate both current production volumes and future expansion targets of up to 1 billion standard cubic feet per day (1 BCFD). This introduces several engineering trade-offs:

Selecting an optimal diameter that avoids underdesign (leading to early bottlenecks) or overdesign (resulting in unnecessary CAPEX)

Allowing for phased development (e.g., initial operation at lower throughput with future compression upgrades)

Ensuring material selection and wall thickness can accommodate future pressure increases

Incorporating provisions for looping, compression, or debottlenecking in later project phases

A robust flow assurance and hydraulic modeling study will be critical to validate the selected design basis and ensure long-term system flexibility.

Cross-Cutting Risks to Monitor

Across all three areas, the following overarching risks should be actively managed:

Data uncertainty from legacy pipeline information

Environmental and regulatory approval timelines

Community and stakeholder engagement challenges

Constructability constraints in swamp and river-crossing sections

Interface risks between FEED, survey contractors, and future EPC execution

Scenarios of OKNU – BBOU Pipeline

- Length Profile: -

- OKNU to Niger River Crossing: ~ 10.68 km

- Niger River Crossing: ~ 167.61 m

|  | - 18in Pipeline-run - 270 MMSCFD Deliverability: - Source Pressure – OKNU F-MF: ~ 164 barg - Arrival Pressure – AKAB: 60 barg - 20in Pipeline-run - 270 MMSCFD Deliverability: - Source Pressure – OKNU F-MF: ~ 130 barg - Arrival Pressure – AKAB: 60 barg - 24in Pipeline-run - 270 MMSCFD Deliverability: - Source Pressure – OKNU F-MF: ~ 94 barg - Arrival Pressure – AKAB: 60 barg |
| --- | --- |

Manifold Facilities

Each midline manifold station shall be designed as a secure, autonomous installation incorporating:

Process Facilities

- Manifold headers for:

- Dedicated DSV custody/check metering for OKNU–BBOU bulk gas flow

Midline Manifolds (Future Tie-ins)

While the primary objective is evacuation of Okpokunou production, provision will be made for future tie-ins from:

  - SEIB tie-in (KP 38) – Firm

  - NUNR/DBUC tie-in (KP 66) – Conditional

Given relative proximity and routing logic, SEIB is considered the most practical candidate for tie-in to the OKNU–BBOU pipeline.

Also, given hydraulic and capacity constraints, only one additional supply node is pragmatically feasible within the current configuration without upsizing.

For NUNR and DBUC, subject to firm gas supply commitments, a separate pipeline network to BBOU may be developed. Conceptual schematics of alternative network configurations will be evaluated during FEED.

Process Design Basis

- Pipeline inlet pressure: ~100 barg

- Pipeline outlet pressure: ~60 barg

- Gas source: 3–4 clustered production wells

- Fluid composition: Raw natural gas containing approximately 2.0–2.5% CO₂

The presence of CO₂ at elevated pressure renders the service mildly corrosive (sweet service with CO₂ corrosion potential).

The FEED shall address:

- Material selection (linepipe, fittings, valves, internals)

- CO₂ corrosion modelling and mitigation strategy

- Internal corrosion allowance vs inhibition philosophy

- Integrity assurance framework

- Suitability for mildly corrosive (“sour-lean”) gas service

Concept Selection Methodology

The final configuration (slug catcher location, pipeline diameter, tie-in strategy, and system integration philosophy) will be determined during FEED through a structured techno-economic evaluation incorporating:

- CAPEX and OPEX comparison

- Lifecycle cost analysis

- Flow assurance modeling

- Operability assessment

- Constructability in swamp terrain

- Environmental and permitting considerations

- Expandability and future integration

The schematics of options for new pipeline networks are shown below.

Applicable Codes and Standards

The FEED shall comply with the latest editions of applicable international and local standards, including but not limited to:

Pipeline Design Codes

- ASME B31.8 – Gas Transmission and Distribution

- ISO 13623 – Petroleum and Natural Gas Pipeline Systems

- DNV-ST-N101 – Submarine/Swamp Pipeline Systems

Materials and Welding

- API 5L – Line Pipe Specification

- ASME Section IX – Welding Qualifications

Corrosion and Integrity

- NACE SP0169 – Cathodic Protection

- ISO 15589 – Pipeline Corrosion Control

Survey and Geotechnical

- ASTM Standards for soil testing

- BS 5930 – Code of Practice for Site Investigations

Environmental

- Nigerian EIA Act

- NUPRC Environmental Guidelines

- IFC Environmental & Social Performance Standards

Satellite Imagery – of New Pipeline Provision for Future Tie-in of NUNR & DBUC, - Two Options: Option 1: DBUC to ELEP through BBOU / Option 2: DBUC direct to ELEP

Option 2: DBUC to ELEP through BBOU- New Pipeline Network Provision for Future Tie-in of NUNR & DBUC

Pipeline Facilities

The DSV pipeline system shall include, but not be limited to:

- Launch and receiving facilities (pig launcher & receiver)

- Gas metering stations (as required)

- Temporary cathodic protection (sacrificial anodes during construction)

- Permanent Impressed Current Cathodic Protection (ICCP) system

- Fibre Optic Cable (FOC) for:

  - Leak detection

  - Intrusion monitoring

  - Communications

- Associated block valves and sectionalization facilities

Water Separation (Subject to FEED Evaluation)

Provision shall be made for water separation at one of the following candidate locations:

- Pipeline inlet at OKNU

- Pipeline outlet at BBOU

- Akabel Gas Hub Station – Firm candidate

Final selection shall be based on:

- Techno-economic optimization

- Hydraulics and liquid hold-up modelling

- Operability and maintainability

- Corrosion management philosophy

Control & Power

- Remote Terminal Unit (RTU)

- Control Room / Field Auxiliary Room (FAR)

- Solar power system with battery storage (minimum 7-day autonomy)

- Electrical transformer and enclosed electrical room

Chemical Injection

- Corrosion inhibitor injection

- Biocide injection

- Methanol injection

Utility & Safety Systems

- Closed drain vessel

- Open drain tank

- Cold vent system for controlled depressurization of trapped volumes

- Earthing and lightning protection system

- Gantry structure with lifting accessories

- Weather shelter / guard house

- High-security perimeter fencing (e.g., Citadel, Heras, or equivalent)

- Navigation aids (aviation/marine lighting where applicable)

# Specialized Survey Activities – to be undertaken by the following proposed 3rd Party Experienced Contractors

| # s/n |  | # Remarks |
| --- | --- | --- |
| # 1 | # Name | # Sckopemate Konsult Limited |
|  | # Role | # Topographical & Geotechnical Survey |
|  | # Address | # #4, 1st Crescent, Rumuibikwe, Port Harcourt |
|  | # Contact | # Paul Nnamah - MD 0803 407 1116 Paul.nnamah@sckope.com |
|  | # Remarks | Extensive operational experience within the Niger Delta environment Accredited by the Nigerian Upstream Petroleum Regulatory Commission (NUPRC) and the Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA). |
| # 2 | # Name | # Environmental Technology Limited (GETL) |
|  | # Role | # EIA Survey |
|  | # Address | # Block A2-9, Suite 117, Sura Complex Simpson Street, Lagos Island , Lagos |
|  | # Contact | # Omotayo Seriki – Chief Operating Officer 0807 496 3021 omotayoseriki@yahoo.com |
|  | # Remarks | Extensive operational experience within the Niger Delta environment Accredited by the Nigerian Upstream Petroleum Regulatory Commission (NUPRC) and the Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA). |

  - Topographical Survey: -

- OKNU–BBOU Pipeline Route (New Survey)

- BBOU–ELEP–AKAB Pipeline Route (Repeat Survey due to route changes/omissions)

SCOPE AND SPECIFICATIONS

Scope will comprise mainly the following:

- Topographical Survey Report (including digital terrain models)

- GIS database and shapefiles (pipeline alignment, KP chainage)

- Updated survey datasets for BBOU–ELEP–AKAB

To this effect ITT will be duly issued containing Scope & Specifications, however note the following:

- The chainage will be done in the direction of flow from source to sink, from KP 0 to KP125.

- The pipeline should follow the optimized route to the Gas Pant Inlet Slug Catcher and not to the Methanol Plant.

  - Geotechnical Survey: -

- OKNU–BBOU Pipeline Route (New Survey)

- Geotechnical Investigation Report (boreholes, lab tests)

- BBOU–ELEP–AKAB Pipeline Route (Repeat Survey due to route changes / omissions)

- Soil classification along ROW

- Bearing capacity and settlement analysis

- Slope stability and erosion control

- Riverbank and shoreline protection requirements

- Groundwater and swamp interaction

SCOPE AND SPECIFICATIONS

To this effect ITT will be duly issued containing Scope & Specifications, however note the following:

- The soil sampling should not terminate at mud or soft clay but on hard rock.

- Please follow the specifications in the ITT.

  - EIA Survey: -

- OKNU–BBOU Pipeline Route (New Survey)

- Environmental sensitivity mapping

- Biodiversity and habitat impact assessment

- Community and socio-economic considerations

- Spill prevention and response planning

- Regulatory compliance framework

SCOPE AND SPECIFICATIONS

Again, the ITT will be duly issued containing Scope & Specifications, however note the following:

  - The exercise will involve 2 seasons, wet and dry seasons

  - The Scope of Work defines the requirements for conducting a full Environmental Impact Assessment (EIA) for the proposed OKNU–BBOU gas pipeline (~85 km) and associated facilities within the Niger Delta swamp terrain.

The assessment shall comply with:

- Federal Ministry of Environment Nigeria EIA Act Cap E12 LFN 2004

- Department of Petroleum Resources (now NUPRC) Environmental Guidelines

- International Finance Corporation Performance Standards

- World Bank Environmental & Social Framework (ESF)

The EIA shall cover the full lifecycle impacts of:

Pipeline System

- 20”–24” gas pipeline (~85 km) from OKNU to BBOU

- Design throughput up to 300 MMscfd (expandable)

- Swamp, riverine, and floodplain terrain

Key Facilities

- OKNU Manifold (KP 0)

- River Niger Crossing (KP 10) – critical sensitivity zone

- Midline Manifolds:

  - KP 38 (SEIB tie-in)

  - KP 66 (NUNR/DBUC tie-in)

- BBOU Manifold (KP 85)

Downstream Integration

- BBOU–ELEP–AKAB pipeline system

- Akabel Petrochemical Complex

- Offshore FLNG (~20–25 km offshore)

# PROJECT DESCRIPTION

# Pipeline System Description and Process Design Basis

# Integrated Gas Transportation Network

The OKNU–BBOU pipeline forms part of an integrated gas gathering and transmission corridor delivering gas to the DSV Gas Hub at Akabel.

Gas will flow:

- From OKNU to BBOU via the proposed ~85 km pipeline

- From BBOU through an existing/planned 20” × ~8 km line to ELEP

- From ELEP through a 28” × 32 km trunkline to the Akabel Gas Processing Plant.

At Akabel, the gas will be processed as feedstock for a Methanol Manufacturing Plant.

The OKNU–BBOU pipeline shall therefore be designed to reliably transport up to 300 MMscfd under all operating scenarios, while maintaining full flow assurance across the integrated OKNU–BBOU–ELEP–AKAB pipeline network, ensuring delivery of the target 500 MMscfd to the Gas Hub.

# Hydraulic Integration Philosophy

The OKNU–BBOU pipeline shall be hydraulically integrated with the downstream BBOU–ELEP and ELEP–AKAB transmission system to ensure stable, reliable and uninterrupted gas delivery to the Akabel Gas Hub.

The hydraulic design shall consider:

- Pressure interaction between OKNU supply and downstream trunkline capacity

- Cumulative injection from SEIB, NUNR and DBUC tie-ins

- Pressure drop across the BBOU–ELEP 20” segment

- Capacity limitations of the 28” ELEP–AKAB trunkline

- Transient scenarios including ramp-up, turndown and restart

The pipeline shall be sized and operated such that:

- 300 MMscfd can be reliably transported from OKNU to BBOU

- The integrated network supports delivery of up to 500 MMscfd to Akabel

- Backpressure effects from downstream systems do not compromise upstream well deliverability

- Flow assurance is maintained across the entire OKNU–BBOU–ELEP–AKAB corridor

Full steady-state and transient hydraulic modelling shall be carried out during FEED to validate network operability under all defined scenarios.

# Corrosion Considerations

CO2 presence in the raw wellhead gas results in mildly corrosive (“sour lean”) service.

FEED will define:

- Material selection

- Corrosion modelling

- Internal corrosion allowance vs inhibition philosophy

- Integrity management framework

- Fitness for service

| Parameter | Description |
| --- | --- |
| Pipeline Diameter | 20 inches |
| Pipeline Length | Approximately 85 km |
| Fluid type/composition | Raw well head gas containing approximately 2.0–2.5% CO₂ |
| Material | API 5L X70 PSL 2 |
| Design Life | Minimum 25 years |
| Design Pressure | 110 barg |
| Inlet Pressure | 100 barg |
| Outlet Pressure | 60 barg |
| Design Capacity | 300 MMscfd |
| Terrain | Niger Delta Swamp |
| Gas source | 3-4 clustered production wells |
| River Crossings | 5 (1 major river crossing and 4 additional river crossings) |
| Creek Crossings | 8 |

# Pipeline Route Alignment

The pipeline route originates at the RAEC OKNU Field and terminates at the BFPCL BBOU Manifold. Route selection will consider:

- Environmental and social constraints

- River and road crossings

- Existing infrastructure corridors

- Constructability and access

# Midline Manifolds and Future Tie-ins

Provision for:

- SEIB (KP ~38 km) – Firm

- NUNR (KP ~45 km) – Conditional

- DBUC (KP ~66 km) – Conditional

Hydraulic constraints indicate that only one additional supply node is feasible without upsizing.

FEED will evaluate conceptual network alternatives for NUNR & DBUC:

- Direct DBUC → ELEP

- DBUC → BBOU → ELEP

With lifecycle cost comparison.

The SEIB, NUNR and DBUC tie-ins will allow injection of third-party gas into the OKNU–BBOU pipeline.

Their facilities would include:

- 20” hot/cold tie-in provision

- Full-bore isolation valve

- Pig-passable branch connection

- Provision for future metering and regulation

- Blind flange for future expansion

- Hydraulic integration with the main pipeline

Each midline manifold shall be fully automated and designed for future production scalability.

# Water Separation Strategy (to be optimized)

Candidate locations:

- OKNU inlet

- BBOU outlet

- Akabel Gas Hub (firm candidate)

Final decision will be based on:

- Hydraulic modelling

- Liquid hold-up behaviour

- Corrosion philosophy

- Lifecycle economics

- Operability

Discharge to inland waters is not permissible under NUPRC and FMEnv regulations.

# DESIGN PHILOSOPHY

## General

The basic principles that will govern the FEED will be safety, value engineering, fitness- for-purpose, quality, and timely delivery. It will be performed in line with the Contract Document but will explore and recommend innovative options that have potential to enhance project value, for total resource utilization and optimum value realization.

The FEED will follow relevant design codes and standards, and well-established quality facilities delivery processes and engineering activity models of the industry. Of the essence will be the deployment of highly competent professionals of the various disciplines of engineering and allied services, as well as state-of-the-art engineering tools needed to execute the project.

EPIC ALTANTIC, with its experienced engineering professionals, will provide additional value by putting emphasis on and addressing the following:

## Basic Concepts

- Pipeline Routing Philosophy
The original concept for the Okpokunou Pipeline (OKNU) was to route it directly to the Elepa Manifold (ELEP). However, subsequent routing studies indicated that the pipeline would intersect the BBOU manifold corridor and run in close parallel to the existing/planned BBOU–ELEP pipeline toward the downstream section.

It is therefore considered prudent to tie into the BBOU manifold and utilize the planned BBOU pipeline to ELEP rather than constructing a dedicated line to ELEP. This approach is technically and economically superior due to reduction in the pipeline length by approximately 9 km, resulting in measurable capital cost savings, reduced environmental footprint, reduced corridor congestion and improved constructability in swamp terrain. The routing logic will be validated through FEED-level survey and optimization studies.

- Capacity and Design Throughput Basis
The 300 MMscfd design capacity comprises of 200 MMscfd (RAEC-DSV GSPA commitment), 70 MMscfd contingency production (OKNU or tie-in fields) and 30 MMscfd design upside allowance. The OKNU-BBOU pipeline shall maintain full flow assurance across the integrated network to deliver the target 500 MMscfd to Gas Hub. FEED will verify hydraulics through steady-state modelling, transient multiphase simulation, ramp-up and turndown sensitivity analysis.

- Liquid Management Strategy
The base concept is to remove most entrained liquids at the upstream stage, thereby significantly reducing the hydraulic load on the pipeline to ELEP/Akabel. Accordingly, a slug catcher is proposed at Okpokunou.

This strategy may potentially permit optimization of the pipeline diameter; however, this will be confirmed during FEED through hydraulic analysis and comparative evaluation against alternative configurations, including slug catcher installation at the pipeline midline or outlet.

- Receiving Facility Protection
A slug catcher at the Pipeline End Manifold (PLEM) will provide protection against liquid slugs, thereby safeguarding downstream processing equipment and ensuring stable plant operations.

- Terrain and Crossings

The alignment traverses Niger Delta swamp terrain and includes:

- Major crossing of the Nun River (>250 m width; >9 m depth)

- 4 additional river crossings

- 8 creek crossings

Crossing methodologies to be evaluated:

- Horizontal Directional Drilling (HDD)

- Micro-tunnelling

- Cofferdam / open-cut trenching

Selection will be based on geotechnical, bathymetric, constructability, and CAPEX considerations.

- Liquid Handling and Disposal
The slug catcher will be designed with a full complement of liquid-handling facilities, including provisions for:

- Condensate/NGL transfer to AKAB for final processing

- Produced water management

- Produced water disposal shall be executed either offshore or via reinjection into suitable aquifers, and other beneficial use, as discharge into inland waters is prohibited under NUPRC and FMEnv regulations.

- Concept Selection
The final configuration will be determined through techno-economic evaluation, incorporating lifecycle cost analysis, operability, constructability, and flow assurance considerations.

## Codes, Standards and Regulations

The pipeline FEED shall comply with, but not be limited to:

- ASME B31.8 – Gas Transmission and Distribution Piping Systems

- DNV-ST-N001 / N002 – Subsea & Pipeline Systems

- NACE SP0169 – Cathodic Protection

- IEC / IEEE – Electrical & Instrumentation

- API 5L – Specification for Line Pipe

- API RP 1110 – Pressure Testing of Steel Pipelines

- ISO and DEP standards

- Nigerian Midstream and Downstream Petroleum Regulatory Authority (NMDPRA) requirements

## Safety Philosophy

Safety is a primary design consideration. The FEED will incorporate:

- Adequate pipeline wall thickness and design factors

- Block valve spacing for isolation

- Emergency shutdown philosophy

- Leak detection and monitoring

- Design for safe pigging and Maintenance operations

## Operability and Maintainability

The pipeline system will be designed to:

- Allow routine pigging operations

- Enable sectional isolation

- Facilitate inspection, testing, and repair

- Minimize operational downtime during tie-in activities

## Focus of FEED

The primary focus of the FEED is to develop a technically robust, safe, operable, and cost-effective design for the OKNU–BBOU 20” × 85 km gas pipeline that will enable informed investment decisions and seamless transition into the EPC phase. The FEED will provide sufficient engineering definition to minimize project risks related to cost, schedule, constructability, operability, and future expansion.

The FEED shall focus on:

- Confirming the technical feasibility of the proposed pipeline system

- Optimizing pipeline sizing and configuration

- Incorporating provisions for future tie-ins and capacity expansion

- Ensuring alignment between technical design and commercial assumptions

- Producing EPC-ready documents with minimal scope gaps

## Flow Assurance/Pipe Sizing

Flow assurance studies shall be undertaken to confirm that the pipeline system can reliably transport wet natural gas under all operating scenarios, including start-up, steady-state operation, turndown, and transient conditions.

The FEED will include:

- Hydraulic simulations to determine pressure profile, velocity limits, and capacity

- Evaluation of liquid dropout, slug formation, and accumulation

- Assessment of pigging requirements for liquid and debris removal

- Verification of pipe diameter adequacy for base and future gas volumes, including SEIB, NUNR and DBUC injections

The selected pipe size shall ensure stable flow, minimize operational risks, and maintain sufficient margin for future throughput increases without major modifications.

## Value Engineering

Value engineering shall be systematically applied throughout the FEED to optimize capital and operating costs without compromising safety, integrity, or operability.

Key value engineering considerations include:

- Optimization of pipeline diameter and wall thickness

- Rationalization of valve spacing and facilities

- Selection of cost-effective materials and coatings

- Minimization of above-ground facilities while maintaining operability

- Alignment of design margins with applicable codes and standards

Value engineering workshops will be conducted at appropriate stages of the FEED to identify and evaluate cost-saving opportunities.

## Material Selection

Material selection shall be based on service conditions, mechanical requirements, corrosion risks, constructability, and lifecycle cost considerations.

The FEED shall:

- Specify line pipe material (API 5L X70 PSL 2) suitable for wet gas service

- Define corrosion allowance and internal corrosion mitigation measures

- Specify external coatings (3LPE) and cathodic protection systems

- Select materials for valves, fittings, and tie-in facilities in accordance with applicable standards

Material selection shall ensure long-term integrity and compliance with regulatory requirements.

## Technical Safety

Technical safety shall be embedded into the design philosophy to ensure the protection of personnel, assets, and the environment.

The FEED will address:

- Pipeline integrity and failure prevention

- Block valve spacing and isolation philosophy

- Emergency shutdown and depressurization concepts

- Fire and explosion risk mitigation

- Compliance with safety distances and codes

Formal safety studies such as HAZID, HAZOP, and SIL assessments shall be conducted as part of the FEED.

## Gas Pressure Boosting

The FEED shall assess the need for gas pressure boosting to meet delivery pressure requirements at BBOU under all operating scenarios.

This assessment will include:

- Evaluation of inlet pressure from OKNU and third-party tie-ins

- Hydraulic profile and pressure drop analysis

- Determination of whether compression is required at FEED stage or deferred

- Provision for future installation of compression facilities if required

## Electric Power

Electric power requirements for pipeline facilities shall be assessed and defined during FEED.

The design shall consider:

- Power requirements for valves, RTUs, metering systems, and communication equipment

- Availability of grid power versus alternative sources (solar, generators)

- Reliability and redundancy requirements

- Compliance with applicable electrical standards

## Ergonomics

Ergonomic considerations shall be incorporated to ensure safe and efficient operation and Maintenance.

The FEED shall:

- Ensure safe access to valves, instruments, and equipment

- Provide appropriate working platforms and clearances

- Minimize manual handling risks

- Comply with human-factor engineering principles

## Operations Assurance

The pipeline system shall be designed to ensure reliable and uninterrupted operations throughout its design life.

Operations assurance considerations include:

- Ease of pigging and maintenance

- Clear operational procedures

- Redundancy where required

- Minimization of downtime during tie-in activities

## Security, Fire Protection and Accessibility

Security considerations shall be addressed to protect the pipeline and facilities from sabotage, theft, and unauthorized access.

The FEED shall consider:

- Location-specific security risks

- Physical security measures at above-ground facilities

- Integration with surveillance and monitoring systems

- Alignment with operator security policies

Fire protection measures shall be incorporated in accordance with applicable codes and standards.

The FEED shall ensure:

- Adequate fire protection for above-ground facilities

- Clear access routes for emergency response

- Compliance with safety spacing requirements

- Integration with emergency shutdown systems

## Survey

Comprehensive survey activities shall be undertaken to support detailed routing, design, and constructability planning. The FEED shall incorporate:

- Desktop route reconnaissance studies

- Topographic surveys along the proposed corridor

- Geotechnical investigations at regular intervals and at major crossings

- Bathymetric surveys for river crossings

- Utility and third-party infrastructure mapping

- Right-of-Way and environmental constraint mapping

Survey data shall form a critical input into pipeline alignment sheets, crossing methodology selection, stability analysis, and foundation design.

## Gas Availability

Gas availability assumptions shall be confirmed to ensure alignment with pipeline capacity and design.

The FEED shall:

- Review production profiles from OKNU, SEIB, NUNR and DBUC

- Confirm gas quality and composition

- Define operating scenarios for peak and minimum flow

## Surveillance

Pipeline surveillance requirements shall be defined to ensure integrity and security.

This includes:

- Routine inspection and monitoring

- Integration with SCADA and leak detection systems

- Patrol and inspection strategies

## SCADA system and Field Logistics

The FEED shall define a SCADA system to enable centralized monitoring and control of the pipeline.

The SCADA system shall provide:

- Real-time monitoring of pressure, flow, and temperature

- Remote operation of valves

- Alarm and event management

- Leak detection and data logging

Field logistics considerations shall be incorporated to ensure constructability and operational efficiency.

The FEED shall address:

- Access roads and construction camps

- Material transportation and storage

- Coordination with local communities

- Environmental and social constraints

# SCOPE OF WORK AND FEED PROCEDURE

## Summary Scope of Work

The scope of work for the FEED of the 20” × 85 km OKNU–BBOU Gas Pipeline for the DSV Gas Hub at Akabel shall cover all engineering activities required to define the technical, safety, operability, constructability, and cost aspects of the pipeline system to a level suitable for EPC tendering.

The FEED scope shall include, but not be limited to:

- Development of a complete Basis of Design

- Pipeline routing and alignment definition

- Hydraulic and flow assurance studies

- Mechanical and pipeline integrity design

- Definition of tie-in facilities at OKNU, SEIB, NUNR, DBUC, and BBOU

- Design of pigging, isolation, and metering facilities

- Instrumentation, control, automation, and SCADA philosophy

- Electrical, civil, and structural design

- Safety, environmental, and security considerations

- Capital cost estimate and project execution schedule

The FEED shall be executed in a manner that minimizes technical uncertainty and facilitates a smooth transition into the EPC phase.

## Detailed Scope of Work

FEED will be fully comprehensive, and the report shall include at the minimum the following:

- Introduction & Project Overview

- Executive Summary

- Project Objectives

- Scope of Facilities

- Basis of Design

- Flow Assurance

- Pipeline Alignment

- Pigging Facilities

- Electrical Power Philosophy

- SCADA Philosophy

- Safety Studies (HAZID, HAZOP, SIL, QRA – FEED level)

- Cost Estimate (±10%)

- Project Execution Strategy

- Master Schedule (Level 3)

- Operations & Maintenance Philosophy

- Regulatory Interfaces (definition only)

- NUPRC requirements (definition / compliance mapping only)

## Scope of FEED Services

Pipeline Engineering

- Line sizing & wall thickness calculation

- Wall thickness design & material selection

- Stress analysis (installation & operational)

- Stability analysis (swamp & river crossings)

- Tie-in design at OKNU, SEIB, NUNR, DBUC, and BBOU

- Pipeline integrity management input

- Valve spacing and isolation philosophy

Flow Assurance & Process

- Hydraulic simulations

- Transient multiphase modelling

- Slug catcher sizing

- Liquid hold-up assessment

- Water separation philosophy

- Process Flow Diagrams (PFDs)

- P&IDs

- Cause & Effect diagrams

Routing & Survey

- Route selection study

- Satellite and GIS mapping

- Topographic and Geotechnical investigations

- Bathymetric survey

- Crossing methodology selection:

  - HDD

  - Micro-tunneling

  - Open-cut/cofferdam

Mechanical & Piping Engineering

- Manifolds Design

- Pig launcher & receiver systems design

- Specification of line pipe, valves, and fittings

- Materials selection and corrosion allowance

- Mechanical datasheets and specifications

Civil and Structural Engineering

- Geotechnical investigations

- Foundations for above-ground facilities

- Structural supports and pipe racks

- Access roads and site grading philosophy

Electrical Engineering

- Electrical load assessment

- Power supply philosophy

- Single line diagrams

- Area classification inputs

- Earthing and lightning protection

Corrosion Protection Engineering

- Internal corrosion mitigation philosophy

- Temporary CP (sacrificial anodes) during construction

- Permanent Impressed Current Cathodic Protection (ICCP)

- CP monitoring stations

- Coating system selection

- Corrosion allowance & mitigation philosophy

Pipeline Manifold Facilities (Each Manifold)

Each pipeline manifold should include:

- Manifold headers for SEIB, NUNR and DBUC pipeline tie-ins

- DSV check meters for OKNU-BBOU bulk flow

- RTU & Control Room / Field Auxiliary Room (FAR)

- Solar power system with ≥7 days battery autonomy

- Electrical transformer & electrical room

- Chemical (corrosion inhibitor) injection system

- Tie-in provisions for:

  - Biocide injection

  - Methanol injection

- Utility and Safety Systems:

  - Closed drain vessel & open drain tank

  - Weather shelter / guard hut

  - Gantry & lifting accessories

  - High-security fencing (Citadel / Heras type)

  - Navigation aids (aviation & marine lighting)

  - Earthing & lightning protection

  - Cold vent for small inventory trap

The level of automation and power infrastructure at each manifold shall be optimized during FEED based on operability and security requirements.

Instrumentation, Control & Automation

- Instrumentation philosophy

- PLC, RTU, and SCADA architecture

- Leak detection philosophy

- Telecom and communication systems

Safety, Health & Environment

- HAZID, HAZOP, SIL studies

- Fire protection philosophy

- Emergency shutdown philosophy

- Environmental and regulatory inputs

- Constructability risk review

- Swamp access strategy

Commercial, Cost and Scheduling

- Capital cost estimate (±10%)

- Project master schedule (Level 3)

- Risk and contingency assessment

- Lifecycle cost analysis

- EPC packaging strategy

## FEED Procedure

A detailed project-specific FEED procedure will be developed on contract award. The emphasis will be on project management to provide essential Project inputs. The FEED will be structured using pre-agreed yardsticks on schedule, milestones, deliverables, quality, cost control, and change control.

Site visits will be carried out where required to confirm already existing data or to acquire fresh data.

The steps to deliver the FEED package will include the following:

Basis For Design: Various concepts for the Pipeline and associated infrastructure will be identified, evaluated and ranked. A Concept Selection Report will be prepared detailing the selection process and the recommended/selected concept. The Concept Selection Report will form a key input into the Basis for Design document

which will outline the boundary conditions, performance criteria and the applicable standards for the selected concept.

Process: EA shall carry out detailed simulation studies – steady state and dynamic – using PIPESIM, HYSIS and OLGA software. Contractor shall perform process simulation and flow assurance for the entire pipeline system from wellheads to the GPP at Akabel.

The hydraulics and flow assurance study shall be focused on the following main items:

- Analysis shall cover the whole pipeline system.

- Analysis of the pipeline system to maintain the required production rate

- Identification of flow instabilities

- Identifications of pressure profile along the pipelines

- Identification of hydrate formation tendencies and hydrate management strategies

- Pipeline pigging and the related induced slug volume to aid slug catcher sizing

- Pipeline depressurisation

Steady State Production: The FEED shall evaluate steady-state operating conditions for the pipeline system based on forecasted gas production from OKNU and third-party tie-ins (SEIB, NUNR and DBUC).

This evaluation shall include:

- Nominal, maximum, and minimum flow cases

- Pressure and temperature profiles along the pipeline

- Confirmation of pipeline capacity to meet Gas Hub demand

- Assessment of operational margins under steady-state conditions

The steady-state analysis shall form the basis for pipeline sizing, wall thickness selection, and valve spacing.

Well Restart Capabilities: Although the OKNU–BBOU pipeline is a transmission system, the FEED shall assess restart scenarios following upstream well shutdowns or pipeline outages.

This assessment shall consider:

- Pressure build-up and transient flow behavior during restart

- Impact on downstream facilities and Gas Hub operations

- Operational procedures for controlled restart

- Potential risks associated with rapid pressurization

The objective is to ensure that pipeline restart can be achieved safely without exceeding design limits.

Hydrate Management: Given the transportation of wet gas, hydrate formation risk shall be assessed as part of the FEED.

Hydrate management considerations shall include:

- Gas composition and water content

- Operating pressure and temperature envelopes

- Identification of hydrate formation conditions

- Mitigation strategies such as pigging, insulation, or chemical injection provisions

Hydrate Management strategies shall be evaluated against seasonal seabed and ambient temperature variations. The FEED shall recommend appropriate hydrate management measures to ensure uninterrupted flow and pipeline integrity.

Pigging Requirement: The OKNU–BBOU Gas Pipeline will transport wet raw wellhead natural gas to the Akabel Gas Hub; therefore, pigging facilities are required to ensure pipeline integrity, operability, and flow assurance throughout the pipeline lifecycle.

The FEED shall define the pigging philosophy, including pig types (cleaning, batching, and intelligent pigs), pigging frequency, and operational requirements for liquid removal, debris cleaning, and internal inspection. Pig Launcher facilities shall be provided at the upstream end (OKNU), while Pig Receiver facilities shall be located at the downstream end (BBOU).

The FEED shall ensure pigging facilities are designed to accommodate all anticipated pig types and allow safe launching and receiving operations, including isolation, venting, draining, and safety systems. Provisions shall also be made to ensure uninterrupted pigging operations across tie-ins at SEIB, NUNR and DBUC.

Depressurisation: The FEED shall define the depressurisation philosophy for the pipeline to enable safe Maintenance, emergency response, and commissioning activities.

This shall include:

- Location and sizing of vent and blowdown facilities

- Controlled depressurisation rates

- Integration with emergency shutdown systems

- Compliance with safety and environmental requirements

Depressurisation philosophy shall ensure that pipeline pressure can be safely reduced without undue risk to personnel or facilities.

Mechanical: EA will commence with determination of the required mechanical equipment and confirm information on their type, size and configuration. EA will then prepare specifications and data sheets for all process and utility equipment

Civil/Structural: EA will establish the scope of civil and structural works for the project. The results of the soil investigation tests carried out by DSV and confirmed by EA will form a key input in the design. Civil/Structural specifications and layouts and will be developed.

Pipelines: EA will confirm the existing route survey reports, ESHIA study reports, and other site study reports received from DSV and provide timely feedback for adjustment where necessary.

Detailed specifications of the pipeline and associated facilities (including alignment sheets and operating and Maintenance procedures) will be prepared. The design will be handled using appropriate sections of ANSI B31 codes.

Electrical: EA will establish the power requirement in each location and ascertain the optimal power system for all the facilities. EA will then prepare electrical schedules, specifications and data sheets for main electrical equipment for the facilities. The FEED will also consider possible future expansion of the facilities, without impacting on operations and HSE.

Instrumentation, Control and Automation: EA will establish the extent of control and automation adequate for the facilities. EA will then carry out the development of all instrument engineering input to Process and Utility flow schemes PEFS; preparation of Cause and Effects diagrams; Instruments Layouts, Instrument specifications, Equipment Data Sheets and Schedules.

Possible future expansion will be taken into consideration.

Layout and Construction: EA will prepare site layout drawings, 3D models, site installation philosophy documents, and define test, pre-commissioning and commissioning philosophies.

Basic Design Engineering Package (BDEP: The BDEP package will typically contain Approved for Design deliverables like equipment specifications, P & IDs, 2D schematics, 3D models, site installation philosophy documents, preliminary procedures for equipment installation, pre- commissioning, commissioning and Maintenance.

EA will submit the final BDEP package after incorporation of COMPANY comments and acceptance of the report by COMPANY.

The BDEP package will be delivered in both hard copy and soft copy formats in the number agreed with COMPANY.

The full list of deliverables is as stated in the Tender Document.

## Key Technical Challenges and Project Risks (FEED Focus)

- Swamp constructability logistics

- Major river crossings

- CO₂ corrosion management

- Slug handling for multiphase gas

- Capacity constraint for future tie-ins

- Regulatory compliance (NUPRC & FMEnv discharge constraints)

- Security and asset protection in remote terrain

- Community and environmental permitting

- Expansion uncertainty

Mitigation strategies will be embedded in FEED.

## Key FEED Deliverables

- FEED Report

- FEED Execution Schedule and Risk Register

- Basis of Design

- Pipeline route maps and alignment sheets

- PFDs AND P&IDs

- Hydraulic and flow assurance study reports

- Geotechnical Report

- Crossing Design Report

- Mechanical and pipeline design calculations

- Pigging and isolation philosophy

- Corrosion study report

- Cathodic Protection (CP) design report

- SCADA and control philosophy

- Electrical and instrumentation philosophies

- Safety study reports

- Capital cost estimate (±10%)

- Material Take-Off (MTO)

- Project Execution Plan for EPC phase

- EPC tender documentation

- Integrity Management Philosophy

## Key FEED Deliverables Schedule

# EXECUTION STRATEGY

This section provides the framework for the proper and excellent execution of the pipelines’ FEED activities to be carried out as part of the overall project.

Epic Atlantic has relevant Project Procedures that govern the various aspects of project delivery such as project management, planning, execution, quality assurance/control, cost estimating and control, and change management.

Stated below is a summary of the execution strategy for the work. The detailed project- specific Project Procedures and Plans will be prepared on contract award drawing from Epic Atlantic’s established corporate plans and procedures, and those of DSV.

## Project Location

All FEED activities will be carried out from the Epic Atlantic’s Lagos office where the Project Team will reside while the Port Harcourt office will provide support services for site visits and liaison with 3rd parties based in Rivers and Bayelsa States.

## Manpower Resourcing / Organisation Chart

Resourcing for the work will be based on the engineering disciplines required to successfully complete it and will be assigned on a full-time and/or part-time basis. Epic Atlantic’s team will be comprised of very experienced oil and gas industry personnel with verifiable track record of high performance in the following engineering disciplines:

- Project Engineering

- Process Engineering

- Mechanical Engineering

- Pipeline Engineering

- Piping Engineering

- Civil/Structural Engineering

- Instrument & Control Engineering

- QA/QC

- Technical Safety

- Electrical Engineering

- Telecommunications Engineering

- Cost Engineering

- Materials and Corrosion Engineering

Roles and responsibilities have been defined for each of the project team members. EA’s proposed preliminary project organization structure is included with this bid. The structure illustrates the administrative and technical reporting relationships applicable to the project team, and roles and responsibilities of key personnel.

Key Personnel List

| s/n | Name | Role | Discipline | Qualifications | Accreditation | Industry Experience (Years) | CVs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Fabian Ogbonna | Project Consultant / Materials & Corrosion Specialist | Mechanical Engineer, Front End Engineer and Project Manager | M.Sc. Engineering Management B. Eng. Metallurgical and Materials Engineering | APEGGA professional membership; Member NSE, COREN | 35 |  |
| 2 | Yusuff Kazeem | Project Manager / Mechanical / Piping Engineer Specialist | Mechanical / Piping Engineer | Master’s Advanced Strategic Project Management BSc. Mechanical Engineering | American Society of Mechanical Engineers (ASME) Institution of Mechanical Engineers (IMECHE) Project Management Institute (PMI) Nigerian Society of Engineers | 17 |  |
| 3 | Tolulope Adeyemo | Lead Process Engineer | Process & Flow Assurance Engineering | B.Tech Chemical Engineering | COREN – R60292 CIPM | 14 |  |
| 4 | Maduka Ekpunobi | Project Manager | Mechanical Engineering | B.Eng. Mech Eng | COREN – R68607 MNSE, MNiMechE Competence Status – Oil & Gas Facilities - Mineral Oils (Safety) Regulations 1963 | 37 |  |
| 5 | Godwin Ibe | Lead Pipeline Engineer | Materials & Corrosion / Pipeline Engineering | B.Sc. Petroleum Eng | COREN – R5289 | 45 |  |
| 6 | Obinna Ezeagu | Lead Process & Systems Engineer | Principal Facilities / Process Engineer | MPE Masters of Process Engineering B.Eng., Petroleum Engineering | COREN – R25253 NSE - R24513 SPE - R3150922 | 18 |  |
| 7 | Basil Akpan | Process Engineer – Flow Assurance | Process Engineering | MSc Process System Engineering, B.Tech. Chemical / Petrochemical Engineering |  | 15 |  |
| 8 | William Irem | Engineering Manager | Civil / Structural Engineering | B.Eng. Civil Eng | COREN – R10878 FNICE, MPMI | 28 |  |
| 9 | Onwuka Idika | Civil Engineer & Geomatics | Civil / Structural Engineering | Master of Project Management B.Eng. Civil / Structural Eng | COREN – R14563 NSE - R 18504 Member of Nigerian Institution of Civil Engineers (NICE) | 27 |  |
| 10 | Paul Nnamah | Civil Engineer & Geomatics | Geomatics / Hydrographic Engineering | DBA (Doctor of Business Administration M. Phil Hydrographic Engineering PGD Survey and Geomatics HND Survey and Hydrography | Registered Surveyor – SURCON (Surveyors Registration Council of Nigeria) | 34 |  |
| 11 | Sylvester Ugiomoh | Lead Electrical Engineer | Electrical / Electronic / Power Systems Engineering | PGD Power Electronics Engineering HND Electrical Eng MBA Oil & Gas Mgt | COREN – R8979 | 43 |  |
| 12 | Olamoniso Joel | Lead I & C & Telecoms Engineer | Production/Maintenance Engineering Project Management | BSc. Electrical Engineering | Member, Nigerian Society of Engineers, (MNSE.) Member Institute of Electrical & Electronic Engineers (IEEE) | 47 |  |
| 13 | Prince Olukah | Lead I & C & Telecoms Designers | Instrumentation & Controls | Advance Diploma in Automation and Instrumentation HND Electrical / Electronic Engineering, |  | 29 |  |
| 14 | Lantey Johnson | Lead Materials & Corrosion | Materials & Corrosion Engineering and Management | Msc. Corrosion Engineering |  | 43 |  |
| 15 | Emiyarei Ikuru | Quality / HSE Manager | Chemical Engineering / HSSE professional | MBA Business Administration Beng. Chemical Engineering | COREN – R19623 MNSE – No.10634 MNES) - No 0433 | 20 |  |
| 16 | Inyang Effiong | Technical Safety | HSSE professional | B.Sc. Chem Eng |  | 36 |  |
| 17 | Adesola Ojesanmi | Technical Safety | HSSE professional / Environment and Regulator Consultant | Doctor of Philosophy in Applied Microbiology M.Sc. Environmental Microbiology and Bioremediation B.Sc. Microbiology | International Association for Impact Assessment, Nigerian Microbiological Society, Nigerian Environmental Society, Waste Management Society of Nigeria, Affiliate Member Energy Institute (AEI) | 18 |  |
| 18 | Olarinde Ige | Operations Readiness | Frontline operations and maintenance, operations readiness | MBA General Mgt BSc Mechanical Engineering | COREN, NSE, SPE | 36 |  |
| 19 | Gibson Okeke | Constructability / Value Engineering Review Manager | Mechanical Engineering / project management, appraisal engineering | BSc Mechanical Engineering | COREN | 47 |  |
| 20 | Obima Oragwu | Project Services Manager | Geology / Geophysics | B. Sc. Geology, Ph. D Geophysics, M. Sc. Geology, |  | 24 |  |
| 21 | Chijioke Anozie | Process & Piping Engineer | Process Engineer, Quality Assurance / Quality Control Engineer | B.Eng. Petroleum Engineering | SPE, NSE | 4 |  |
| 22 | Osaze Omonjahio | IT Support | Information Technology, Network Engineer, Data Analyst, Data Scientist | B.Eng. Petroleum Engineering | SPE, NSE | 12 |  |
| 23 | David Oyekunle | Dashboard Engineer / Document Control | Mechatronics Engineering | B.Eng. Mechatronics Engineering | NSE | 1 |  |
| 24 | Aloy Duru | Project Director | Chemical Engineering / Environmental Economics | B.Sc. Chem Eng PG Certificate – Environmental Economics & Policy Analysis | FNSE COREN – R7580 Competence Status – Oil & Gas Facilities - Mineral Oils (Safety) Regulations 1963 | 44 |  |

## Communication

Communications and interactions with DSV will be governed by the terms, conditions, and procedure(s) as stated in the Tender Document and/or to be agreed with COMPANY on contract award.

## Documentation

Documentation, Document Structure & Numbering System, Document Delivery Register and Document Control Procedures will be properly defined and agreed with client, as these will enhance the effectiveness and efficiency of project execution and asset management.

Drawing procedures shall be agreed with DSV before start of work. The objective of adopting this procedure is to achieve consistency and a uniform level of quality in the deliverables.

## Change Control / Quality

Proper Management System will be instituted to address changes, technical queries, deviation requests, reviews, HAZOP, verification and approval of design documents & drawings, etc., and will follow multidisciplinary approach.

Quality of work will be managed in a structured manner, using Epic Atlantic’s Quality Management System and following relevant national and international standards.

## Design Review

At pre-planned stages of the FEED, formal documented reviews will be conducted.  The reviews shall involve all functions concerned, as well as other specialist personnel. Design reviews will be carried out to confirm progress, verify quality, and identify problem areas.  This will include discipline and inter-disciplinary checks, HAZOP, and milestone reviews and will involve in-house and external/3rd party subject matter experts.

## Design Software

Specialty Software to be used includes the latest versions of the following:

- AutoCAD / AutoCAD Plant 3D / REVIT

- HYSYS

- Caesar II

- PDMS / E3D

- STAAD

- PROTA

- SACS

- ArcGIS

- PIPESIM

- OLGA

- SOLID WORKS

  - Risk Management Approach

- Structured stage-gated design reviews

- Option screening matrix

- Value engineering workshops

- Constructability review with swamp logistics specialists

- Stakeholder engagement with regulators

# PROJECT EXECUTION AND ADMINISTRATIVE FRAMEWORK

# Progress Reporting

Progress reporting will be through weekly and monthly progress reports.

For progress and man-hour reporting, the cut-off day for each week will be agreed after contract award.

# Weekly Progress Report

EA will provide DSV with a weekly progress report on the day to be agreed after contract award.

The information to be provided will, as a minimum, include the following;

- HSE, Security and Community Affairs update

- Summary on progress during period

- Planned work for next period

- Issues/Concerns

- Status of Technical Queries

# Monthly Progress Report

EA will provide a monthly report to DSV by the first Friday of each month and will include progress from the cut-off date of the previous monthly report.

The information to be provided will include as a minimum:

    - HSE, Security and Community Affairs update

    - Summary on progress during period

    - Planned work for next period

    - Issues/Concerns

    - Technical Queries

    - Changes/Variation status

    - Invoice Status

    - Updated Level 2 Project Schedule Performance relative to Baseline

    - Document Register

    - Status of Deliverables

# Progress Review Meetings

The frequency of progress meetings between The Company and Epic Atlantic will be determined after contract award. A bi-weekly progress meeting is suggested.

# Planning – Scheduling and Control

The project schedule will be maintained at Level 3 showing details of project activities. A project schedule at Level 2 will be maintained by showing summary of the Level 3 schedule and will be presented to The Company for reporting purposes.

Both the weekly and monthly progress reports will contain a weekly and a monthly look ahead respectively. Looking ahead will be a guide for monitoring progress at a high level for the next reporting duration.

Project Schedule

| Phase | Description | Duration (Weeks) |
| --- | --- | --- |
| 1 | Project Kick-off, Mobilization & Data Collection | 2 |
| 2 | Surveys and Field Investigations | 6 |
| 3 | FEED, Design and HSE | 14 |
| 4 | Optimization and Costing | 6 |
| 5 | EPC Tender Package and Final Documentation | 4 |
| Total FEED Duration |  | 32 Weeks |

# Client Inputs Required

The following inputs shall be provided by the Employer:

- Gas composition and production forecasts

- Tie-in locations and capacities (SEIB, NUNR and DBUC)

- Site access and route constraints

- Applicable standards and specifications

- Regulatory and third-party interface requirements

- Existing survey and geotechnical data (if available)

# FEED Assumptions and Exclusions

Assumptions

- Gas quality and flow rates remain within defined limits

- Right-of-Way (RoW) access is achievable

- No major route re-alignment during FEED

- FEED cost estimate accuracy ±10%

- Geotechnical data to be confirmed during FEED

Exclusions

The following items are excluded from the FEED scope and shall be addressed during subsequent project phases or under separate contracts.

- Detailed EPC engineering

- Procurement and construction activities

- ESIA approval and permitting

- Vendor selection and contract negotiation

- AFC drawings and construction documentation

- Land acquisition compensation and permitting fees

# Value Proposition

Our FEED approach ensures:

- Optimized pipeline diameter

- Reduced lifecycle cost

- Robust corrosion management

- Future-proof tie-in strategy

- Minimized environmental footprint

- Constructability-driven engineering

- Bankable cost certainty

# Conclusion

The proposed FEED execution methodology provides a structured and technically robust approach for the successful delivery of the OKNU–BBOU Gas Pipeline project. The design philosophy, engineering processes, and quality assurance measures outlined herein ensure that all project requirements will be met in accordance with applicable standards and best industry practices. This proposal ensures commercial clarity, cost efficiency and risk-managed execution.

Epic Atlantic Limited is confident in its ability to deliver a comprehensive FEED package that supports efficient project execution and seamless transition into the EPC phase.

# FEED EXECUTION SCHEDULE

# Overall Phasing

| Phase | Description | Duration (Weeks) | Output |
| --- | --- | --- | --- |
| 1 | Project Kick-off, Mobilization & Data Collection | 2 | Kick-off & BOD Approval |
| 2 | Surveys and Field Investigations | 6 | Survey Data |
| 3 | FEED, Design and HSE Studies | 14 | 60% Design Review |
| 4 | Optimization and Cost Estimate Development | 6 | 90% Design Review |
| 5 | FEED Deliverables and FID Package | 4 | Final FEED Close-Out |
| Total FEED Duration |  | 32 Weeks |  |

# Detailed Week-By-Week Structure

Phase 1 – Kick-Off, Mobilization and Data Collection (Weeks 1–2)

Activities:

- Contract award & mobilization

- Project execution plan

- Data collection & verification

- Stakeholder alignment workshop

- FEED Basis of Design

Milestone: Project Kick-off & Basis of Design Approval

Phase 2 – Surveys and Field Investigations (Weeks 3–8)

Activities:

- Topographical Survey- (Weeks 3–5)

- Bathymetric Survey (Nun River & creeks)- (Weeks 3–5)

- Geotechnical Investigation- (Weeks 4–6)

- Soil Resistivity Survey- (Weeks 5–7)

- Environmental Baseline Study- (Weeks 6-8)

Deliverables:

- Alignment sheets (draft)

- Geotechnical interpretive report

- River crossing data

- Preliminary constructability assessment

Milestone: Survey Data (Week 8)

Phase 3 – Detailed Feed Engineering and Studies (Weeks 9–22)

Activities:

Process & Flow Assurance (Weeks 9–15)

- Steady-state hydraulic modelling

- Transient multiphase simulation

- Slug catcher sizing & location optimization

- Turndown & ramp-up analysis

- Future tie-in scenarios

Mechanical & Pipeline Engineering (Weeks 12–18)

- Wall thickness calculations

- Material selection (CO₂ corrosion consideration)

- Corrosion modelling

- Pigging philosophy

- Block valve spacing

- Crossing methodology selection (HDD vs micro-tunnel vs trench)

Manifold & Facilities Engineering (Weeks 16–22)

- PFDs & P&IDs

- Plot plans

- Utility systems

- Chemical injection design

- Solar power & control system design

Milestone: 60% Design Review (Week 22)

Phase 4 – Optimization and Cost Development (Weeks 23–28)

Activities:

- Class III CAPEX estimate development (Week 23-25)

- Quantity take-off (MTO) (Week 23-24)

- OPEX forecast (Week 24-26)

- Lifecycle cost analysis (Week 25-27)

- Risk-adjusted cost modelling (Week 26-28)

- Value engineering workshop (Week 26)

- Tie-in option economic comparison (Week 24-26)

Milestone: 90% Design Review (Week 28)

Phase 5 – FEED Deliverables and FID Package (Weeks 29–32)

Activities:

- FEED design report (Week 29-31)

- Technical specifications (Week 29-30)

- Schedule Level 3 (EPC basis) (Week 29-31)

- Management review (Week 29-30)

- EPC tender documentation (Week 29-32)

- Final FEED submission & FID readiness package (Week 30-32)

Milestone: Final FEED Close-Out (Week 32)

# Key Reviews

| S/N | Review Stage | Week | Focus |
| --- | --- | --- | --- |
| 1 | Kick-off | 2 | Basis of Design |
| 2 | 30% Review | 8 | Concept Validation |
| 3 | 60% Review | 22 | Technical Maturity |
| 4 | 90% Review | 28 | Cost and Constructability |
| 5 | Final | 32 | EPC-Ready Package |

# Critical Path Items

- Geotechnical investigation in swamp terrain

- Nun River crossing methodology selection

- Slug catcher configuration decision

- Diameter confirmation via flow assurance

- Midline tie-in hydraulic validation

- CAPEX development for major crossings

# Deliverable Maturity Profile

| S/N | Deliverable | 30% | 60% | 90% | Final |
| --- | --- | --- | --- | --- | --- |
| 1 | Basis of Design | ✓ | - | - | - |
| 2 | Hydraulic Report | Draft | Rev A | Final | - |
| 3 | PFD and P&ID | Draft | Rev A | Rev B | IFC (FEED) |
| 4 | Alignment Sheets | Draft | Rev A | Rev B | Final |
| 5 | Cost Estimate | - | Draft | Class III | Final |
| 6 | Risk Register | Draft | Updated | Final | - |

# Summary of Proposed FEED Execution Schedule

# Schedule Summary

Total Duration: 32 Weeks
Estimate Class: Class III (±10%)
Execution Strategy: Stage-gated with structured technical and commercial reviews

Concurrent Activities: Yes
Estimated Engineering Hours: To be aligned with commercial schedule
Schedule Confidence Level: High, subject to timely survey execution and stakeholder approvals

# COMMERCIAL PROPOSAL (INTRODUCTION AND OBJECTIVES)

# Purpose of the Commercial Proposal

The Commercial Proposal covers the execution of the Front-End Engineering Design (FEED) for the 20” × 85 km OKNU–BBOU Gas Pipeline for the Akabel Gas Hub Project, in accordance with the Technical Proposal and Scope of Work defined herein.

It provides the basis for commercial evaluation and enables informed decision-making by the Client through a structured presentation of costs, assumptions, and associated risks. It also ensures alignment between technical deliverables and commercial commitments, thereby minimizing ambiguity during project execution.

# Objectives of the Proposal

The key objectives of this Commercial Proposal are to:

- Provide a transparent and defensible cost structure for the FEED scope

- Establish a clear and practical payment framework aligned with project milestones

- Define contractual principles to guide project execution

- Identify commercial risks and propose mitigation strategies

- Support budget approval and investment planning for the project

# Project Scope Alignment

This proposal strictly covers the FEED activities associated with the 20” × 85 km OKNU–BBOU Gas Pipeline segment. The commercial estimate has been developed specifically for this defined scope using a detailed, discipline-based approach.

All pricing presented herein reflects only the OKNU–BBOU pipeline scope, ensuring that the estimate is realistic, avoids inclusion of unrelated project elements, and remains technically and financially representative of the defined project boundaries.

# PRICING PHILOSOPHY, BASIS AND COST DRIVERS

# Pricing Philosophy

The pricing approach adopted for this FEED proposal is based on a bottom-up, man-hour driven estimation methodology, which ensures that all engineering, project management, and support activities are adequately captured and costed.

The philosophy is centred on achieving a balance between cost competitiveness and technical integrity, ensuring that the Client receives a high-quality FEED package without unnecessary cost escalation. Discipline-specific engineering inputs are evaluated independently and then integrated into a consolidated cost model.

Benchmarking has been carried out against similar pipeline FEED projects executed within the Niger Delta region, considering environmental challenges, terrain complexity, and industry-standard engineering practices.

# Pricing Basis

The commercial estimate has been developed based on the following key parameters:

- Engineering Man-Hours: Derived per discipline based on scope complexity and deliverable requirements

- Blended Labour Rate: An average rate applied across engineering grades and disciplines to ensure simplicity and competitiveness

- Project Duration: Estimated at approximately 32 weeks, covering all FEED phases from initiation to final submission

- Scope of Deliverables: Full FEED package including design basis, engineering calculations, drawings, specifications, and cost estimates

- Location Factor: Consideration of Niger Delta terrain, including swamp conditions, river crossings, and accessibility constraints

# Key Cost Drivers

The major cost drivers influencing the FEED estimate include:

- Pipeline Engineering & Routing: Alignment optimization, wall thickness design, stress analysis, and constructability considerations

- Flow Assurance Studies: Hydraulic simulations, pressure drop analysis, and slugging assessments to ensure operational integrity

- Survey Integration: Coordination and interpretation of topographical, geotechnical, and bathymetric data

- River and Swamp Crossings: Specialized engineering for horizontal directional drilling (HDD) and other crossing methods

- Instrumentation & SCADA Design: Development of monitoring, control, and automation systems

- Project Management & Coordination: Planning, scheduling, reporting, and stakeholder engagement

These elements collectively define the engineering effort required and form the backbone of the commercial estimate.

# COMMERCIAL COST STRUCTURE AND ESTIMATION

# Cost Breakdown by Discipline

The total FEED cost has been distributed across key engineering and project support disciplines to ensure clarity and traceability. The primary contributors include:

- Pipeline & Mechanical Engineering: Responsible for pipeline design, material selection, and stress analysis

- Process & Flow Assurance: Covers hydraulic modelling and operational performance validation

- Civil & Structural Engineering: Includes supports, crossings, and structural design elements

- Electrical Engineering: Power supply systems and electrical infrastructure

- Instrumentation & SCADA: Automation, control systems, and communication architecture

- Project Management: Planning, coordination, and execution oversight

- Cost Engineering: Development of CAPEX estimates and cost validation

- Documentation & QA/QC: Preparation and review of deliverables

# PROJECT SCHEDULE AND COMMERCIAL EXECUTION

# Project Duration

The FEED execution is planned over a total duration of approximately 32 weeks, covering all phases from project initiation to final deliverables submission.

# Commercial Execution Profile

The project cost distribution follows a typical engineering curve:

- Early Phase (Weeks 1–6): Mobilization and data gathering (low-cost burn)

- Core Engineering Phase (Weeks 7–22): Intensive design activities (peak cost expenditure)

- Final Phase (Weeks 23–32): Costing, Documentation, reviews, and close-out

# Resource Loading Strategy

Engineering resources are optimized to ensure efficient utilization, with peak manpower deployment occurring during the detailed engineering phase. This approach minimizes idle time and ensures cost efficiency.

# ASSUMPTIONS, EXCLUSIONS AND RISK MANAGEMENT

# Key Assumptions

The commercial proposal is based on the following key assumptions:

- A FEED execution duration of approximately 32 weeks

- Capital cost estimate accuracy of ±10%

- Lump-sum pricing excludes regulatory approval and statutory fees

- Timely provision of Client inputs and approvals

Any deviation from these assumptions may impact cost and schedule.

# Exclusions

The following items are excluded from this proposal:

- EPC execution and construction costs

- Procurement of pipeline materials and equipment

- Construction supervision beyond FEED scope

- Vendor selection and contract negotiation

- Regulatory permit fees and statutory payments

- Community-related compensation and engagement costs

# Commercial Risk Assessment

Key risks include:

- Scope changes leading to additional engineering effort

- Delays in survey data affecting design progression

- Regulatory approval delays impacting schedule

- Additional tie-ins requiring redesign

# Contingency Provision

A contingency allowance of 10% is recommended to cover uncertainties such as minor scope changes, rework, and data gaps.

# CONTRACTUAL FRAMEWORK, LOCAL CONTENT AND VALUE PROPOSITION

# Contract Type and Commercial Structure

The FEED shall be executed on a lump-sum basis, with payments linked to agreed project milestones and deliverables.

Provisional sums shall be included for Third-Party Services and Survey Activities, while reimbursable expenses shall be treated in accordance with agreed commercial terms where applicable.

A detailed commercial cost breakdown shall be provided to the Client under separate cover, forming part of the overall commercial submission.

# Variation Management

Any changes to the agreed scope shall be managed through a formal variation process, including:

- Scope definition

- Cost implication assessment

- Schedule impact evaluation

- Client approval prior to execution

# Local Content Compliance

The project will prioritize the use of Nigerian engineering resources and local subcontractors in compliance with applicable local content regulations. This includes survey works, engineering support, and stakeholder engagement activities.

# Value Addition

The proposed approach delivers value through:

- Optimized pipeline routing to reduce costs

- Early identification of technical and commercial risks

- Efficient integration with existing infrastructure

- A structured transition pathway from FEED to EPC

# Commercial Strength & Execution Capability

The execution strategy is supported by:

- Proven experience in pipeline FEED projects

- Strong understanding of Niger Delta operating conditions

- Competitive and transparent pricing methodology

- Integrated technical and commercial delivery approach

# COMPETITIVE ADVANTAGE (WHY US) AND CONCLUSION

# Technical Strength

Epic Atlantic Limited brings strong technical expertise in pipeline FEED delivery, with proven capability in executing complex onshore pipeline projects within challenging environments such as the Niger Delta. The team possesses deep knowledge of pipeline design, flow assurance, and multidisciplinary integration required for successful FEED execution.

# Commercial Competitiveness

The proposed pricing structure is both competitive and transparent, developed using a bottom-up methodology and aligned with industry benchmarks. The cost reflects an optimal balance between affordability and the level of engineering detail required to de-risk subsequent EPC phases.

# Local Content & Execution Advantage

The project will leverage local engineering expertise and in-country resources, ensuring compliance with local content requirements while enhancing cost efficiency and execution speed. Familiarity with regional conditions further reduces project risks.

# Integrated Delivery Approach

The integration of technical and commercial planning ensures seamless execution, minimizing rework and enabling a smooth transition from FEED to EPC. Early identification of risks and optimization opportunities enhances overall project value.

# Commitment to Quality and Schedule

The project execution strategy emphasizes quality, timely delivery, and adherence to international standards. Robust project controls and governance frameworks will ensure that deliverables meet Client expectations within the agreed schedule and budget.

# Conclusion

This Commercial Proposal presents a clear, competitive, and well-structured cost framework for the execution of the OKNU–BBOU Gas Pipeline FEED. The pricing has been carefully developed to reflect project scope, engineering complexity, and prevailing industry benchmarks, while maintaining cost efficiency and execution reliability.

The proposed commercial structure, combined with a milestone-based payment plan and robust risk management approach, ensures transparency and financial control throughout the project lifecycle.

Epic Atlantic Limited remains committed to delivering value-driven engineering solutions and looks forward to partnering with the Client for the successful realization of this project.

# CORPORATE CAPABILITY AND PROJECT EXPERIENCE

# Company Profile

- Corporate Overview: Epic Atlantic Limited (EA) is a premier multidisciplinary engineering firm with over 22 years of experience in the Nigerian Oil & Gas sector. We specialize in complex midstream infrastructure, specifically swamp and land-based gas gathering systems and high-pressure transmission pipelines.

- Technical Competency: Our core strength lies in providing end-to-end FEED and Project Management Consultancy (PMC) services. For the DSV Gas Hub project, we deploy a "Center of Excellence" approach, utilizing senior-level expertise in:

  - Subsea & Pipeline Engineering: Specialized routing and on-bottom stability in deltaic terrains.

  - Process & Flow Assurance: Expertise in liquid holdup and slug management for long-distance gas transport.

  - Technical Safety: Industry-standard HAZOP/HAZID facilitation and Risk Assessment (QRA/FERA).

- Project Delivery Track Record: With operational bases in Lagos and Port Harcourt, Epic Atlantic has a proven history of delivering FEED packages that successfully transition into EPC execution. Our ISO-compliant quality management systems ensure that every deliverable—from the P&IDs to the final Cost Estimate—meets the highest international and local regulatory standards (NUPRC/FMEnv).