1. EXECUTIVE SUMMARY

This proposal defines the strategy and execution plan for the safe decommissioning and abandonment of the integrated OKNU–BBOU–ELEP–AKAB gas pipeline network, traversing the swamp and riverine terrain of the Niger Delta.

The approach adopts a hybrid strategy (Removal + Abandonment-in-Place) to:

- Ensure zero residual hydrocarbon risk

- Minimize environmental disturbance

- Optimize cost and execution feasibility

- Enable asset recovery (TAR)

The proposal is aligned with project FEED philosophy and regulatory expectations.

2. SYSTEM OVERVIEW

Pipeline Network

- Total Length: ~125 km

- Segments:

  - OKNU → BBOU (~85 km, new line)

  - BBOU → ELEP (~8 km)

  - ELEP → AKAB (~32 km trunkline)

Key Nodes

- OKNU Manifold (KP0)

- River Niger Crossing (~KP10)

- Midline Manifolds (KP38, KP66)

- BBOU (KP85)

- ELEP (KP93)

- AKAB Gas Hub (KP125)

Terrain Characteristics

- Predominantly swamp and mangrove

- Multiple river and creek crossings

- Offshore export connection to FLNG

3. DECOMMISSIONING PHILOSOPHY

Core Principles

- Safety-first (zero harm, zero release)

- Environmental protection (no inland discharge)

- Regulatory compliance

- Value optimization (TAR)

- Minimum intervention in sensitive terrain

4. KEY DECOMMISSIONING PROCESSES

4.1 Planning & Regulatory Approval

- Asset verification (as-built vs installed)

- Environmental baseline study

- Decommissioning Execution Plan (DEP)

- Engagement with regulators and communities

4.2 Shutdown & Isolation

- Controlled system shutdown

- Mechanical isolation (valves, blinds, spades)

- Electrical and SCADA deactivation

- Segmentation into manageable sections (KP-based)

4.3 Cleaning & Hydrocarbon Removal

- Depressurization and venting

- Pigging operations:

  - Cleaning pigs

  - Gauging pigs

- Condensate and sludge removal

4.4 Flushing, Drying & Inerting

- Water or chemical flushing

- Air or nitrogen drying

- Nitrogen purging to inert condition

👉 This is the most critical safety barrier

4.5 Disconnection & Segmentation

- Cutting pipeline into sections

- Disconnection at:

  - OKNU

  - KP38 & KP66 manifolds

  - BBOU / ELEP

  - AKAB

4.6 Execution Decision

Each segment evaluated for:

- Removal or

- Abandonment-in-Place

4.7 Pipeline Removal (Where Applicable)

- Excavation using swamp-compatible equipment

- Lifting and transport

- Scrap recovery and reuse

4.8 Waste Management

- Segregation:

  - Scrap steel

  - Hazardous waste

  - Contaminated soils

- Certified disposal

4.9 Site Restoration

- Backfilling and grading

- Mangrove restoration

- Erosion control

- Post-restoration monitoring

5. KEY ABANDONMENT ACTIVITIES

Applied where removal is impractical or environmentally damaging.

5.1 Cleaning to Regulatory Standard

- Internal cleaning to hydrocarbon-free condition

- Verification via pigging and sampling

5.2 Permanent Isolation

- Installation of:

  - Blind flanges

  - End caps

- Removal of above-ground tie-ins

5.3 Filling & Stabilization

Swamp / Onshore

- Water filling (treated/inhibited)

- Cement grouting (where required)

River / Offshore

- Seawater flooding

- Natural sediment stabilization

- Rock dumping (if necessary)

5.4 Cathodic Protection Decommissioning

- CP system shutdown

- Removal or abandonment of anodes

- Electrical isolation

5.5 Long-Term Integrity Assurance

- Corrosion risk evaluation

- Monitoring requirements (if mandated)

- Documentation of abandoned sections

5.6 Marking & Records

- GIS update and pipeline status change

- Surface markers (where required)

- Regulatory documentation

6. KP-BASED EXECUTION STRATEGY

| Segment | Strategy | Justification |
| --- | --- | --- |
| KP0 (OKNU) | Remove | High-value facilities (TAR) |
| KP0–10 | Mixed | Accessible sections removable |
| KP10 (River Niger) | Abandon | High environmental risk |
| KP10–38 | Abandon (majority) | Deep swamp |
| KP38 Manifold | Remove | Strategic node |
| KP38–66 | Mixed | Access-dependent |
| KP66 Manifold | Remove | Future tie-in |
| KP66–85 | Mixed | Near infrastructure |
| BBOU / ELEP | Remove | Operational hubs |
| ELEP–AKAB | Case-by-case | Depends on reuse |
| Offshore line | Abandon | Industry standard |

7. SPECIAL NIGER DELTA CONSIDERATIONS

- Swamp mobility constraints → use low-ground-pressure equipment

- Mangrove sensitivity → prioritize abandonment

- River crossings → avoid disturbance

- Community engagement → critical success factor

- Seasonal flooding → schedule optimization

8. SCHEDULE (INTEGRATED)

| Phase | Duration |
| --- | --- |
| Planning & Approvals | 4–6 months |
| Engineering & Preparation | 3–4 months |
| Cleaning & Isolation | 2–3 months |
| Removal / Abandonment | 6–10 months |
| Restoration | 3–6 months |

Total Duration: ~12–18 months

9. COST ESTIMATE (ORDER OF MAGNITUDE)

| Component | Cost (₦ Billion) |
| --- | --- |
| Engineering & Approvals | 2.5 – 4.0 |
| Cleaning & Inerting | 3.0 – 5.0 |
| Removal Activities | 15 – 25 |
| Abandonment Activities | 5 – 10 |
| Restoration | 4 – 7 |
| Total | 29 – 49 Billion |

10. RISK MANAGEMENT

| Risk | Mitigation |
| --- | --- |
| Residual hydrocarbons | Multi-stage pigging + inerting |
| Environmental damage | Abandonment strategy |
| Swamp instability | Specialized equipment |
| Regulatory delays | Early engagement |
| Community issues | Stakeholder plan |

11. CONCLUSION

This proposal delivers a balanced, execution-ready decommissioning strategy that:

- Ensures safe hydrocarbon-free pipeline retirement

- Minimizes environmental impact in the Niger Delta

- Optimizes cost through hybrid removal/abandonment

- Maximizes asset recovery value

NEXT STEP (HIGHLY RECOMMENDED)

If you want to elevate this to client submission standard, I can:

- Convert this into a fully formatted proposal document (Word/PDF)

- Build a PowerPoint pack with visuals + KP map

- Add a Gantt chart aligned to your FEED timeline

- Or produce a commercial BOQ with detailed line items (Nigeria benchmarks)

Top of Form

Bottom of Form

Alright—here’s a complete, boardroom-ready package covering all three:

1. POWERPOINT SLIDE DECK (CONTENT + DESIGN STRUCTURE)

(You can paste this directly into PowerPoint — I’ve structured each slide with title + content + visual cues)

Slide 1 – Title Slide

Title:
Pipeline Decommissioning Strategy
OKNU–BBOU–ELEP–AKAB Gas System

Subtitle:
Integrated Removal & Abandonment Plan

Slide 2 – Executive Overview

Content:

- End-to-end decommissioning of ~125 km pipeline network

- Hybrid strategy: Removal + Abandonment-in-Place

- Designed for:

  - Niger Delta swamp terrain

  - Regulatory compliance

  - Cost optimization

Visual: 4 icons → Safety | Environment | Cost | Compliance

Slide 3 – Process Flow

(Use horizontal flow arrows)

Flow:
Planning → Engineering → Shutdown → Cleaning → Segmentation → Decision → Execution → Restoration → Close-out

Slide 4 – Removal vs Abandonment Strategy

Left Column: Removal

- Facilities & manifolds

- Accessible shallow sections

- Future development zones

Right Column: Abandonment

- River crossings

- Deep swamp sections

- Offshore pipelines

Slide 5 – KP-Based Execution Strategy

(Insert simple linear diagram KP0 → KP125)

- KP0–10: Partial removal

- KP10 (River Niger): Abandon

- KP10–66: Selective abandonment

- KP38 & KP66: Remove (nodes)

- KP85–125: Mixed strategy

Slide 6 – Decision Framework

(Flowchart style)

- Environmental sensitivity?

- Access feasibility?

- Cost vs risk?
→ Decision: Remove / Abandon

Slide 7 – Schedule

Timeline bar:

- Engineering: 4–6 months

- Cleaning: 2–3 months

- Execution: 6–10 months

- Restoration: 3–6 months

Slide 8 – Cost Overview

- Total Estimate: ₦29B – ₦49B

- Key drivers:

  - Terrain

  - Removal scope

  - Restoration requirements

Slide 9 – Value Optimization

- Hybrid strategy reduces cost

- Asset recovery (TAR)

- Reduced environmental liability

Slide 10 – Key Risks & Controls

| Risk | Control |
| --- | --- |
| Residual gas | Pigging + inerting |
| Swamp instability | Specialized equipment |
| Environmental damage | Abandonment strategy |

Slide 11 – Conclusion

- Safe

- Compliant

- Cost-optimized

- Execution-ready

2. VISUAL MAP (KP0–125 STRATEGY OVERLAY)

You can recreate this easily in PowerPoint or Visio.

Linear Map Representation

OKNU (KP0)
│
├── KP10 → River Niger Crossing → [ABANDON]
│
├── KP38 → Midline Manifold → [REMOVE]
│
├── KP66 → Midline Manifold → [REMOVE]
│
├── BBOU (KP85) → [REMOVE]
│
├── ELEP (KP93) → [REMOVE]
│
└── AKAB (KP125) → Gas Hub

Color Coding (Important)

- 🔴 RED → Remove

- 🟢 GREEN → Abandon

- 🟡 YELLOW → Mixed / Conditional

Segment Strategy Overlay

| Segment | Strategy |
| --- | --- |
| KP0–10 | 🟡 Mixed |
| KP10 Crossing | 🟢 Abandon |
| KP10–38 | 🟢 Mostly abandon |
| KP38 Node | 🔴 Remove |
| KP38–66 | 🟡 Mixed |
| KP66 Node | 🔴 Remove |
| KP66–85 | 🟡 Mixed |
| Facilities | 🔴 Remove |

3. FULL PROPOSAL PACK STRUCTURE (MERGED & READY)

This is your final submission structure—you can compile into Word or PDF.

SECTION 1 – EXECUTIVE SUMMARY

- Project overview

- Decommissioning objective

- Hybrid strategy

SECTION 2 – SYSTEM DESCRIPTION

- OKNU–BBOU–ELEP–AKAB pipeline

- Length, diameter, facilities

- Terrain (swamp, river, offshore)

SECTION 3 – DECOMMISSIONING PHILOSOPHY

- Safety-first approach

- Removal vs abandonment principles

- TAR (asset recovery) integration

SECTION 4 – KEY PROCESSES

- Shutdown & isolation

- Cleaning & inerting

- Segmentation

- Execution

SECTION 5 – ABANDONMENT METHODOLOGY

- Cleaning standards

- Filling (water / grout)

- Stabilization

- Long-term integrity

SECTION 6 – SEGMENT STRATEGY (KP-BASED)

- KP0–125 breakdown

- River crossing approach

- Facility removal plan

SECTION 7 – AS-BUILT & DATA REQUIREMENTS

- Drawing checklist

- Data room structure

- Critical gaps

SECTION 8 – SCHEDULE

- Integrated timeline (12–18 months)

SECTION 9 – COST ESTIMATE

- ₦29B – ₦49B range

- Cost drivers

- Optimization levers

SECTION 10 – RISK MANAGEMENT

- Environmental

- Technical

- Execution

SECTION 11 – ENVIRONMENTAL & REGULATORY

- Compliance strategy

- Restoration approach

- Stakeholder engagement

SECTION 12 – CONCLUSION

- Safe execution

- Regulatory alignment

- Cost efficiency

FINAL EXECUTIVE POSITIONING

What you now have is a complete, investment-grade narrative:

- Slide deck → for decision makers

- Map → for clarity and alignment

- Full proposal → for submission and execution

If you want the last mile polish:

I can next:

- Design this into a fully formatted PowerPoint file (consulting-grade visuals)

- Create a proper geographic map (satellite-style with route overlay)

- Or build a financial model (NPV of removal vs abandonment scenarios)

Top of Form

Bottom of Form

do all three

Below are all three deliverables, structured so you can drop them straight into your proposal pack or slides for the OKNU–BBOU–ELEP–AKAB pipeline system.

1. PROCESS FLOW DIAGRAM (EXECUTIVE VISUAL – SLIDE READY)

Writing

PIPELINE DECOMMISSIONING PROCESS FLOW

PLANNING & APPROVAL
→ Asset Verification
→ Regulatory Engagement (NUPRC / NMDPRA / FMEnv)
→ Environmental Baseline & Risk Assessment

⬇

ENGINEERING & PREPARATION
→ Decommissioning Execution Plan (DEP)
→ HAZID / HAZOP
→ Work Packs & Method Statements

⬇

SHUTDOWN & ISOLATION
→ Controlled Shutdown
→ Mechanical Isolation (Valves / Blinds)
→ Electrical & SCADA De-energization

⬇

CLEANING & INERTING
→ Depressurization
→ Pigging (Cleaning + Gauging)
→ Flushing & Chemical Cleaning
→ Nitrogen Purging

⬇

DISCONNECTION & SEGMENTATION
→ Cut & Cap Sections
→ Disconnect from OKNU / BBOU / ELEP / AKAB
→ Prepare Sections for Removal or Abandonment

⬇

EXECUTION DECISION
→ REMOVE | ABANDON-IN-PLACE

⬇

PIPELINE REMOVAL (IF SELECTED)
→ Excavation (Swamp Methods)
→ Lifting & Transportation
→ Scrap / Reuse Handling

⬇

ABANDONMENT (IF SELECTED)
→ Final Cleaning Verification
→ Flooding / Grouting / Stabilization
→ Permanent Isolation

⬇

WASTE MANAGEMENT
→ Segregation (Scrap / Hazardous / Soil)
→ Certified Disposal

⬇

SITE RESTORATION
→ Backfilling & Regrading
→ Mangrove Restoration
→ Erosion Control

⬇

CLOSE-OUT
→ As-Left Documentation
→ Regulatory Sign-Off
→ Lessons Learned

2. DECISION TREE – REMOVAL vs ABANDONMENT

Writing

PIPELINE DECOMMISSIONING DECISION TREE

START: PIPELINE SEGMENT IDENTIFIED

⬇

Q1: Is the segment in a sensitive environment?
(Swamp / River / Offshore / Mangrove)

→ YES → Proceed to Q2
→ NO → Proceed to Q3

⬇

Q2: Will removal cause significant environmental damage?
→ YES → ABANDON IN PLACE
→ NO → Proceed to Q3

⬇

Q3: Is the segment located in a congested or developable area?
(Facilities / Future projects / Urban proximity)

→ YES → REMOVE PIPELINE
→ NO → Proceed to Q4

⬇

Q4: Is the pipeline shallow and easily accessible?
→ YES → REMOVE PIPELINE
→ NO → Proceed to Q5

⬇

Q5: Is abandonment more cost-effective with acceptable risk?
→ YES → ABANDON IN PLACE
→ NO → REMOVE PIPELINE

⬇

FINAL VALIDATION
→ Regulatory Approval (NUPRC / FMEnv)
→ Environmental Acceptability
→ Long-Term Liability Assessment

3. INTEGRATION INTO FINAL PROPOSAL PACK (COST + SCHEDULE LINKAGE)

3.1 Integrated Execution Strategy (OKNU–BBOU–ELEP–AKAB)

Segment-Based Approach

| Segment | Strategy | Rationale |
| --- | --- | --- |
| OKNU Facilities (KP0) | Remove | High-value equipment (TAR) |
| KP0–KP10 (Swamp) | Partial removal | Accessibility varies |
| River Niger Crossing (~KP10) | Abandon | High environmental risk |
| KP10–KP38 | Selective abandonment | Deep swamp terrain |
| KP38 Manifold | Remove | Future tie-in conflict |
| KP38–KP66 | Mixed | Depends on access |
| KP66 Manifold | Remove | Strategic node |
| KP66–KP85 (BBOU) | Partial removal | Near infrastructure |
| BBOU / ELEP Facilities | Remove | Integration hubs |
| ELEP–AKAB trunkline | Case-by-case | Depends on reuse |
| Offshore FLNG line | Abandon | Standard offshore practice |

3.2 Integrated Schedule (Aligned to Decommissioning Phases)

| Phase | Duration | Key Output |
| --- | --- | --- |
| Planning & Approval | 4–6 months | Permits secured |
| Engineering & Prep | 3–4 months | DEP finalized |
| Cleaning & Isolation | 2–3 months | Hydrocarbon-free system |
| Removal / Abandonment | 6–10 months | Pipeline retired |
| Restoration | 3–6 months | Site reinstated |

Total Duration: ~12–18 months

3.3 Cost Integration (Linked to Strategy)

| Activity | Cost Driver |
| --- | --- |
| Cleaning & Inerting | Pigging, chemicals |
| Removal | Excavation, logistics |
| Abandonment | Filling, stabilization |
| Restoration | Environmental sensitivity |
| TAR Recovery | Cost offset opportunity |

3.4 Value Optimization Lever

- Maximize abandonment in deep swamp & offshore → reduces cost by ~30–50%

- Maximize removal at facilities → enables asset recovery (TAR)

- Hybrid strategy = optimal lifecycle cost + regulatory acceptance

EXECUTIVE CLOSE

This integrated approach ensures:

- Safety: Fully cleaned and inert system

- Environmental Protection: Minimal disturbance in Niger Delta

- Cost Efficiency: Right balance of removal vs abandonment

- Value Recovery: Preservation of high-value assets

If you want the final polish

I can now:

- Turn this into a fully designed PowerPoint deck (icons, colors, layout)

- Add a visual map (KP0–125 with strategy overlay) ← very powerful for boardrooms

- Or merge everything into your complete decommissioning submission pack (ready for client)

Top of Form

Bottom of Form

Below is a boardroom-ready Decommissioning Proposal tailored to your OKNU–BBOU–ELEP–AKAB integrated gas pipeline system. It aligns with Niger Delta realities, regulatory expectations, and your FEED philosophy.

PROPOSAL FOR PIPELINE DECOMMISSIONING

OKNU–BBOU–ELEP–AKAB GAS PIPELINE NETWORK

1. EXECUTIVE SUMMARY

This proposal presents a structured, safe, and environmentally compliant approach for the decommissioning of pipelines and associated facilities within the OKNU–BBOU–ELEP–AKAB gas transmission system.

The objective is to:

- Safely retire pipeline assets at end-of-life or during system reconfiguration

- Minimize environmental and social impact in sensitive Niger Delta swamp terrain

- Preserve recoverable value through Technical Asset Recovery (TAR)

- Ensure full compliance with NUPRC, NMDPRA, and FMEnv regulations

The decommissioning philosophy integrates:

- Plug-and-Play asset preservation (where applicable)

- Phased execution strategy

- Risk-based methodology (environmental + integrity-driven)

2. SCOPE OF DECOMMISSIONING

The scope covers the full pipeline network and associated infrastructure:

2.1 Pipelines

- OKNU–BBOU Pipeline (~85 km, 20”–24”)

- BBOU–ELEP Pipeline (~8 km, 20”)

- ELEP–AKAB Trunkline (~32 km, 28”–32”)

- Offshore gas export line to FLNG (~20–25 km)

2.2 Facilities

- OKNU inlet manifold

- Midline manifolds (KP 38, KP 66)

- BBOU and ELEP manifolds

- AKAB Gas Hub tie-in facilities

- Slug catchers (inlet, midline, PLEM)

- Metering and pigging stations

2.3 Ancillary Systems

- Cathodic protection systems

- SCADA / control systems

- Pipeline supports and crossings

- River/creek crossing installations

3. DECOMMISSIONING PHILOSOPHY

A hybrid approach will be adopted:

3.1 Key Principles

- Safety First: Zero harm to personnel and communities

- Environmental Protection: No uncontrolled discharge or contamination

- Regulatory Compliance: Full adherence to Nigerian laws

- Value Optimization: Recover high-value materials and equipment

- Minimal Footprint: Reduce disturbance in swamp terrain

3.2 Decommissioning Options

Each pipeline segment will be assessed and assigned one of the following:

| Option | Description | Applicability |
| --- | --- | --- |
| Full Removal | Complete excavation and removal | Sensitive areas, river crossings |
| Partial Removal | Removal of critical sections only | Congested corridors |
| Abandonment in Place | Cleaned, inerted, and buried | Deep swamp / offshore |
| Asset Recovery (TAR) | Preservation for reuse | High-value equipment |

4. EXECUTION METHODOLOGY

Phase 1: Pre-Decommissioning Engineering

- Asset register validation

- Pipeline cleaning & pigging studies

- Environmental baseline survey

- Risk and HAZID/HAZOP assessment

- Regulatory engagement and approvals

Phase 2: Pipeline Isolation & Cleaning

- Mechanical isolation and valve shutdown

- Hydrocarbon depressurization

- Pigging (cleaning + gauging)

- Chemical cleaning (if required)

- Nitrogen purging / inerting

Phase 3: Decommissioning Execution

Onshore / Swamp Sections

- Sectional cutting and removal

- Excavation using swamp-compatible equipment

- Controlled lifting and transport

River & Creek Crossings

- HDD-installed sections → typically abandon in place

- Open-cut crossings → removal where feasible

Offshore Pipeline

- Flushing and seawater displacement

- Flooding and stabilization OR removal (case-specific)

Phase 4: Facilities Decommissioning

- Slug catcher cleaning and dismantling

- Manifold disconnection and removal

- Mechanical/electrical isolation

- Hazardous material handling

Phase 5: Site Restoration

- Backfilling and regrading

- Mangrove and vegetation restoration

- Erosion control

- Post-restoration monitoring

5. ENVIRONMENTAL & REGULATORY COMPLIANCE

Applicable Framework

- Nigerian EIA Act

- NUPRC Environmental Guidelines

- NMDPRA Midstream Regulations

- IFC Performance Standards

Key Environmental Measures

- Zero discharge into inland waters

- Produced water treatment prior to disposal

- Waste segregation and certified disposal

- Biodiversity protection (especially mangroves)

6. TECHNICAL ASSET RECOVERY (TAR)

Consistent with your earlier TAR model:

Recoverable Assets

- Line pipes (subject to integrity checks)

- Valves and actuators

- Metering systems

- Structural steel

Preservation Strategy

- Controlled dismantling

- Cleaning and coating

- Storage on prepared hardstand areas

- Certification for reuse

7. RISK MANAGEMENT

Key Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Residual hydrocarbons | Multi-stage pigging & gas testing |
| Swamp instability | Use of swamp mats & low-ground-pressure equipment |
| Community disruption | Stakeholder engagement plan |
| Environmental contamination | Spill prevention & response plan |
| River crossing complexity | Prefer abandonment-in-place |

8. SCHEDULE (INDICATIVE)

| Phase | Duration |
| --- | --- |
| Engineering & Approvals | 4–6 months |
| Cleaning & Isolation | 2–3 months |
| Decommissioning Execution | 6–10 months |
| Restoration & Close-out | 3–6 months |

Total Duration: ~12–18 months

9. COST ESTIMATE (ORDER OF MAGNITUDE)

Based on Niger Delta benchmarks:

| Component | Estimated Cost (NGN Billion) |
| --- | --- |
| Engineering & Studies | 2.5 – 4.0 |
| Cleaning & Isolation | 3.0 – 5.0 |
| Pipeline Removal / Abandonment | 15.0 – 25.0 |
| Facilities Dismantling | 5.0 – 8.0 |
| Environmental Restoration | 4.0 – 7.0 |
| Total Estimate | 29 – 49 Billion NGN |

Accuracy: ±30% (Pre-FEED level)

10. DELIVERABLES

- Decommissioning Execution Plan (DEP)

- Environmental Management Plan (EMP)

- Waste Management Plan

- Asset Recovery Report

- Regulatory Close-out Documentation

11. CONCLUSION

This decommissioning proposal provides a technically robust, environmentally responsible, and commercially optimized framework for retiring the OKNU–BBOU–ELEP–AKAB pipeline system.

It ensures:

- Safe cessation of operations

- Protection of the Niger Delta ecosystem

- Maximum recovery of asset value

- Full regulatory compliance

If you want, I can take this further into:

- A 1-page executive slide (investment committee grade)

- A detailed cost breakdown (line-by-line BOQ)

- A decommissioning Gantt chart aligned with your FEED schedule

- Or merge it into your full submission pack (Proposal + Slides + Cover Letter)

Uploading files? Try using connectors

Use connected apps to access all your documents automatically.

Try Business free

key decommissioning processes and abandonment activities

Here’s a clear, executive-grade breakdown of the key decommissioning processes and abandonment activities, aligned with your OKNU–BBOU–ELEP–AKAB pipeline system and Niger Delta conditions:

KEY DECOMMISSIONING PROCESSES & ABANDONMENT ACTIVITIES

1. Decommissioning Processes (End-to-End Execution)

1.1 Pre-Decommissioning Planning

- Asset verification (as-built vs actual condition)

- Regulatory approvals (Nigerian Upstream Petroleum Regulatory Commission, Nigerian Midstream and Downstream Petroleum Regulatory Authority)

- Environmental baseline and risk assessment

- Stakeholder/community engagement

1.2 System Shutdown & Isolation

- Controlled shutdown of gas flow

- Mechanical isolation (valves, blinds, spading)

- Electrical and instrumentation de-energization

- Segmentation into manageable sections (by KP / hydrotest sections)

1.3 Pipeline Cleaning & Hydrocarbon Removal

- Depressurization and venting

- Pigging operations:

  - Cleaning pigs

  - Batching pigs

- Chemical cleaning (if required)

- Removal of condensate, sludge, and residues

1.4 Flushing, Drying & Inerting

- Water flushing or gel cleaning

- Air or nitrogen drying

- Nitrogen purging to achieve inert condition

👉 Critical to eliminate explosion and contamination risks

1.5 Disconnection & Mechanical Works

- Cutting of pipeline into sections

- Disconnection from:

  - Manifolds (OKNU, BBOU, ELEP)

  - AKAB gas hub

- Removal of above-ground facilities:

  - Slug catchers

  - Pigging stations

  - Metering systems

1.6 Pipeline Removal (Where Applicable)

- Excavation (swamp-compatible methods)

- Lifting and transport

- Removal of:

  - Shallow buried pipelines

  - Congested corridor sections

- Special handling at crossings

1.7 Waste Management

- Segregation:

  - Scrap steel

  - Hazardous waste

  - Contaminated soils

- Transport to certified disposal facilities

- Compliance with Federal Ministry of Environment standards

1.8 Site Restoration

- Backfilling and grading

- Mangrove and vegetation restoration

- Erosion control (especially in swamp areas)

- Post-restoration monitoring

2. Abandonment Activities (Pipeline Left In Place)

Applied where removal is technically difficult, environmentally risky, or uneconomic.

2.1 Cleaning to Acceptable Standard

- Internal cleaning to remove hydrocarbons

- Verification via pigging and sampling

2.2 Isolation & Disconnection

- Physical disconnection from live systems

- Installation of:

  - Blind flanges

  - Permanent caps

- Removal of surface tie-ins

2.3 Filling / Stabilization

Depending on location:

Onshore / Swamp

- Filling with inert material:

  - Nitrogen (short-term)

  - Water or inhibited fluid

  - Cement grout (long-term stability)

River / Offshore

- Flooding with seawater

- Natural sediment stabilization

- Rock dumping (if required)

2.4 Cathodic Protection Decommissioning

- Deactivation of CP systems

- Removal or safe abandonment of anodes

- Electrical isolation

2.5 Long-Term Integrity Assurance

- Corrosion risk assessment

- Monitoring (if required by regulator)

- Documentation of abandoned sections

2.6 Marking & Records

- Updating pipeline records as “abandoned”

- GIS and survey updates

- Installation of surface markers (where required)

3. Special Considerations for OKNU–BBOU–ELEP–AKAB

High-Priority Abandonment Zones

- River Niger crossing (~KP10) → Abandon in place preferred

- Deep swamp sections (KP10–KP66) → Selective abandonment

- Offshore FLNG line → Flood & stabilize

High-Priority Removal Zones

- Manifold areas (OKNU, KP38, KP66, BBOU, ELEP, AKAB)

- Congested corridors

- Areas with future development conflicts

4. Decision Framework (Removal vs Abandonment)

| Factor | Removal | Abandonment |
| --- | --- | --- |
| Environmental sensitivity | ❌ | ✅ |
| Swamp / offshore terrain | ❌ | ✅ |
| Congested facilities | ✅ | ❌ |
| Cost efficiency | ❌ (higher) | ✅ (lower) |
| Future land use | ✅ | ❌ |

5. Executive Takeaway

Decommissioning success depends on three critical controls:

- Complete hydrocarbon removal and inerting

- Right selection of removal vs abandonment strategy

- Full environmental restoration and regulatory closure

If you want, I can:

- Convert this into a process flow diagram (visual slide)

- Or build a decision tree for abandonment vs removal (very powerful for board presentation)

- Or align it into your final decommissioning proposal pack with cost + schedule integration

Top of Form

Bottom of Form

key list of as-built drawings relevant in the exercise

Here’s a focused, project-ready list of as-built drawings required for a pipeline decommissioning exercise—structured the way regulators, EPCs, and asset teams expect to see it.

Key As-Built Drawings for Pipeline Decommissioning

1. Route & Alignment Drawings

- Pipeline Alignment Sheets (Plan & Profile)

  - Chainage (KP), coordinates, elevations

  - Terrain classification (swamp, river, upland)

- Right-of-Way (ROW) Drawings

  - Corridor width, access routes, encroachments

- Survey As-Built Drawings

  - Final surveyed route vs design deviations

👉 Critical for locating buried assets and planning removal vs abandonment

2. Pipeline Layout & General Arrangement

- Pipeline General Arrangement (GA) Drawings

- Plot Plans (Facilities & Manifolds)

- Station Layouts (OKNU, BBOU, ELEP, AKAB)

- Isometric Drawings (Pipeline Sections)

👉 Defines physical configuration and tie-in relationships

3. Crossings & Special Installations

- River Crossing Drawings (HDD / Open Cut)

- Creek Crossing Details

- Road / Rail Crossing Drawings

- Typical Trench & Burial Details

👉 Key for deciding: remove vs abandon-in-place

4. Pipeline Mechanical & Material Records

- Line Pipe Mill Certificates (linked to drawings)

- Wall Thickness & Coating Specifications

- Weld Maps (Field Weld Identification Drawings)

- Coating & Wrapping As-Built Drawings

👉 Supports integrity assessment and reuse (TAR decisions)

5. Valves, Pigging & Manifolds

- Valve Location Drawings (chainage referenced)

- Pig Launcher / Receiver Drawings

- Manifold Piping & Instrumentation Layouts

- Slug Catcher As-Built Drawings

👉 Essential for isolation, segmentation, and cleaning strategy

6. Instrumentation & Control

- P&IDs (As-Built)

- Cause & Effect Diagrams

- SCADA / Telemetry Layouts

- Cable Routing Drawings

👉 Required for safe shutdown and system isolation

7. Cathodic Protection & Electrical

- CP Layout Drawings (Anode Beds, TR Units)

- Pipeline Coating Holiday Survey Records (linked)

- Earthing & Bonding Drawings

- Electrical Single Line Diagrams (SLDs)

👉 Important for safe de-energization and environmental protection

8. Civil & Structural Drawings

- Foundation Drawings (Manifolds, Skids, Slug Catchers)

- Pipe Supports & Sleepers

- Access Roads & Temporary Works (as-built)

👉 Guides dismantling and site restoration

9. Hydrotest & Commissioning Records (Drawings-Linked)

- Hydrotest Section Layout Drawings

- Test Boundaries and Isolation Points

- Dewatering and Drying Layouts

👉 Useful for defining pipeline sections during decommissioning

10. Environmental & Restoration Drawings

- Pre-Construction Environmental Baseline Maps

- Sensitive Area Mapping (Mangroves, Wetlands)

- Reinstatement / Restoration Drawings (if previously done)

👉 Critical for compliance and post-decommissioning restoration

11. Modifications & Deviation Records

- Redline Drawings (Design vs As-Built Changes)

- Tie-in Modification Drawings

- Looping / Rerouting As-Builts

👉 Prevents missing hidden or undocumented assets

Executive Summary (Slide-Ready)

Minimum Critical Drawing Set

- Alignment Sheets (Plan & Profile)

- P&IDs (As-Built)

- Valve & Isolation Drawings

- Crossing Details (River/Creek/HDD)

- Manifold & Slug Catcher GAs

- Weld Maps & Material Traceability

- CP & Electrical Layouts

- Plot Plans & Facility Layouts

Bottom Line

Without accurate as-built drawings:

- Isolation becomes unsafe

- Cleaning becomes inefficient

- Removal risks increase

- Regulatory approval may be delayed

→ As-builts are the foundation of safe, compliant decommissioning.

If you want, I can:

- Convert this into a document checklist (for contractor bid submission)

- Or map each drawing to your OKNU–BBOU system components (KP-by-KP relevance)

- Or create a data room index structure for your project

Top of Form

do all three, covering the entire pipeline: OKNU-BBOU-ELEP-AKAB

Below is a complete, project-ready package covering all three deliverables for the OKNU–BBOU–ELEP–AKAB pipeline system:

A. CONTRACTOR BID SUBMISSION – AS-BUILT DRAWING CHECKLIST

Instruction to Bidders

All bidders shall provide complete, verified, and indexed as-built documentation for decommissioning execution. Missing or incomplete drawings will be treated as a technical compliance gap.

A1. Mandatory Drawing Categories

1. Route & Alignment

- Pipeline Alignment Sheets (Plan & Profile, KP 0–125 km)

- ROW Drawings (full corridor coverage)

- Survey As-Built (final coordinates and deviations)

2. Layout & Configuration

- Pipeline General Arrangement (GA)

- Plot Plans:

  - OKNU Manifold (KP 0)

  - BBOU Manifold (KP 85)

  - ELEP (KP 93)

  - AKAB Gas Hub (KP 125)

- Pipeline Isometrics (segment-wise)

3. Crossings & Special Sections

- River Niger Crossing (~KP 10) drawings

- Creek/River crossings (all locations)

- HDD / trenchless installation drawings

- Trench and burial profiles

4. Mechanical & Materials

- Weld maps (full traceability)

- Wall thickness and coating specs

- Line pipe data sheets

- Material certificates (API 5L traceability)

5. Valves & Facilities

- Valve location drawings (chainage-based)

- Pig launcher/receiver drawings

- Manifold piping layouts (OKNU, KP38, KP66, BBOU, ELEP)

- Slug catcher drawings

6. Process & Control

- As-built P&IDs (entire system)

- Cause & Effect diagrams

- SCADA / instrumentation layouts

7. Electrical & CP

- Cathodic Protection layout

- Transformer Rectifier (TR) locations

- Earthing & bonding drawings

- Electrical Single Line Diagrams

8. Civil & Structural

- Foundations (manifolds, slug catchers)

- Pipe supports and sleepers

- Access roads and pads

9. Testing & Commissioning

- Hydrotest layouts and sectioning

- Dewatering/drying layouts

10. Environmental

- Baseline environmental maps

- Sensitive area mapping (mangroves, wetlands)

- Restoration drawings (if applicable)

11. Modifications & Deviations

- Redline drawings

- Tie-in modifications (KP38, KP66, BBOU integration)

- Looping / resizing updates

A2. Submission Requirements

- Digital format (PDF + native CAD)

- Indexed and searchable

- Linked to asset register

- Verified as “As-Built” (not IFC/IFD)

B. KP-BY-KP DRAWING RELEVANCE (OKNU → AKAB)

This maps critical drawings to physical pipeline segments—very useful for execution planning.

KP 0 – KP 10 (OKNU → River Niger Crossing)

Key Features: Inlet manifold, slug catcher, swamp terrain

Required Drawings:

- OKNU Plot Plan & P&IDs

- Slug catcher GA

- Alignment sheets

- Valve and pigging drawings

- CP layout

KP 10 – River Niger Crossing

Key Features: Major river crossing (~200 m width)

Required Drawings:

- HDD / crossing profile drawings

- Bathymetric and geotechnical drawings

- Crossing method as-built

- Environmental sensitivity maps

Execution Note: High likelihood of abandonment-in-place

KP 10 – KP 38 (Swamp Section)

Key Features: Challenging swamp terrain

Required Drawings:

- Alignment + trench details

- CP and coating drawings

- Weld maps

- Access road drawings

KP 38 – Midline Manifold (SEIB Tie-in)

Key Features: Future tie-in node

Required Drawings:

- Manifold GA and piping layout

- Metering system drawings

- Isolation valve drawings

KP 38 – KP 66

Key Features: Long swamp stretch

Required Drawings:

- Alignment sheets

- Weld maps

- CP layout

- Environmental maps

KP 66 – Midline Manifold (NUNR/DBUC Tie-in)

Key Features: Conditional tie-in

Required Drawings:

- Manifold GA

- Tie-in spool drawings

- Instrumentation layouts

KP 66 – KP 85 (BBOU)

Key Features: Approach to major hub

Required Drawings:

- Alignment and profile

- Valve segmentation drawings

- Hydrotest section drawings

KP 85 – BBOU Manifold

Key Features: Major integration node

Required Drawings:

- Plot plan & P&IDs

- Tie-in drawings (OKNU + ELEP line)

- Metering and control systems

KP 85 – KP 93 (BBOU → ELEP)

Key Features: Existing/planned 20” pipeline

Required Drawings:

- Alignment sheets

- Isometrics

- CP and coating drawings

KP 93 – KP 125 (ELEP → AKAB)

Key Features: 28” trunkline

Required Drawings:

- Trunkline alignment

- Weld maps

- Hydrotest layouts

- SCADA layouts

KP 125 – AKAB Gas Hub

Key Features: Processing hub

Required Drawings:

- Full plot plan

- P&IDs

- Slug catcher / inlet facilities

- Export tie-ins (methanol / LNG)

C. DATA ROOM INDEX STRUCTURE (PROJECT-WIDE)

This is how you should structure your digital data room for execution and audit readiness.

01. Project Overview

- Pipeline description

- Key coordinates and KP definitions

- Asset register

02. Route & Survey

- Alignment sheets

- ROW drawings

- Survey as-builts

03. Pipeline Engineering

- GA drawings

- Isometrics

- Wall thickness & specs

04. Facilities

- OKNU

- KP38 manifold

- KP66 manifold

- BBOU

- ELEP

- AKAB

05. Crossings

- River Niger crossing

- Creek crossings

- HDD drawings

06. Mechanical & Materials

- Weld maps

- Material certificates

- Coating specs

07. Process & Instrumentation

- P&IDs

- Cause & Effect

- SCADA

08. Electrical & CP

- CP layouts

- SLDs

- Earthing

09. Civil & Structural

- Foundations

- Supports

- Access infrastructure

10. Testing & Commissioning

- Hydrotest

- Drying

- Pre-commissioning

11. Environmental

- EIA

- Baseline data

- Restoration plans

12. Modifications

- Redlines

- Tie-ins

- Design changes

13. Decommissioning (To Be Developed)

- Decommissioning Execution Plan

- Cleaning & pigging procedures

- Waste management plan

- Restoration plan

Final Executive Insight

For your OKNU–BBOU–ELEP–AKAB system, the most critical drawing gaps to watch are:

- River Niger crossing as-built details

- Midline manifold tie-in documentation (KP38 & KP66)

- Weld maps and material traceability

- Updated P&IDs reflecting integration with AKAB

→ These will make or break safe isolation, cleaning, and regulatory approval.

If you want next-level refinement, I can:

- Turn this into a bid evaluation checklist (scoring template)

- Or build a data completeness heat map (red/amber/green by KP)

- Or integrate this directly into your decommissioning proposal submission pack

Top of Form

Bottom of Form

Bottom of Form

key elements of the decommissionin

Here are the key elements of pipeline decommissioning, distilled into a clear, executive-ready structure you can drop into a proposal or slide:

Key Elements of Pipeline Decommissioning

1. Regulatory & Compliance Framework

- Alignment with NUPRC, NMDPRA, and FMEnv requirements

- Environmental Impact Assessment (EIA) / Decommissioning Plan approval

- Stakeholder and host community engagement

- Permits for waste handling, marine works, and site restoration

2. Decommissioning Strategy Definition

- Selection of optimal approach:

  - Full Removal

  - Partial Removal

  - Abandonment-in-Place

- Risk-based decision considering:

  - Terrain (swamp, offshore, river crossings)

  - Environmental sensitivity

  - Cost vs. long-term liability

3. Pre-Decommissioning Engineering

- Asset register validation and condition assessment

- Pipeline integrity review and historical data analysis

- Development of:

  - Decommissioning Execution Plan (DEP)

  - HAZID / HAZOP studies

  - Method statements

4. Pipeline Cleaning & Isolation

- System shutdown and mechanical isolation

- Hydrocarbon removal (depressurization)

- Pigging operations:

  - Cleaning pigs

  - Gauging pigs

- Flushing and chemical cleaning (if required)

- Nitrogen purging / inerting

5. Facilities Decommissioning

- Isolation and dismantling of:

  - Manifolds

  - Slug catchers

  - Metering systems

- Electrical and control system de-energization

- Hazardous material removal (e.g., residues, chemicals)

6. Pipeline Decommissioning Execution

- Cutting, lifting, and removal of pipeline sections

- Handling of:

  - Swamp sections (low-ground-pressure equipment)

  - River/creek crossings

  - Offshore pipelines

- Transportation to disposal or storage sites

7. Waste Management

- Segregation of waste streams:

  - Scrap metal

  - Hazardous waste

  - Contaminated soils

- Certified disposal in approved facilities

- Compliance with environmental standards

8. Technical Asset Recovery (TAR)

- Identification of reusable assets:

  - Line pipes

  - Valves and fittings

  - Structural components

- Cleaning, inspection, and certification

- Storage for future reuse (plug-and-play readiness)

9. Environmental Restoration

- Backfilling and regrading of excavated areas

- Mangrove and vegetation restoration (critical in Niger Delta)

- Erosion and sediment control

- Post-restoration monitoring

10. Health, Safety & Risk Management

- HSE plan and emergency response procedures

- Gas testing and confined space controls

- Spill prevention and response readiness

- Community safety and security management

11. Documentation & Close-Out

- As-left condition reports

- Environmental compliance certification

- Regulatory close-out approvals

- Lessons learned and final reporting

12. Schedule & Cost Control

- Phased execution plan

- Integration with broader asset lifecycle strategy

- Budget tracking and cost optimization

- Risk-adjusted contingency planning

Bottom Line (Executive Framing)

Pipeline decommissioning is built on four pillars:

- Safe isolation and cleaning

- Environmentally responsible removal or abandonment

- Value recovery through asset reuse

- Full regulatory and stakeholder compliance

If you want, I can compress this into a single, high-impact boardroom slide (with icons + flow structure) or align it directly with your OKNU–BBOU project narrative.

Top of Form

yes

Here’s a single, investment-committee–grade slide you can use directly for your OKNU–BBOU project:

Writing

PIPELINE DECOMMISSIONING – KEY ELEMENTS (EXECUTIVE SUMMARY)

Objective

Deliver a safe, compliant, and cost-optimized decommissioning of the OKNU–BBOU–ELEP–AKAB pipeline system, while preserving asset value and minimizing environmental impact in the Niger Delta.

1. STRATEGY & COMPLIANCE

- Regulatory alignment: NUPRC / NMDPRA / FMEnv

- Approved Decommissioning & Environmental Plans

- Strategy selection: Remove | Partial Remove | Abandon-in-Place

- Stakeholder & host community engagement

2. ENGINEERING & PREPARATION

- Asset register validation & integrity review

- HAZID / HAZOP and risk assessments

- Decommissioning Execution Plan (DEP)

- Detailed method statements

3. ISOLATION & CLEANING

- Pipeline shutdown and sectional isolation

- Hydrocarbon removal and depressurization

- Pigging (cleaning, gauging)

- Flushing and nitrogen inerting

4. EXECUTION (PIPELINE & FACILITIES)

- Pipeline cutting, lifting, and removal

- Swamp, river, and offshore execution strategies

- Dismantling of manifolds, slug catchers, and metering systems

- Safe handling of hazardous materials

5. WASTE & ASSET MANAGEMENT

- Waste segregation and certified disposal

- Environmental compliance tracking

- Technical Asset Recovery (TAR):

  - Recovery of pipes, valves, and equipment

  - Preservation for future reuse (plug-and-play readiness)

6. ENVIRONMENTAL RESTORATION

- Backfilling and land regrading

- Mangrove and vegetation restoration

- Erosion control and monitoring

- Zero discharge compliance

7. HSE & RISK CONTROL

- Zero harm execution philosophy

- Gas testing and spill prevention

- Emergency response readiness

- Community safety management

8. CLOSE-OUT & VALUE DELIVERY

- Regulatory sign-off and compliance certification

- As-left condition documentation

- Lessons learned

- Optimized lifecycle cost outcome

EXECUTIVE TAKEAWAY

A phased, risk-based decommissioning model that ensures:
✔ Safety and environmental protection
✔ Regulatory compliance
✔ Cost efficiency
✔ Maximum recovery of asset value

If you want the next step, I can:

- Turn this into a PowerPoint slide (fully designed, icons + layout)

- Add a Gantt timeline strip at the bottom

- Or integrate it into your full proposal pack with consistent visual style

Top of Form

Bottom of Form

Bottom of Form

Below is a comprehensive Decommissioning Proposal aligned with your FEED scope, project philosophy, and Niger Delta operating conditions.

TECHNICAL PROPOSAL FOR PIPELINE DECOMMISSIONING

OKNU–BBOU–ELEP–AKAB Integrated Gas Development

1. Executive Summary

This proposal outlines a structured, safe, and environmentally compliant approach for the decommissioning of pipeline systems and associated facilities within the OKNU–BBOU–ELEP–AKAB gas infrastructure network.

The objective is to:

- Safely retire pipeline assets at end-of-life or prior to system modification

- Preserve high-value equipment where applicable (aligned with TAR philosophy)

- Minimize environmental and social impact within the Niger Delta

- Ensure full compliance with NUPRC and NMDPRA regulatory frameworks

The decommissioning philosophy integrates with the FEED design to ensure:

- Future expandability is not compromised

- Reusable assets remain in “plug-and-play” condition

- System integrity is maintained during transition phases

2. Scope of Decommissioning

The scope covers the following pipeline segments and facilities:

2.1 Pipeline Systems

- OKNU–BBOU Pipeline (~85 km, new development – future decommissioning provision)

- BBOU–ELEP–AKAB Pipeline (~40 km existing system)

- Gas Gathering Network (~125 km total network)

- Offshore Gas Export Pipeline to FLNG (~20–25 km)

2.2 Associated Facilities

- Manifolds (OKNU, KP38, KP66, BBOU, ELEP)

- Gas Processing Plant (AKAB)

- Methanol and LNG feed pipelines

- Offshore FLNG tie-in system

- Product export pipelines (Condensate, LPG)

- Utilities and offsite infrastructure

3. Decommissioning Philosophy

The decommissioning strategy adopts a fit-for-purpose, risk-based approach:

3.1 Key Principles

- Safety First: Zero harm to personnel and communities

- Environmental Protection: Full restoration of swamp and riverine ecosystems

- Regulatory Compliance: Adherence to DPR/NUPRC/NMDPRA guidelines

- Asset Value Optimization: Recovery and reuse of high-value equipment

- Minimal Footprint: Reduce intervention in sensitive terrains

3.2 Decommissioning Options

Each pipeline segment will be assessed under:

- Full Removal

  - Applicable for shallow, accessible, or environmentally sensitive areas

- Partial Removal

  - Removal of above-ground facilities; burial of pipelines

- In-situ Abandonment

  - Preferred in deep swamp or offshore environments

  - Pipelines cleaned, filled, and isolated

4. Decommissioning Execution Strategy

4.1 Pre-Decommissioning Activities

- Asset register validation and integrity assessment

- Pipeline cleaning (pigging, flushing)

- Hydrocarbon removal and gas freeing

- Environmental baseline survey

- Stakeholder engagement (host communities, regulators)

4.2 Pipeline Decommissioning Methodology

Step 1: Isolation

- Mechanical isolation at manifolds and tie-in points

- Installation of blinds and double block-and-bleed systems

Step 2: Cleaning & Purging

- Pigging operations (mechanical and chemical cleaning)

- Nitrogen purging to remove residual hydrocarbons

Step 3: Cutting & Sectioning

- Controlled cold cutting in swamp terrain

- Sectioning into transportable lengths

Step 4: Removal or Abandonment

- Onshore/swamp:

  - Excavation using amphibious equipment

  - Pipeline removal or burial

- Offshore:

  - Flooding and stabilization

  - Rock dumping (if required)

Step 5: Material Handling

- Segregation:

  - Reusable (valves, manifolds, fittings)

  - Scrap (steel recovery)

  - Hazardous waste

4.3 Facility Decommissioning

- Gas Processing Plant: depressurization, dismantling, equipment recovery

- Methanol/LNG systems: purging and isolation

- FLNG interface: subsea disconnection and abandonment

5. Environmental and Social Management

5.1 Environmental Protection Measures

- Zero discharge policy for hydrocarbons

- Controlled waste disposal

- Sediment and erosion control in swamp areas

- Biodiversity protection programs

5.2 Site Restoration

- Backfilling and regrading

- Re-vegetation with native species

- Wetland restoration

5.3 Community Engagement

- Stakeholder consultations

- Local workforce participation

- Community safety awareness

6. Integration with FEED and Future Expansion

The decommissioning plan is aligned with FEED objectives:

- Supports system integration between OKNU and existing pipelines

- Enables future expansion to 1 BCFD gas hub capacity

- Preserves midline manifolds (KP38, KP66) for reuse

- Maintains compatibility with:

  - Methanol production

  - LNG export (FLNG)

7. Risk Assessment and Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Residual hydrocarbons | Fire/explosion | Gas-free certification |
| Swamp terrain instability | Equipment failure | Use of amphibious rigs |
| Environmental contamination | Regulatory penalties | Spill prevention & monitoring |
| Community disruption | Social conflict | Early engagement |
| Offshore pipeline exposure | Navigation hazard | Burial / rock dumping |

8. Regulatory Compliance

All activities will comply with:

- NUPRC Decommissioning Guidelines

- NMDPRA Midstream Regulations

- Environmental Impact Assessment (EIA) Act

- International standards (ISO, API, DNV)

9. Execution Schedule

| Phase | Duration |
| --- | --- |
| Planning & Approvals | 3–6 months |
| Pre-Decommissioning | 2–3 months |
| Execution | 6–12 months |
| Restoration & Closeout | 3–6 months |

10. Cost Estimate Framework

Cost elements include:

- Engineering & project management

- Cleaning and purging

- Removal or abandonment works

- Waste management

- Environmental restoration

- Contingency (~15–20%)

Accuracy Target: ±15% (aligned with FEED level)

11. Deliverables

- Decommissioning Execution Plan (DEP)

- Environmental Management Plan (EMP)

- Waste Management Plan

- Risk Assessment (HAZID/HAZOP)

- Regulatory approval documentation

- As-left condition report

12. Conclusion

This decommissioning proposal ensures a safe, compliant, and value-driven retirement strategy for the OKNU–BBOU–ELEP–AKAB pipeline system, fully aligned with:

- FEED design philosophy

- Niger Delta environmental realities

- Long-term gas monetization strategy

It provides a balanced approach between asset recovery, environmental stewardship, and future system flexibility.

If you want, I can next:

- Convert this into a formal submission document (PDF-ready)

- Add cost breakdown (₦ detailed CAPEX/OPEX)

- Or align it with your TAR model for asset preservation strategy

Uploading files? Try using connectors

Use connected apps to access all your documents automatically.

Try Business free

Top of Form

Bottom of Form