## WBS - FEED OKNU-BBOU Gas PL
Epic Atlantic Commercial Proposal - Front End Engineering Design (FEED) - OKNU - ELEP Gas Pipeline - DSV Gas Hub Project
Time in Months
2026
[11 empty] | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Date: | 2026-03-25 | man-days |  |  | Rate (USD) | Unit Cost (USD) | Total/Sub Costs USD | Indicative WBS - Subject to Additions & Subtractions
|  |  |  | ACTIVITY |  |  |  | 281.375
140687.5
0 | NTP
| FEED - Grand Total |  |  |  | 6816 |  |  |  |  | 1992852
A | Project Management |  |  |  | 142500 |  | 470 |  |  | 157246.25
| 01 | Project Execution Schedule - Swamp Baseline |  |  |  | 50 |  |  | 14068.75
| 02 | Project's MDR - Marine Requirements |  |  |  | 50 |  |  | 14068.75
| 03 | Project Execution Plan - Swamp Marine |  |  |  | 50 |  |  | 14068.75
| 04 | Project Quality Management Plan (QA & QC) - Swamp QA |  |  |  | 50 |  |  | 14068.75
| 05 | Project HSE Plan - Swamp Operations |  |  |  | 50 |  |  | 14068.75
| 06 | NCD Plan - Niger Delta Swamp |  |  |  | 20 |  |  | 5627.5
| 07 | Provision for Site Visits / Externalities - Swamp Marine Survey | [6 empty] | 25000
| 08 | Project Monitoring & Control - Swamp |  |  |  | 200 |  |  | 56275
B | Executive Summaries Documents |  |  |  | 310000 |  | 1240 |  |  | 348905
| 01 | FEED Overview - Swamp Challenges |  |  |  | 130 |  |  | 36578.75
| 02 | Basis of Design Document - Swamp Conditions |  |  |  | 70 |  |  | 19696.25
| 03 | Pipeline Design & Operating Philosophy - Swamp |  |  |  | 70 |  |  | 19696.25
| 04 | Infrastructural Support Marine Access |  |  |  | 30 |  |  | 8441.25
| 05 | PFDs and P&IDs - Swamp Facilities |  |  |  | 60 |  |  | 16882.5
| 06 | ESIA Report Review, Approval & Compliance Register - Swamp Mangrove Impact |  |  |  | 50 |  |  | 14068.75
| 07 | Effulent & Emission Requirement & Swamp Compliance Plan |  |  |  | 50 |  |  | 14068.75
| 08 | Operations Philosophy Documents - Marine Spread |  |  |  | 60 |  |  | 16882.5
| 09 | Spare Parts Marine Access Strategy |  |  |  | 30 |  |  | 8441.25
| 10 | Consumables Swamp Logistics Plan |  |  |  | 30 |  |  | 8441.25
| 11 | Pipeline & Manifolds Swamp Security |  |  |  | 70 |  |  | 19696.25
| 12 | Flow Assurance Report - Swamp Conditions |  |  |  | 60 |  |  | 16882.5
| 13 | Layout Drawings & 3D Swamp Models |  |  |  | 80 |  |  | 22510
| 14 | Stress Analysis Swamp Load Cases |  |  |  | 50 |  |  | 14068.75
| 15 | Design Review & Hazop - Swamp |  |  |  | 60 |  |  | 16882.5
|  | 15.1 | Design Review / Records of Engineering & Technical Safety Control (TSC) Reviews |  | 15
|  | 15.2 | Pre-HAZOP Review |  | 15
|  | 15.3 | Final Hazop Review & Report |  | 15
|  | 15.4 | HAZOP Close-out |  | 15
| 16 | Other NUPRC Swamp Specific Requirements |  |  |  | 240 |  |  | 67530
|  | 16.1 | Manufacturing Inspection Plan for Fabrication of Line Pipes / Coating, as well as Pipeline Fittings / Accessories |  | 50
|  | 16.2 | Pipeline Construction Plan, inclusive of WPS / PQR, and Technical Data Sheets for Pipeline Fttings / Accessories |  | 50
|  | 16.3 | Pipeline Monitoring System Philosophy |  | 35
|  | 16.4 | Utilities and Blow-down Planimetric Flow Diagrams |  | 35
|  | 16.5 | Decommisiong Plan |  | 35
|  | 16.6 | OPL Application / Support Documents |  | 35
| 17 | EPC Marine Spread Documents |  |  |  | 100 |  |  | 28137.5
|  | 17.1 | AFD / AFC Drawings |  | 20
|  | 17.2 | Materials Requisition List |  | 20
|  | 17.3 | LLI |  | 20
|  | 17.4 | EPC Scope of Work |  | 20
|  | 17.5 | EPC Cost Estimate |  | 20
C | Process & Systems Engineering |  |  |  | 232000 |  | 728 |  |  | 254841
| 01 | Process Design Memorandum Documentations - Swamp |  |  |  | 88 |  |  | 24761
|  | 01.1 | Process Design Data Update - Notional |  | 25
|  | 01.2 | Process Design Philosophy |  | 25
|  | 01.3 | Process System Description |  | 19
|  | 01.4 | Process Control & Safeguarding Philosophy |  | 19
| 02 | Pipeline System Swamp Configuration & Design |  |  |  | 220 |  |  | 61902.5
|  | 02.1 | Process Flow Diagrams (PFDs) - P/L, PLEMs Swamp Conditions |  | 35
|  | 02.2 | Utility Flow Diagrams (UFDs) |  | 30
|  | 02.3 | P&IDs Swamp Facilities |  | 35
|  | 02.4 | Utilities P&IDs |  | 30
|  | 02.5 | Pipelines Sizing Check & Calculation Notes |  | 30
|  | 02.6 | Pipeline Blow-down and Depressurisation Plan |  | 30
|  | 02.7 | Safe Chart |  | 30
| 03 | Process Simulation & Pipeline Flow Assurance Analysis |  |  |  | 280 |  |  | 128785
|  | 03.1 | Provision for Softwares Licences - PIPESIM & HYSYS |  |  |  |  | 50000
|  | 03.2 | Hydraulic Analysis - PIPESIM & HYSYS |  | 60
|  | 03.3 | Steady State Simulation - Pipesim |  | 60
|  | 03.4 | Process Heat & Materials Balance |  | 60
|  | 03.5 | Utilities Heat & Materials Balance |  | 50
|  | 03.6 | Flow Assurance Analysis |  | 50
| 04 | Process Engineering Equipment Lists, & Datasheets |  |  |  | 140 |  |  | 39392.5
|  | 04.1 | Equipment List |  | 25
|  | 04.2 | Line List |  | 25
|  | 04.3 | Utility List |  | 25
|  | 04.4 | Process Equipment Data Sheets (Main Eqpt) |  | 25
|  | 04.5 | Process Instrument Data Sheets - Control Valves (Main Process Lines), Relief Valves and Manual Valves |  | 20
|  | 04.6 | Process Instrument Data Sheets - Flow Meters |  | 20
D | Materials Specification & Corrosion Management |  |  |  | 73750 |  | 295 |  |  | 83005.625
| 01 | Swamp Materials Selection |  |  |  | 70 |  |  | 19696.25
|  | 01.1 | Materials Selection Philosophy |  | 20
|  | 01.2 | Linepipe Materials Specification |  | 30
|  | 01.3 | Equipment Materials Specification |  | 20
| 02 | Corrosion Swamp Management Strategy |  |  |  | 225 |  |  | 63309.375
|  | 02.1 | Corrosion Analysis and Corrosion Protection & Control Philosophy |  | 35
|  | 02.2 | Coating Specification - Pipelines, Structures, & Equipment |  | 35
|  | 02.3 | CP Specification |  | 35
|  | 02.4 | Isolation Joint Specification |  | 35
|  | 02.5 | External Field Joint Coating Specification |  | 35
|  | 02.6 | Insulation Specification (Thermal) |  | 25
|  | 02.7 | Corrosion Inhibitor Specification |  | 25
E | Pipeline Engineering |  |  |  | 271750 |  | 1087 |  |  | 305854.625
| 01 | Pipeline Route Drawings / Location Maps |  |  |  | 155 |  |  | 43613.125
|  | 01.1 | Location Plan |  | 31
|  | 01.2 | RoW Drawing |  | 31
|  | 01.3 | Plan/Profile |  | 31
|  | 01.4 | Crossings |  | 31
|  | 01.5 | End Manifolds |  | 31
| 02 | Pipeline Design Drawings & Calculation Notes |  |  |  | 318 |  |  | 89477.25
|  | 02.1 | Pipeline Alignment Sheets |  | 53
|  | 02.2 | Pipeline Wall Thickness Calculations |  | 53
|  | 02.3 | Buoyancy Calculations & On Bottom Stability Analysis |  | 53
|  | 02.4 | Pipeline Crossing Details |  | 53
|  | 02.5 | Schedule of Crossings |  | 53
|  | 02.6 | Stress Analysis |  | 53
| 03 | Pipeline System Specifications - Swamp |  |  |  | 264 |  |  | 74283
|  | 03.1 | Specifications & Data Sheets for Line Pipes |  | 22
|  | 03.2 | Specifications & Data Sheets for Concrete Weight Coating |  | 22
|  | 03.3 | Specifications & Data Sheets for Line Pipe Coating |  | 22
|  | 03.4 | Specifications & Data Sheets for Mainline Valves |  | 22
|  | 03.5 | Specifications & Data Sheets for Mainline Fittings |  | 22
|  | 03.6 | Hot-Tap Fittings (Kp 38/66) Datasheets |  | 22
|  | 03.7 | Pipeline Construction Specification |  | 22
|  | 03.8 | Pipeline Pre-Commissioning Specification |  | 22
|  | 03.9 | Pipeline Cleaning, Gauging, & Hydrotesting Specification |  | 22
|  | 03.10 | Pipeline Integrity Management Philosophy |  | 22
|  | 03.11 | Manufacturing Inspection Plan for Fabrication of Line Pipes / Coating, as well as Pipeline Fittings / Accessories |  | 22
|  | 03.12 | Pipeline Construction Plan, inclusive of WPS / PQR, and Technical Data Sheets for Pipeline Fittings / Accessories |  | 22
| 04 | Marine Spread Requisitions |  |  |  | 102 |  |  | 28700.25
|  | 04.1 | Vessels |  | 34
|  | 04.2 | Equipment |  | 34
|  | 04.3 | Operations |  | 34
| 05 | Pipeline End Manifolds Design |  |  |  | 48 |  |  | 13506
|  | 05.1 | OKNU End Manifold Design |  | 24
|  | 05.2 | ELEP End Manifold Design |  | 24
| 06 | Nun River (Major river) Crossing Design |  |  |  | 100 |  |  | 28137.5
|  | 06.1 | HDD/Micro-tunneling analysis and design |  | 25
|  | 06.2 | Riverbed (Scour analysis and Bedding & protection) |  | 25
|  | 06.3 | Hydraulic (Flood modelling and Buoyancy control) |  | 25
|  | 06.4 | Structural (HDD entry/exit platforms and Contingency open-cut) |  | 25
| 07 | 12 Water Crossings (4 river + 8 creek crossings) Engineering |  |  |  | 100 |  |  | 28137.5
|  | 07.1 | 4 River crossings engineering |  | 35
|  | 07.2 | 8 Creek crossings engineering |  | 35
|  | 07.3 | Buoyancy calcs, Hydrotest provisions and Drawing packages |  | 30
F | Mechanical & Piping Engineering |  |  |  | 223750 |  | 895 |  |  | 251830.625
| 01 | Station Locations Plot Plans |  |  |  | 150 |  |  | 42206.25
|  | 01.1 | OKNU Plot Plan / 3D Model |  | 38
|  | 01.2 | ELEP Plot Plan / 3D Model |  | 38
|  | 01.3 | SEIB PL-MF Kp 38 |  | 37
|  | 01.4 | DBUC PL-MF Kp 66 |  | 37
| 02 | PFDs / P&IDs |  |  |  | 150 |  |  | 42206.25
|  | 02.1 | PFDs / P&IDs - OKNU M/F |  | 38
|  | 02.2 | PFDs / P&IDs - ELEP M/F |  | 38
|  | 02.3 | PFDs / P&IDs - SEIB PL- M/F |  | 37
|  | 02.4 | PFDs / P&IDs - DBUC PL- M/F |  | 37
| 03 | Equipment Specification / Datasheets Pig traps |  |  |  | 140 |  |  | 39392.5
|  | 03.1 | OKNU Pig Launcher Datasheets |  | 35
|  | 03.2 | ELEP Pig Receiver Datasheets |  | 35
|  | 03.3 | SEIB Pigging/Isolation |  | 35
|  | 03.4 | DBUC Pigging/Isolation |  | 35
| 04 | Piping Layout Drawings |  |  |  | 155 |  |  | 43613.125
|  | 04.1 | General Piping Arrangement Drawing - OKNU |  | 31
|  | 04.2 | General Piping Arrangement Drawing - ELEP |  | 31
|  | 04.3 | General Piping Arrangement Drawing - SEIB PL M/F |  | 31
|  | 04.4 | General Piping Arrangement Drawing - DBUC PL M/F |  | 31
|  | 04.5 | Piping Layout Details |  | 31
| 05 | Swamp Tie-in Marine Details |  |  |  | 100 |  |  | 28137.5
|  | 05.1 | Tie-ins - OKNU-ELEP, SEIB & DBUC Hot-tap |  | 40
|  | 05.2 | Flooding |  | 30
|  | 05.3 | Welding |  | 30
| 06 | Piping Specifications |  |  |  | 90 |  |  | 25323.75
|  | 06.1 | Piping Class Specification |  | 15
|  | 06.2 | Piping Materials Specification |  | 15
|  | 06.3 | Piping Design Calculation Notes |  | 15
|  | 06.4 | Specification For Welding and Testing |  | 15
|  | 06.5 | Specification for Painting and Coating |  | 15
|  | 06.6 | Specification for Hydrostatic Testing |  | 15
| 07 | Pipe Supports |  |  |  | 80 |  |  | 22510
|  | 07.1 | Pipe Supports - OKNU/ELEP |  | 30
|  | 07.2 | Pipe Supports - SEIB PL-MF |  | 25
|  | 07.3 | Pipe Supports - DBUC PL-MF |  | 25
| 08 | Piping Stress Analysis |  |  |  | 30 |  |  | 8441.25
|  | 08.1 | Piping Stress Analysis and Report - OKNU/ELEP |  | 15
|  | 08.2 | Piping Stress Analysis and Report - SEIB/DBUC |  | 15
G | Civil / Foundations Engineering - M/F Foundations |  |  |  | 65000 |  | 260 |  |  | 73157.5
| 01 | Manifolds Foundations Design |  |  |  | 48 |  |  | 13506
|  | 01.1 | OKNU Foundation Basis |  | 12
|  | 01.2 | ELEP Foundation Basis |  | 12
|  | 01.3 | SEIB PL-MF Foundations |  | 12
|  | 01.4 | DBUC PL-MF Foundations |  | 12
| 02 | Foundations Drawings & Calculation Notes |  |  |  | 100 |  |  | 28137.5
|  | 02.1 | Foundation Layout Drawings |  | 14
|  | 02.2 | Pile Layout Drawings |  | 14
|  | 02.3 | Structural Layout Drawings |  | 14
|  | 02.4 | Sewer System Planimetric Flow diagram |  | 14
|  | 02.5 | Manifolds Elevations & Plan / 3D Model |  | 14
|  | 02.6 | Foundations Calculations |  | 15
|  | 02.7 | Structural Calculations |  | 15
| 03 | MTO |  |  |  | 22 |  |  | 6190.25
|  | 03.1 | Civil MTO |  | 11
|  | 03.2 | Structural MTO |  | 11
| 04 | Marine Platforms Design |  |  |  | 90 |  |  | 25323.75
|  | 04.1 | Platform |  | 30
|  | 04.2 | Swamp |  | 30
|  | 04.3 | Mooring |  | 30
H | Electrical Engineering |  |  |  | 127000 |  | 508 |  |  | 142938.5
| 01 | Analysis of Manifold Power Options |  |  |  | 70 |  |  | 19696.25
|  | 01.1 | Thermal Cable Power |  | 35
|  | 01.2 | Solar Power |  | 35
| 02 | Load / Electrical Equipment List |  |  |  | 84 |  |  | 23635.5
|  | 02.1 | Load & Electrical Equipment List - OKNU |  | 21
|  | 02.2 | Load & Electrical Equipment List - ELEP |  | 21
|  | 02.3 | Load & Electrical Equipment List - SEIB PL-MF |  | 21
|  | 02.4 | Load & Electrical Equipment List - DBUC PL-MF |  | 21
| 03 | Electrical Single Line Diagram |  |  |  | 48 |  |  | 13506
|  | 03.1 | Electrical Single Line Diagram - OKNU |  | 12
|  | 03.2 | Electrical Single Line Diagram - ELEP |  | 12
|  | 03.3 | Electrical Single Line Diagram - SEIB PL-MF |  | 12
|  | 03.4 | Electrical Single Line Diagram - DBUC PL-MF |  | 12
| 04 | Power & Lighting Layout |  |  |  | 40 |  |  | 11255
|  | 04.1 | Power and Lighting Layout - OKNU/ELEP |  | 20
|  | 04.2 | Power and Lighting Layout - PL-MF |  | 20
| 05 | Earthing Layout Drawing |  |  |  | 40 |  |  | 11255
|  | 05.1 | Earthing Layout Drawing - OKNU/ELEP |  | 20
|  | 05.2 | Earthing Layout Drawing - PL-MF |  | 20
| 06 | Electrical Equipment |  |  |  | 76 |  |  | 21384.5
|  | 06.1 | Schematics of Power Panels |  | 19
|  | 06.2 | Data Sheets for Electrical Equipment |  | 19
|  | 06.3 | Electrical MTO for Cost Estimate |  | 19
|  | 06.4 | Cable Sizing |  | 19
| 07 | Swamp Cathodic Protection (CP) Marine Design |  |  |  | 150 |  |  | 42206.25
|  | 07.1 | Anodes |  | 45
|  | 07.2 | Cables |  | 35
|  | 07.3 | Transformer |  | 70
I | Automation / Control / Instrumentation Engineering |  |  |  | 92000 |  | 368 |  |  | 103546
| 01 | ICS System Architecture |  |  |  | 60 |  |  | 16882.5
|  | 01.1 | ICS System Architecture - OKNU |  | 15
|  | 01.2 | ICS System Architecture - ELEP |  | 15
|  | 01.3 | ICS System Architecture - SEIB PL-MF |  | 15
|  | 01.4 | ICS System Architecture - DBUC PL-MF |  | 15
| 02 | Control System Block Diagram |  |  |  | 84 |  |  | 23635.5
|  | 02.1 | Control System Block Diagram |  | 42
|  | 02.2 | ESD Block Diagram |  | 42
| 03 | Instrument List / Datasheets |  |  |  | 84 |  |  | 23635.5
|  | 03.1 | Instrument List / Datasheets - OKNU/ELEP |  | 42
|  | 03.2 | Instrument List / Datasheets - PL-MF |  | 42
| 04 | I/O List/C&E/ESD |  |  |  | 84 |  |  | 23635.5
|  | 04.1 | I/O List DCS/ESD |  | 28
|  | 04.2 | Cause & Effect Diagrams |  | 28
|  | 04.3 | ESD System Diagrams |  | 28
| 05 | Fire & Gas Detection Block Diagram |  |  |  | 56 |  |  | 15757
|  | 05.1 | Fire & Gas Detection Block Diagrams |  | 28
|  | 05.2 | Fire & Gas Detection Specifications |  | 28
J | Technical HSE |  |  |  | 241250 |  | 965 |  |  | 271526.875
| 01 | Project Hazard & Risk Register / Risk Assessment Matrix |  |  |  | 35 |  |  | 9848.125
| 02 | Process Safety Systems Engineering |  |  |  | 30 |  |  | 8441.25
| 03 | HAZOP |  |  |  | 115 |  |  | 32358.125
| 04 | Environmental Management Plan |  |  |  | 60 |  |  | 16882.5
| 05 | Hazardous Area Classification - OKNU, ELEP, SEIB & DBUC |  |  |  | 115 |  |  | 32358.125
| 06 | Safety Equipment & Escape Route - OKNU, ELEP, SEIB & DBUC |  |  |  | 100 |  |  | 28137.5
| 07 | Other EPC Requisite documents listed on project schedule |  |  |  | 450 |  |  | 126618.75
| 08 | Project Close-out |  |  |  | 60 |  |  | 16882.5
| FEED Grand Total | [5 empty] | 6816 |  |  | 1992852
Notes
Specific NUPRC Requirements
Additions, following TCE Comments
199285.2
2192137.2