## 1. Last Probabilistic Sch Oct25
Updated Probabilistic - BFPCL Gas Processing & Methanol Complex Project Schedule - Pre-Mitigated SRA Results 01Oct,2025
| ACTIVITY | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
Contract Effective Date
The Integrated Project | bar: 2025 D to 2029 F
01 | PIPELINES | bar: 2026 J to 2028 J
Mobilisation | bar: 2026 J to 2027 D
Design | bar: 2026 J to 2026 J
Procurement | bar: 2026 M to 2027 D
Construction | bar: 2026 N to 2027 D
FEED | bar: 2026 J to 2026 A
EPC | bar: 2026 J to 2028 J
Mechanical Completion | bar: 2027 J to 2028 A
Pre-Commissioning & Commissioning | bar: 2028 M to 2028 J
02 | GAS PLANT | bar: 2026 J to 2028 A
Design | bar: 2026 J to 2027 D
Procurement | bar: 2026 M to 2027 D
Construction | bar: 2026 S to 2027 D
FEED | bar: 2026 J to 2026 A
EPC | bar: 2026 J to 2028 J
Mechanical Completion | bar: 2027 J to 2028 F
Pre-Commissioning & Commissioning | bar: 2028 M to 2028 A
03 | METHANOL PLANT | bar: 2026 J to 2029 F
Design | bar: 2026 J to 2027 D
Procurement | bar: 2026 M to 2027 D
Construction | bar: 2026 O to 2027 D
Mechanical Completion | bar: 2027 J to 2028 J
Pre-Commissioning & Commissioning | bar: 2028 J to 2029 F
Intergrated Project Commissioning | bar: 2028 J to 2029 F
Related GSPA Timelines
Mechanical Completion
First Gas Delivery
GSPA Start
24/02
30/06
30/06
19/02
24/02
19/02
28/08
28/08
09/07
09/07
24/02
01/12

## 2. Update Sch Mar2026
Updated Probabilistic - BFPCL Gas Processing & Methanol Complex Project Schedule - Pre-Mitigated SRA Results 20Mar2026
| ACTIVITY | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Contract Effective Date | bar: 2027 F to 2027 M
The Integrated Project - GSPA 270 Facilities | bar: 2026 A to 2029 J
01 | PIPELINES - BBOU-ELEP-AKAB | bar: 2026 A to 2029 F
Mobilisation | bar: 2026 A to 2027 J
Design | bar: 2026 A to 2026 O; 2027 F to 2027 M
Procurement | bar: 2026 J to 2027 A
Construction | bar: 2027 F to 2028 A
Mechanical Completion, incl Punchlist | bar: 2027 F to 2027 M
Pre-Commissioning | bar: 2027 F to 2027 M; 2028 S to 2028 D
Commissioning | bar: 2027 F to 2027 M; 2028 N to 2029 F
02 | GAS PLANT | bar: 2027 F to 2027 M
Design | bar: 2027 F to 2027 M
Procurement | bar: 2027 F to 2027 M
Construction | bar: 2027 F to 2027 M
Mechanical Completion | bar: 2027 F to 2027 M
Pre-Commissioning & Commissioning | bar: 2027 F to 2027 M
OSD Readiness | bar: 2027 F to 2027 M
02 | GAS PLANT | bar: 2026 A to 2028 D
Design | bar: 2026 A to 2027 M
Procurement | bar: 2026 S to 2027 S
Construction | bar: 2027 J to 2028 J
Mechanical Completion, incl Punchlist | bar: 2027 F to 2027 M
Pre-Commissioning | bar: 2027 F to 2027 M; 2028 J to 2028 O
Commissioning | bar: 2027 F to 2027 M; 2028 S to 2028 D
OSD Readiness | bar: 2027 F to 2027 M
03 | METHANOL PLANT | bar: 2026 A to 2029 J
Design | bar: 2026 A to 2027 M
Procurement | bar: 2026 S to 2027 S
Construction | bar: 2027 F to 2028 D
Mechanical Completion, incl Punchlist | bar: 2027 F to 2027 M
Pre-Commissioning | bar: 2027 F to 2027 M; 2029 J to 2029 A
Commissioning | bar: 2027 F to 2027 M; 2029 M to 2029 J
OSD Readiness | bar: 2027 F to 2027 M
Integrated Project OSD Readiness - GSPA 270 Facilities | bar: 2027 F to 2027 M
Integrated Project OSD Readiness - GSPA 270 Facilities | bar: 2027 F to 2027 M; 2028 S to 2029 J
Related GSPA Timelines | bar: 2027 F to 2027 M
Mechanical Completion - GSPA 270 Facilities | bar: 2027 F to 2027 M
First Gas Delivery | bar: 2027 F to 2027 M
GSPA Start | bar: 2027 F to 2027 M
OKNU Pipeline & FLNG - Other GSPA Facilities | bar: 2026 A to 2030 S
05 | OKNU-BBOU Pipeline | bar: 2026 A to 2029 N
| FEED | 2026 M: 8 months
| EPC | 2027 N: 30 months
Mechanical Completion, incl Punchlist | bar: 2027 F to 2027 M
Pre-Commissioning | bar: 2027 F to 2027 M; 2029 J to 2029 S
Commissioning | bar: 2027 F to 2027 M; 2029 A to 2029 N
02 | GAS PLANT | bar: 2027 F to 2027 M
Design | bar: 2027 F to 2027 M
Procurement | bar: 2027 F to 2027 M
Construction | bar: 2027 F to 2027 M
Mechanical Completion | bar: 2027 F to 2027 M
Pre-Commissioning & Commissioning | bar: 2027 F to 2027 M
OSD Readiness | bar: 2027 F to 2027 M
FLNG | bar: 2026 A to 2030 A
| FEED | 2026 A: 12 months
| EPC | 2028 A: 36 months
Mechanical Completion, incl Punchlist | bar: 2027 F to 2027 M
Pre-Commissioning | bar: 2027 F to 2027 M; 2030 A to 2030 J
Commissioning | bar: 2027 F to 2027 M; 2030 J to 2030 S
OSD Readiness | bar: 2027 F to 2027 M
30/06
31/12
31/12
30/06
01/04
31/08
30/06
28/02
28/02
31/12
31/12
30/06
30/06
31/12
30/09
31/03
30/11
31/05
30/11

## 3. OKNU PL FEED Sch Mar2026
OKNU – BBOU Gas Pipeline Project Schedule
|  | OKNU – BBOU Gas Pipeline Project Schedule | 2026 | [47 empty] | EPC 2027 - 2029
|  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
|  |  | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42 | wk43 | wk44 | wk45 | wk46 | wk47 | wk48 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
0 |  | Scope Definition / Pre‑FEED
1.0 |  | PROJECT MANAGEMENT & FEED INITIATION:
| 1.1 | Contract award / Notice to Proceed
| 1.2 | FEED Kick-off Meeting
| 1.3 | Project Execution Plan (PEP) preparation
| 1.4 | Project Control setup (schedule, cost, document control)
| 1.5 | HSE Management Plan
| 1.6 | Stackholder engagement & regulatory interface
2.0 |  | DATA COLLECTION & FIELD SURVERYS
| 2.1 | Existing data review & corridor definition
| 2.2 | Satallite imagery & GIS mapping
| 2.3 | Topographic survey
| 2.4 | Bathymetric survey (Nun River & crossings)
| 2.5 | Geotechnical Investiation
| 2.6 | Environmental baseline survey
| 2.7 | Land acquisition corridor mapping
| 2.8 | Survey data processing & reporting
3.0 |  | PROCESS & FLOW ASSURANCE STUDIES
| 3.1 | Process Design Basis preparation
| 3.2 | Gas composition validation
| 3.3 | Steady -state hydraulic modelling
| 3.4 | Transient mutliphase modelling
| 3.5 | Pipeline diamenter Optimization (20" vs 24")
| 3.6 | Slug catcher location studies
| 3.7 | Liquid hold-up & slugging analysis
| 3.8 | hydrate risk assesment
| 3.9 | Chemical injection Philosophy
| 3.10 | Final flow assurance report
4.0 |  | PIPELINE ENGINEERING
| 4.1 | Pipeline route selection
| 4.2 | Pipeline wall thickness design
| 4.3 | material selection & corrosion philosophy
| 4.4 | CO2 corrosion modelling
| 4.5 | Pipeline stress analysis
| 4.6 | Block valve spacing study
| 4.7 | Pigging philosophy
| 4.8 | Cathodic protection design (ICCP)
| 4.9 | Fibre optic leak detection concept
| 4.10 | Pipeline alignmnet sheets
5.0 |  | CROSSING ENGINEERING
| 5.1 | Nun river crossing concept selection
| 5.2 | HDD feasibility study
| 5.3 | Creek crossing design (8 locations)
| 5.4 | River crossing design (4 locations)
| 5.5 | Construction methodology study
6.0 |  | FACTILITIES ENGINEERING (OKNU & BBOU)
| 6.1 | Slug catcher concept design
| 6.2 | Inlet manifold design (OKNU)
| 6.3 | Pipeline End manifold (PLEM) design
| 6.4 | Pig launcher & receiver design
| 6.5 | Produced water handling concept
| 6.6 | Condensate transfer to AKAB
| 6.7 | process PFD development
| 6.8 | P&ID development
7.0 |  | INSTRUMENTATION, CONTROL & POWER
| 7.1 | Control philosophy
| 7.2 | RTU system archhitecture
| 7.3 | leak detection system
| 7.4 | Solar power system design
| 7.5 | telecom & fibre optic integration
8.0 |  | HSE, RAM & RISK STUDIES
| 8.1 | HAZID workshop
| 8.2 | HAZOP study
| 8.3 | Quantitative risk Assessment supports
| 8.4 | Environmental Impact Assessment support
| 8.5 | Constructability review
9.0 |  | LAYOUT & 3D DESIGN
| 9.1 | Plot plans
| 9.2 | Equipment layout
| 9.3 | 3D model development
| 9.4 | Model review
10.0 |  | COST ESTIMATE & EXECUTION PLANNING
| 10.1 | Quantity take-off
| 10.2 | Class-3 CAPEX estimate
| 10.3 | EPC execution strategy
| 10.4 | Project schedule ( level 1 & level 2 EPC)
11.0 |  | FEED DELIVERABLES & FID PACKAGE
| 11.1 | FEED design report
| 11.2 | Technical specifications
| 11.3 | EPC tender package
| 11.4 | Management review
| 11.5 | Final FEED submission
| 11.6 | FID readiness presentation
|  | OKNU – BBOU Gas Pipeline Project Schedule | Jan wk1: 2026; 2027 Q1: EPC 2027 - 2029
|  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
|  |  | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42 | wk43 | wk44 | wk45 | wk46 | wk47 | wk48 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 12 | PIPELINE EPC | 2027 Q1: OKNU - BBOU Pipeline EPC

## 4. FLNG FEED Sch Mar2026
FLNG (Floating Liquefied Natural Gas) FEED Schedule
|  | FLNG Project Schedule | 2026 | [48 empty] | EPC 2027 Q2 - 2030 Q3
|  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
|  |  | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42 | wk43 | wk44 | wk45 | wk46 | wk47 | wk48 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
0 |  | Scope Definition / Pre‑FEED
1.0 |  | PROJECT MANAGEMENT & FEED INITIATION
| 1.1 | Contract award & alignment
| 1.2 | FEED Kick-off Meeting
| 1.3 | Project organization & staffing
| 1.4 | Mobilization
| 1.5 | HSE Management Plan
| 1.6 | Stakeholder engagement & regulatory interface
2.0 |  | DATA COLLECTION & SURVERYS
| 2.1 | Data gathering & review
| 2.2 | GIS mapping
| 2.3 | Topographic survey
| 2.4 | Bathymetric survey
| 2.5 | Geotechnical survey
| 2.5 | Metocean analysis
| 2.6 | Environmental baseline survey
| 2.7 | Land Acquisition corridor mapping
| 2.8 | Survey data processing & reporting
3.0 |  | PROCESS DESIGN & LNG SYSTEM
| 3.1 | Feed gas validation
| 3.2 | Process design basis
| 3.3 | Liquefaction screening
| 3.4 | Technology selection
| 3.5 | Process simulation
| 3.6 | Heat & material balance
| 3.7 | PFD development
| 3.8 | P&ID development
| 3.9 | Utility integration
| 3.1 | Process finalization
4.0 |  | FLOW ASSURANCE & PIPELINE INTERFACE
| 4.1 | Steady-state modelling
| 4.2 | Transient simulation
| 4.3 | Slugging analysis
| 4.4 | Hydrate study
| 4.5 | Turndown analysis
| 4.6 | Start-up/restart
| 4.7 | Interface definition
| 4.8 | Chemical injection Philosophy
| 4.9 | Final flow assurance report
5.0 |  | FLNG CONCEPT SELECTION
| 5.1 | Newbuild vs conversion
| 5.2 | Technical evaluation
| 5.3 | Cost comparison
| 5.4 | Risk assessment
| 5.5 | Final selection
6.0 |  | HULL, TOPSIDES & LAYOUT ENGINEERING
| 6.1 | Hull concept design
| 6.2 | Deck layout
| 6.3 | Module arrangement
| 6.4 | Weight control
| 6.5 | Stability analysis
| 6.6 | Integration
| 6.7 | Design/Model review
| 6.8 | 3D Model Development
| 6.9 | Plot Plans
7.0 |  | MOORING, RISERS & OFFLOADING
| 7.1 | Mooring concept
| 7.2 | Mooring analysis
| 7.3 | Riser design
| 7.4 | Offloading system
| 7.5 | Tanker interface
| 7.6 | Integration studies
8.0 |  | UTILITIES, ELECTRICAL & POWER
| 8.1 | Power system design
| 8.2 | Load list
| 8.3 | Electrical distribution
| 8.4 | Utility systems
| 8.5 | Flare & relief
| 8.6 | Fuel gas system
| 8.7 | Integration
9.0 |  | INSTRUMENTATION & CONTROL
| 9.1 | Control philosophy
| 9.2 | Instrument index
| 9.3 | DCS/ESD design
| 9.4 | SCADA/Telecom
| 9.5 | Metering systems
| 9.6 | Integration
| 9.7 | Leak Detection System
10.0 |  | SAFETY & RISK ENGINEERING
| 10.1 | HAZID
| 10.2 | HAZOP prep
| 10.3 | HAZOP workshop
| 10.4 | Fire & Gas Design
| 10.5 | Quantitative Risk Assessment
| 10.6 | EER Analysis
| 10.7 | Explosion Analysis
| 10.8 | Environmental Impact Assessment Support
11.0 |  | COST ESTIMATION
| 11.1 | Cost basis
| 11.2 | MTO
| 11.3 | CAPEX estimate
| 11.4 | OPEX estimate
| 11.5 | Cost risk analysis
| 11.6 | Validation
12.0 |  | EXECUTION STRATEGY & EPC PLANNING
| 12.1 | Execution strategy
| 12.2 | Fabrication strategy
| 12.3 | Installation methodology
| 12.4 | Procurement strategy
| 12.5 | EPC packaging
| 12.6 | EPC schedule (Level 1 & 2)
| 12.7 | Constructability review
13.0 |  | FINAL FEED & FID PACKAGE
| 13.1 | Draft FEED report
| 13.2 | Specifications finalization
| 13.3 | EPC tender package
| 13.4 | Reviews
| 13.5 | Final FEED submission
| 13.6 | FID support
| 14 | FLNG Project Schedule - Summary | Jan wk1: 2026; 2027 Q1: 2027; 2028 Q1: 2028; 2029 Q1: 2029; 2030 Q1: 2030
|  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42 | wk43 | wk44 | wk45 | wk46 | wk47 | wk48 | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16
|  | FEED | wk13: FEED
|  | EPC | 2027 Q2 wk2: EPC FLNG