## BOQ Summary
Bill of Quantities (BOQ) Summary Breakdown
Bill No. | Main Work Packages | Total Price
1 | Preliminaries & General Project Overheads
2 | Survey & Engineering
3 | Pipeline Procurement & Material Supply
4 | Right of Way (ROW) & Civil Earthworks
5 | Pipeline Construction & Non-Destructive Testing (NDT)
6 | Crossings & HDD
7 | Stations, Valves & Pigging Facilities
8 | Instrumentation, SCADA, Telecoms & Solar Systems
9 | Testing, Pre-commissioning & Dewatering
10 | Environmental, Regulatory & Close-Out

## Detailed Itemized BOQ
Detailed Itemized Bill of Quantities (BOQ)
BILL NO. 1.0: Preliminaries & General Project Overheads |  |  | \
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
1.1 | Contractor mobilization of plant, equipment, and personnel to operational bases. | LS | 1
1.2 | Procurement of Project All Risks Insurance, Marine Insurance and performance bonds. | LS | 1 |  |  | Includes Contractor's All Risks (CAR), Marine Cargo Insurance, Third-Party Liability Insurance, Workmen's Compensation and Performance Bonds.
1.3 | Construction of temporary project site offices, camps, workshops, and pipe stockyards near OKNU and BBOU. | LS | 1
1.4 | Temporary Camp Utilities (Power, Water, Communications) | LS | 1
1.5 | Maintenance of Site Health, Safety, and Environment (HSE) systems, personal protective equipment (PPE), and waste disposal programs. | Month | Proj. Duration
1.6 | Pipe Transportation (Port Handling, Customs Clearance & Inland Transport) | tonnes | 28000 |  |  | Estimated pipe tonnage. Includes port handling, customs clearance, trucking and delivery to stockyards.
1.7 | Marine Logistics | Month | Proj. Duration |  |  | Includes barges, tug boats, crew boats and marine support vessels.
1.8 | Personnel Transportation | Month | Proj. Duration |  |  | Includes personnel boats, vehicle transportation and helicopter support where required.
1.9 | Fuels & Consumables | LS | 1 |  |  | Includes diesel, marine fuel, lubricants and consumables for project execution.
1.1 | Security Logistics | Month | Proj. Duration |  |  | Includes escort boats, security personnel, surveillance and access control.
BILL NO. 2.0: Surveys & Engineering
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
2.1 | Topographical survey and Differential GPS (DGPS) Survey | km | 85 |  |  | Entire pipeline route requires coverage.
2.2 | Longitudinal Profile and Cross-Section Survey | km | 85 |  |  | Provides elevation profile for hydraulic and crossing design.
2.3 | Bathymetric survey | km | 25 |  |  | Applicable to navigable rivers, creeks and waterway crossings.
2.4 | Route center-line staking survey | km | 85 |  |  | Centerline must be established for the full route.
2.5 | Establishment of Survey Control Points & Permanent Reference Monuments | No. | 50 |  |  | Approximately every 1.5–2 km along the route. Includes establishment, protection, documentation and handover of survey control points and permanent reference monuments along the pipeline alignment.
2.6 | Geotechnical soil boring investigations | Borehole | 42 |  |  | Pipeline Route= 20, Major HDD River Crossing= 6, 4 River Crossings= 8 & 8 Creek Crossings= 8 Total- 20+6+8+8= 42 Borehole locations and depths subject to detailed geotechnical investigation plan.
2.7 | Cone Penetration Tests (CPT) | No. | 85 |  |  | 1 CPT approximately every 1 km. 85 km route= 85 CPTs. CPT to supplement borehole investigations in swamp terrain and soft-soil areas
2.8 | Trial Pits | No. | 30 |  |  | Typical usage: Valve stations, Tie-in locations, Access roads & Civil structures Final locations subject to route accessibility and site conditions.
2.9 | Soil Corrosivity Assessment | Lot | 1 |  |  | Results shall be used for coating selection and cathodic protection design.
2.1 | Finalization of detailed pipeline drawings, alignment sheets, P&IDs, and Stress Analysis reports. | LS | 1
2.11 | Full EIA Survey Package & Permitting Management | LS | 1
2.12 | GIS Database Development | LS | 1 |  |  | Includes geospatial database and digital route records.
2.13 | Corridor Alignment Sheets | No. | 25 |  |  | 85 km ÷ approximately 3.5 km/sheet ≈ 25 sheets Final quantity subject to drawing scale and route alignment.
2.14 | High Resolution Orthophotos | km2 | 10 |  |  | Generated from aerial/UAV survey data.
2.15 | KMZ / Google Earth Deliverables | LS | 1 |  |  | For route visualization and stakeholder review.
2.16 | Detailed Engineering & AFC Documentation | LS | 1 |  |  | Covers detailed engineering after FEED completion. Includes AFC drawings, vendor integration, installation details and construction work packs.
2.17 | Integrity Management Philosophy Development | LS | 1 |  |  | Includes development of pipeline integrity management philosophy, inspection strategy, corrosion monitoring, and operational integrity framework.
2.18 | Geotechnical Laboratory Testing | Lot | 1 |  |  | Includes laboratory testing of borehole and CPT samples for geotechnical and pipeline foundation design purposes.
2.19 | Water Quality Assessment | No. | 40 |  |  | Sampling at major water crossings and environmentally sensitive areas. Supports EIA and environmental permitting.
2.2 | Environmental Soil Sampling & Testing | No. | 40 |  |  | Supports environmental baseline and restoration requirements.
2.21 | Geotechnical Interpretation & Design Recommendations Report | LS | 1 |  |  | Includes geotechnical design recommendations for trenching, HDD, buoyancy control and station foundations.
2.22 | Air Quality Monitoring | No. | 20 |  |  | Baseline and construction-phase air quality monitoring.
2.23 | Noise Monitoring | No. | 20 |  |  | Baseline and construction-phase environmental noise assessment.
2.24 | Flora & Fauna Study | LS | 1 |  |  | Ecological baseline survey including vegetation, wildlife and habitat assessment.
2.25 | Fisheries Study | LS | 1 |  |  | Assessment of fisheries resources and potential project impacts on aquatic livelihoods.
2.26 | Socioeconomic Survey | LS | 1
BILL NO. 3.0: Pipeline Procurement & Materials Supply
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
3.1 | Supply and delivery of 20" Nominal OD API 5L X70 PSL2 Line Pipe, Submerged Arc Welded (SAW). Wall Thickness: 12.70 mm. External anti-corrosion coating: 3-Layer Polyethylene (3LPE). | m | 85000
3.2 | Supply and delivery of 20" API 5L X70 bends (induction bends, 3D/5D) for route directional changes. | No. | 80 |  |  | Quantity subject to final route alignment
3.3 | Supply of Tees, Reducers, Flanges, Spectacle Blinds, Weldolets | No. | 106 |  |  | Equal Tees= 2, Reducing Tees= 2, Reducers= 6, Flanges= 40, Blind Flanges= 12, Spectacle Blinds= 4, Weldolets= 40 Total- 2+2+6+40+12+4+40= 106
3.4 | Supply of small bore piping, fittings, gaskets, stud bolts & nuts | LS | 1
3.5 | Supply of 3-Layer Polyethylene (3LPE) heat-shrinkable sleeves for field girth weld joint protection. | No. | 7500
3.6 | Supply and delivery of Cathodic Protection (CP) system components (sacrificial anodes or impressed current systems for swamp terrain). | LS | 1
3.7 | Cathodic Protection (CP) Test Posts | No. | 170 |  |  | Marker every 500 m- 85,000 ÷ 500= 170 Final spacing subject to final CP design
3.8 | Supply of coating repair kits and field coating consumables | LS | 1
3.9 | Supply of Monolithic Insulating Joints (MIJs) | No. | 8 |  |  | Pig launcher, pig receiver, 2 sectionalising valves, tie-ins
3.1 | Pipeline route markers, warning signs and kilometer posts | No. | 341 |  |  | 170 Pipeline Route Markers: Approx. every 500 m along 85 km 85 Warning Sign Posts: Approx. every 1 km 86 Kilometer Marker Posts: 0 km to 85 km
3.11 | Material Receiving, Inspection, Storage & Preservation | LS | 1
3.12 | Pipe Mill Inspection, Mill Testing & Pipe Beveling | LS | 1 |  |  | Includes mill inspection, witness testing, quality surveillance and bevel verification.
BILL NO. 4.0: Right of Way (ROW) & Civil Works
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
4.1 | Clearing and grading of pipeline Right of Way (ROW) up to standard working width (typically 25m–30m) including removal of vegetation and roots. | ha | 255 |  |  | Assuming ROW Width = 30 m Length = 85,000 m Area: 85,000 × 30 = 2,550,000 m² = 255 ha
4.2 | Excavation of pipeline trench to standard minimum depth (ensuring minimum 1.2m cover from top of pipe to natural ground level). Shallow/swamp excavation rules apply. | m3 | 204000 |  |  | Pipeline OD = 0.508 m Typical trench- Width = 1.2 m, Depth = 2.0 m Cross-sectional area= 1.2 × 2.0 = 2.4 m² Length = 85,000 m Volume- 2.4 × 85,000 = 204,000 m³ Final quantities subject to detailed route survey and geotechnical investigations.
4.3 | Stockpiling of excavated topsoil for post-construction reinstatement. | m3 | 40800 |  |  | Topsoil Stockpile is about 20% of excavation volume Final quantities subject to detailed route survey and geotechnical investigations.
4.4 | Construction and maintenance of temporary access roads and swamp access corridors | km | 85 |  |  | Extent subject to terrain conditions and construction methodology.
4.5 | Timber/swamp mats for equipment movement | PS | 1 |  |  | Quantity subject to swamp accessibility assessment and equipment load requirements.
4.6 | Temporary pipe skids and supports | No | 7100 |  |  | One per pipe joint (approx.)
BILL NO. 5.0: Pipeline Construction & NDT
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
5.1 | Stringing of 20" line pipes along the prepared ROW. | Joint | 7100
5.2 | Field welding of 20" line pipes (API 5L X70, 12.70mm WT) in compliance with API 1104 specifications. | Joint | 7100
5.3 | 100% Non-Destructive Testing (NDT) of field girth welds utilizing Automated Ultrasonic Testing (AUT) or Radiographic Testing (RT). | Joint | 7100
5.4 | Application of anti-corrosion coating to field girth welds using heat-shrinkable sleeves including surface blasting to Sa 2.5. | Joint | 7100
5.5 | Lowering-in of the welded pipeline string into the trench, including padding with select clean soil where necessary. | m | 85000
5.6 | Backfilling of trench using native soil, and mechanical compaction to pre-construction profiles. | m3 | 204000 |  |  | Backfill roughly equals excavation volume. Final quantities subject to detailed route survey and geotechnical investigations.
5.7 | Fiber Optic Cable (FOC) Supply & Laying in Trench | m | 85000
5.8 | FOC Splicing, Termination, & Control Room Integration | LS | 1
5.9 | Fiber Optic Joint Boxes / Splice Closures | No. | 25 |  |  | Fiber reel lengths are about 4 km For 85 km route- 85 ÷ 4 km ≈ 21 joints Add Launcher, Receiver & 2 Sectionalising Valves = 25 Quantity subject to final telecom routing and splice plan.
5.1 | Tie-In Works- Hot taps, shutdown tie-ins and cut-overs | LS | 1 |  |  | OKNU and BBOU tie-ins
5.11 | Mechanical completion, punch-list clearing and handover support | LS | 1 |  |  | Final punch-list closure
5.12 | Weld Repairs, Tie-In Welds and Final Closure Welds | No. | 140 |  |  | Weld Repairs= 120, Tie-In Welds= 8 and Final Closure Welds= 12
BILL NO. 6.0: Crossings & HDD
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
6.1 | Major HDD River Crossing | No. | 1
6.2 | Minor River HDD Crossings | PS | 1
6.3 | Creek Crossings | PS | 1
6.4 | Open-cut crossing installations for smaller wetlands, streams, or access roads, including cofferdam construction and bank stabilization. | PS | 1 |  |  | Quantity to be confirmed by detailed route survey and crossing methodology selection.
6.5 | Supply and installation of concrete weight coatings (or bolt-on concrete anchors) for buoyancy control in marshy/swamp segments. | PS | 1 |  |  | Quantity subject to buoyancy and geotechnical analysis
6.6 | Riverbank Shoreline Stabilization (River Niger + 4 Rivers) | No. | 5
6.7 | Existing pipeline, cable and utility crossings | PS | 1 |  |  | Quantity to be confirmed by detailed route survey
6.8 | Road crossings including casing installation | PS | 1 |  |  | Quantity to be confirmed by detailed route survey
6.9 | Dredging Works | PS | 1 |  |  | Applicable only where required by detailed crossing design
6.1 | Watercourse Restoration | No. | 15 |  |  | 1 major river + 4 river crossings + 8 creek crossings + 2 contingency locations. Includes bank stabilization, erosion control, cleanup, and reinstatement of disturbed watercourse areas.
BILL NO. 7.0: Stations, Valves & Pigging Facilities
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
7.1 | Civil foundation works and security fencing for the OKNU Pig Launcher Station and BBOU Pig Receiver Station. | No. | 2
7.2 | Procurement, fabrication, and installation of the 20" Pig Launcher Assembly at OKNU manifold, including quick-opening closures, kicker lines, bypass piping, and structural supports. | No. | 1
7.3 | Procurement, fabrication, and installation of the 20" Pig Receiver Assembly at BBOU manifold, including slug handling tying structures. | No. | 1
7.4 | 20" Full Bore Ball Valves, Valve Actuators, Valve Bypass Assemblies & Valve Control Panels | No. | 28 |  |  | 20" Full Bore Ball Valves= 10, Valve Actuators= 10, Valve Bypass Assemblies= 4 & Valve Control Panels= 4 Total- 10+10+4+4= 28
7.5 | Pig Signallers | No. | 4 |  |  | Two signallers at launcher facility and two at receiver facility. Provides pig passage indication for operations and maintenance.
7.6 | Sectionalising Valve Stations | No. | 2 |  |  | In accordance with ASME B31.8 spacing requirements
7.7 | Automated Midline Manifold Assembly (KP 38 SEIB Tie-In) | PS | 1 |  |  | Provisional Sum pending final tie-in confirmation.
7.8 | Midline Manifold Foundation/Valving Allowance (KP 66 Tie-In) | PS | 1 |  |  | Provisional Sum pending final tie-in confirmation.
7.9 | Design, Procurement, Construction and Commissioning of Slug Catcher | PS | 1 |  |  | Subject to confirmation by FEED Flow Assurance Studies
7.1 | Emergency Shutdown System (ESD) | LS | 1 |  |  | For pigging/valve facilities
BILL NO. 8.0: Instrumentation, SCADA Telecoms & Solar Systems
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
8.1 | Pressure transmitters, temperature transmitters, flow monitoring instruments | LS | 1
8.2 | SCADA system, RTUs, telemetry and communications integration | LS | 1
8.3 | Cybersecurity & SCADA Hardening | LS | 1
8.4 | Solar power systems and battery banks | No. | 4 |  |  | For unmanned remote valve stations and pigging facilities
BILL NO. 9.0: Testing, Pre-commissioning & Dewatering
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
9.1 | Pipeline Cleaning Pig Runs | LS | 1 |  |  | To be performed before hydrotest and commissioning.
9.2 | Hydrostatic testing of the entire 85 km pipeline segment in designated sections per ASME B31.8, including water sourcing, filtration, inhibition, pressurization, and safe disposal. | km | 85 |  |  | Test sections and test medium requirements subject to final testing procedure.
9.3 | Pipeline dewatering, swabbing, and geometric gauge pigging to check for internal ovality or construction defects. | LS | 1
9.4 | Air drying and vacuum drying of the line to specified dewpoint parameters (-40°C). | LS | 1
9.5 | Nitrogen purging and preservation of the pipeline until ready for active natural gas introduction. | LS | 1 |  |  | Applicable where required prior to commissioning and start-up.
9.6 | Intelligent pigging readiness verification and baseline geometry pigging | LS | 1 |  |  | To confirm future pigging and integrity management requirements.
9.7 | Leak testing and commissioning support | LS | 1
9.8 | Operations & Maintenance Training | LS | 1 |  |  | Training for operations personnel. Includes classroom and field training for pipeline operations, pigging, CP systems, SCADA and emergency response.
9.9 | Operations Readiness Support | LS | 1 |  |  | Preparation for handover to operations. Includes operating procedures review, maintenance planning support, spare parts review and operational readiness assessments.
BILL NO. 10.0: Construction Management
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
10.1 | Construction Management & Site Supervision | Month | Proj. Duration |  |  | Includes Construction Manager, Site Engineers, discipline supervision, contractor coordination, work-front planning and daily construction oversight.
10.2 | Project Controls, Planning & Scheduling | Month | Proj. Duration |  |  | Includes planning, scheduling, progress measurement, earned-value tracking, forecasting, change management and monthly reporting.
10.3 | QA/QC Management & Inspection Coordination | Month | Proj. Duration |  |  | Includes QA/QC management, inspection coordination, ITP compliance, audit support, NCR management and turnover dossier review.
10.4 | Construction Reporting & Document Control | Month | Proj. Duration |  |  | Includes document control, transmittals, construction records, daily/weekly/monthly reports and close-out documentation support.
10.5 | Construction HSE Management & Compliance | Month | Proj. Duration |  |  | Includes HSE management personnel, safety audits, toolbox talks, incident reporting, regulatory compliance monitoring, emergency preparedness and HSE performance reporting.
BILL NO. 11.0: Environmental, Regulatory & Closeout
Item | Description | Unit | Qty | Rate | Amount | Basis & Remarks
11.1 | Stakeholder Engagement & Community Consultation Meetings | LS | 1 |  |  | Supports permitting, social license and FTO activities.
11.2 | Managing Community Liaison Officer (CLO) operations, Freedom to Operate (FTO) certificates, and local community development mandates. | LS | 1
11.3 | As-Built mapping, generating final documentation handovers, and obtaining regulatory operation permits from NUPRC/FMEnv. | LS | 1 |  |  | Includes final as-built records, dossiers and handover documentation.
11.4 | Marine Navigation & Waterways Permits | LS | 1 |  |  | Includes NIWA, waterways access permits and navigation approvals where applicable.
11.5 | Environmental monitoring and restoration | LS | 1 |  |  | Includes reinstatement of temporary work areas and access routes.
11.6 | Final RoW reinstatement and vegetation restoration | km | 85 |  |  | Entire route. Includes restoration of disturbed areas to pre-construction condition
11.7 | Regulatory Compliance Closeout | LS | 1 |  |  | Explicitly captures final NUPRC/NOSDRA/NCDMB closeout activities.
11.8 | EPC Project Management, Planning, Cost Control & Reporting | Month | Proj. Duration |  |  | Includes EPC project management, planning, scheduling, cost control, progress reporting, and document control services throughout project execution.

## Cost Reporting Structure
Cost Reporting Structure
A | Engineering & Surveys Costs
| BOQ Bill No. | Description | Unit | Quantity | Rate (USD) | Amount (USD)
| 2.1 | Topographical survey and Differential GPS (DGPS) Survey | km | 85
| 2.2 | Longitudinal Profile and Cross-Section Survey | km | 85
| 2.3 | Bathymetric survey | km | 25
| 2.4 | Route center-line staking survey | km | 85
| 2.5 | Establishment of Survey Control Points & Permanent Reference Monuments | No. | 50
| 2.6 | Geotechnical soil boring investigations | Borehole | 42
| 2.7 | Cone Penetration Tests (CPT) | No. | 85
| 2.8 | Trial Pits | No. | 30
| 2.9 | Soil Corrosivity Assessment | Lot | 1
| 2.1 | Finalization of detailed pipeline drawings, alignment sheets, P&IDs, and Stress Analysis reports. | LS | 1
| 2.11 | Full EIA Survey Package & Permitting Management | LS | 1
| 2.12 | GIS Database Development | LS | 1
| 2.13 | Corridor Alignment Sheets | No. | 25
| 2.14 | High Resolution Orthophotos | km2 | 10
| 2.15 | KMZ / Google Earth Deliverables | LS | 1
| 2.16 | Detailed Engineering & AFC Documentation | LS | 1
| 2.17 | Integrity Management Philosophy Development | LS | 1
| 2.18 | Geotechnical Laboratory Testing | Lot | 1
| 2.19 | Water Quality Assessment | No. | 40
| 2.2 | Environmental Soil Sampling & Testing | No. | 40
| 2.21 | Geotechnical Interpretation & Design Recommendations Report | LS | 1
| 2.22 | Air Quality Monitoring | No. | 20
| 2.23 | Noise Monitoring | No. | 20
| 2.24 | Flora & Fauna Study | LS | 1
| 2.25 | Fisheries Study | LS | 1
| 2.26 | Socioeconomic Survey | LS | 1
| 8.2 | SCADA system, RTUs, telemetry and communications integration | LS | 1
| 8.3 | Cybersecurity & SCADA Hardening | LS | 1
B | Materials & Equipment Costs
| BOQ Bill No. | Description | Unit | Quantity | Rate (USD) | Amount (USD)
| 3.1 | 20" Nominal OD API 5L X70 PSL2 Line Pipe, Submerged Arc Welded (SAW). Wall Thickness: 12.70 mm. External anti-corrosion coating: 3-Layer Polyethylene (3LPE). | m | 85000
| 3.2 | 20" API 5L X70 bends (induction bends, 3D/5D) for route directional changes. | No. | 80
| 3.3 | Tees, Reducers, Flanges, Spectacle Blinds, Weldolets | No. | 106
| 3.4 | Small bore piping, fittings, gaskets, stud bolts & nuts | LS | 1
| 3.5 | 3-Layer Polyethylene (3LPE) heat-shrinkable sleeves for field girth weld joint protection. | No. | 7500
| 3.6 | Cathodic Protection (CP) system components (sacrificial anodes or impressed current systems for swamp terrain). | LS | 1
| 3.7 | Cathodic Protection (CP) Test Posts | No. | 170
| 3.8 | Coating repair kits and field coating consumables | LS | 1
| 3.9 | Monolithic Insulating Joints (MIJs) | No. | 8
| 3.1 | Pipeline route markers, warning signs and kilometer posts | No. | 341
| 3.11 | Material Receiving, Inspection, Storage & Preservation | LS | 1
| 3.12 | Pipe Mill Inspection, Mill Testing & Pipe Beveling | LS | 1
| 7.2 | 20" Pig Launcher Assembly at OKNU manifold, including quick-opening closures, kicker lines, bypass piping, and structural supports. | No. | 1
| 7.3 | 20" Pig Receiver Assembly at BBOU manifold, including slug handling tying structures. | No. | 1
| 7.4 | 20" Full Bore Ball Valves, Valve Actuators, Valve Bypass Assemblies & Valve Control Panels | No. | 28
| 7.5 | Pig Signallers | No. | 4
| 7.6 | Sectionalising Valve Stations | No. | 2
| 7.7 | Automated Midline Manifold Assembly (KP 38 SEIB Tie-In) | PS | 1
| 7.8 | Midline Manifold Foundation/Valving Allowance (KP 66 Tie-In) | PS | 1
| 7.9 | Slug Catcher | PS | 1
| 7.1 | Emergency Shutdown System (ESD) | LS | 1
| 8.1 | Pressure transmitters, temperature transmitters, flow monitoring instruments | LS | 1
| 8.4 | Solar power systems and battery banks | No. | 4
C | Construction & Installation Costs
| BOQ Bill No. | Description | Unit | Quantity | Rate (USD) | Amount (USD)
| 1.3 | Construction of temporary project site offices, camps, workshops, and pipe stockyards near OKNU and BBOU. | LS | 1
| 4.1 | Clearing and grading of pipeline Right of Way (ROW) up to standard working width (typically 25m–30m) including removal of vegetation and roots. | ha | 255
| 4.2 | Excavation of pipeline trench to standard minimum depth (ensuring minimum 1.2m cover from top of pipe to natural ground level). Shallow/swamp excavation rules apply. | m3 | 204000
| 4.3 | Stockpiling of excavated topsoil for post-construction reinstatement. | m3 | 40800
| 4.4 | Construction and maintenance of temporary access roads and swamp access corridors | km | 85
| 4.6 | Temporary pipe skids and supports | No | 7100
| 5.1 | Stringing of 20" line pipes along the prepared ROW. | Joint | 7100
| 5.2 | Field welding of 20" line pipes (API 5L X70, 12.70mm WT) in compliance with API 1104 specifications. | Joint | 7100
| 5.3 | 100% Non-Destructive Testing (NDT) of field girth welds utilizing Automated Ultrasonic Testing (AUT) or Radiographic Testing (RT). | Joint | 7100
| 5.4 | Application of anti-corrosion coating to field girth welds using heat-shrinkable sleeves including surface blasting to Sa 2.5. | Joint | 7100
| 5.5 | Lowering-in of the welded pipeline string into the trench, including padding with select clean soil where necessary. | m | 85000
| 5.6 | Backfilling of trench using native soil, and mechanical compaction to pre-construction profiles. | m3 | 204000
| 5.7 | Fiber Optic Cable (FOC) Supply & Laying in Trench | m | 85000
| 5.8 | FOC Splicing, Termination, & Control Room Integration | LS | 1
| 5.9 | Fiber Optic Joint Boxes / Splice Closures | No. | 25
| 5.1 | Tie-In Works- Hot taps, shutdown tie-ins and cut-overs | LS | 1
| 5.11 | Mechanical completion, punch-list clearing and handover support | LS | 1
| 5.12 | Weld Repairs, Tie-In Welds and Final Closure Welds | No. | 140
| 6.1 | Major HDD River Crossing | No. | 1
| 6.2 | Minor River HDD Crossings | PS | 1
| 6.3 | Creek Crossings | PS | 1
| 6.4 | Open-cut crossing installations for smaller wetlands, streams, or access roads, including cofferdam construction and bank stabilization. | PS | 1
| 6.5 | Supply and installation of concrete weight coatings (or bolt-on concrete anchors) for buoyancy control in marshy/swamp segments. | PS | 1
| 6.6 | Riverbank Shoreline Stabilization (River Niger + 4 Rivers) | No. | 5
| 6.7 | Existing pipeline, cable and utility crossings | PS | 1
| 6.8 | Road crossings including casing installation | PS | 1
| 6.9 | Dredging Works | PS | 1
| 6.1 | Watercourse Restoration | No. | 15
| 7.1 | Civil foundation works and security fencing for the OKNU Pig Launcher Station and BBOU Pig Receiver Station. | No. | 2
| 9.1 | Pipeline Cleaning Pig Runs | LS | 1
| 9.2 | Hydrostatic testing of the entire 85 km pipeline segment in designated sections per ASME B31.8, including water sourcing, filtration, inhibition, pressurization, and safe disposal. | km | 85
| 9.3 | Pipeline dewatering, swabbing, and geometric gauge pigging to check for internal ovality or construction defects. | LS | 1
| 9.4 | Air drying and vacuum drying of the line to specified dewpoint parameters (-40°C). | LS | 1
| 9.5 | Nitrogen purging and preservation of the pipeline until ready for active natural gas introduction. | LS | 1
| 9.6 | Intelligent pigging readiness verification and baseline geometry pigging | LS | 1
| 9.7 | Leak testing and commissioning support | LS | 1
| 9.8 | Operations & Maintenance Training | LS | 1
| 9.9 | Operations Readiness Support | LS | 1
D | Logistics & Transportation Costs
| BOQ Bill No. | Description |  | Quantity | Rate (USD) | Amount (USD)
| 1.1 | Contractor mobilization of plant, equipment, and personnel to operational bases.
| 1.2 | Procurement of Project All Risks Insurance and performance bonds.
| 1.4 | Temporary Camp Utilities (Power, Water, Communications)
| 1.5 | Maintenance of Site Health, Safety, and Environment (HSE) systems, personal protective equipment (PPE), and waste disposal programs.
| 1.6 | Pipe Transportation (Port Handling, Customs Clearance & Inland Transport)
| 1.7 | Marine Logistics
| 1.8 | Personnel Transportation
| 1.9 | Fuels & Consumables
| 1.1 | Security Logistics
| 4.5 | Timber/swamp mats for equipment movement
E | Indirect Costs
| BOQ Bill No. | Description |  | Quantity | Rate (USD) | Amount (USD)
| 10.1 | Construction Management & Site Supervision
| 10.2 | Project Controls, Planning & Scheduling
| 10.3 | QA/QC Management & Inspection Coordination
| 10.4 | Construction Reporting & Document Control
| 10.5 | Construction HSE Management & Compliance
| 11.1 | Stakeholder Engagement & Community Consultation Meetings
| 11.2 | Managing Community Liaison Officer (CLO) operations, Freedom to Operate (FTO) certificates, and local community development mandates.
| 11.3 | As-Built mapping, generating final documentation handovers, and obtaining regulatory operation permits from NUPRC/FMEnv.
| 11.4 | Marine Navigation & Waterways Permits
| 11.5 | Environmental monitoring and restoration
| 11.6 | Final RoW reinstatement and vegetation restoration
| 11.7 | Regulatory Compliance Closeout
| 11.8 | EPC Project Management, Planning, Cost Control & Reporting
Cost Distribution
| S/N | Cost Category |  | % of Total Cost | Budget Weight
| A | Engineering & Survey |  | 5 - 8% | 7%
| B | Materials & Equipment |  | 35 - 45% | 42%
| C | Construction & Installation |  | 30 - 40% | 34%
| D | Logistics & Transportation |  | 8 - 12% | 10%
| E | Indirect |  | 5 - 10% | 7%